## D&NH
Government of India
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2018-19
UT : Dadra & Nagar Haveli
Part-D: ANALYSIS SHEET
Section-A : REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2018-19(1.4.17 to 31.03.18)
1. Calculation of Bench mark for utilisation.
1.1) No. of children
Stage | MDM PAB Approval for 2017-18 | Average number of children availed MDM during 1.4.17 to 31.03.18 (AT-5&5A) | Diff. | Diff in %
1 | 2 | 3 | 4=(3-2) | 5=(4/2)*100
Primary | 19500 | 22060.9542 | 2560.9542 | 13.13%
Up Primary | 13900 | 10402.3708 | -3497.6292 | -25.16%
Total | 33400 | 32463.325 | -936.675 | -2.804%
1.2) No. of School working days upto the 31-03-2018
Stage | As per PAB Approval 2017-18 | No of Day Covered | Diff. | Diff. in %
PY | 231 | 240 | 9 | 3.896%
UP.PY | 231 | 240 | 9 | 3.896%
i) Base period 01.04.17 to 31.03.18 (As per PAB aaproval = 231 days for Py & U Py)
Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Diff. | Diff in %
PY | 4504500 | 5294629 | 790129 | 17.54% |  |  |  | 218.6682
UP PY | 3210900 | 2496569 | -714331 | -22.25% |  |  |  | 154.288
Total | 7715400 | 7791198 | 75798 | 0.9824%
2. COVERAGE
2.1 Institutions- (Primary) (Source data : Table AT-3A of AWP&B 2018-19)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Dadra & Nagar Haveli | 161 | 161 | 0 | 0%
2.2 Institutions- (Primary with Upper Primary) (Source data : Table AT-3B of AWP&B 2018-19)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Dadra & Nagar Haveli | 119 | 119 | 0 | 0
2.2A Institutions- (Upper Primary) (Source data : Table AT-3C of AWP&B 2018-19)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Dadra & Nagar Haveli | 0 | 0 | 0 | 0%
2.3 Coverage Chidlren vs. Enrolment ( Primary) (Source data : Table AT-4 & 5 of AWP&B 2018-19)
Sl. No. | Districts | Enrolment as on 30.9.2017 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Dadra & Nagar Haveli | 28296 | 22060.9542 | -6235.0458 | -22.04%
2.4 Coverage Chidlren vs. Enrolment ( Upper Primary) (Source data : Table AT- 4A & 5-A of AWP&B 2017-18)
Sl. No. | Districts | Enrolment as on 30.9.2017 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Dadra & Nagar Haveli | 14085 | 10402.3708 | -3682.6292 | -26.15%
2.5 No. of children ( Primary) (Source data : Table AT-5 of AWP&B 2018-19)
Sl. No. | Districts | No. of children as per PAB Approval for 2017-18 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Dadra & Nagar Haveli | 19500 | 22060.9542 | 2560.9542 | 13.13%
2.6 No. of children ( Upper Primary) (Source data : Table AT-5-A of AWP&B 2018-19)
Sl. No. | Districts | No. of children as per PAB Approval for 2017-18 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Dadra & Nagar Haveli | 13900 | 10402.3708 | -3497.6292 | -25.16%
2.7 Number of meal to be served and actual number of meal served during 2017-18 (Source data: Table AT-5 & 5A of AWP&B 20117-18)
Sr. No. | District | No of meals to be served during 1.4.17 to 31.03.18 | No of meal served during 1.4.17 to 31.03.18 | % Meals Served
1 | 2 | 3 | 4 | 5
1 | Dadra & Nagar Haveli | 7715400 | 7791198 | 101%
2.8. Aadhaar Enrolment (Data Source Table : AT-4B of AWP&B 2018-19)
S.No. | Name of District | Total Enrolment | Number of children having Aadhaar | Number of children applied for Aadhaar | % having aadhaar Enrl
1 | 2 | 3 | 4 | 5 | 6
1 | D&N.H | 42381 | 34408 | 7973 | 100%
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 1.4.2017 | 0 | 0 | 0 | 0%
2 | Allocation for 2017-18 | 932.09 | 932.09 | 0 | 0% |  | 450.45
3 | Lifting as on 31.03.2018 | 913.73 | 913.73 | 0 | 0% |  | 481.635
932.085
3.2) District-wise opening balance as on 1.4.2017 (Source data: Table AT-6 & 6A of AWP&B 2018-19)
(in MTs)
S.No. | Name of District | Allocation for 2017-18 | Opening Stock as on 1.4.2017 | % of OS on allocation 2017-18
1 | 2 | 3 | 4 | 5
1 | Dadra & Nagar Haveli | 932.09 | 0 | 0%
3.3) District-wise unspent balance as on 31.03.2018(Source data: Table AT-6 & 6A of AWP&B 2018-19)
(in MTs)
S.No. | Name of District | Allocation for 2017-18 | Unspent Balance as on 31.03.2018 | % of UB on allocation 2017-18
1 | 2 | 3 | 4 | 5
1 | Dadra & Nagar Haveli | 932.09 | -39.02 | -4.186%
3.4) Foodgrains Allocation & Lifting
(in MTs)
Allocation | Unspent balance as on 31.3.18 | Lifting upto 31.03.18 | Total Availibility | % Availibility
932.09 | -39.02 | 913.73 | 913.73 | 98.03%
Source: Table AT-6 & 6A of AWP&B 2017-18
3.5) District-wise Foodgrains availability as on 31.03.18 (Source data: Table AT-6 & 6A of AWP&B 2018-19)
(in MTs)
Sl. No. | District | Allocation | OB as on 1.4.2017 | Lifted from FCI | Total Availibility | % Availibility
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Dadra & Nagar Haveli | 932.09 | 0 | 913.73 | 913.73 | 98.03%
3.6) Foodgrains Allocation, Lifting (availibility) & Utilisation
Allocation | T. Availibility | % T. Availibility | Utilisation | % Utilisation
932.09 | 913.73 | 98.03% | 952.754 | 102.2%
3.7) District-wise Utilisation of foodgrains (Source data: Table AT-6 & 6A of AWP&B 2018-19)
Sl. No. | District | Allocation | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5
1 | Dadra & Nagar Haveli | 932.09 | 952.754 | 102.2%
3.8) Cost of Foodgrains, Payment to FCI
Allocation | Bills submited by FCI | Payment made to FCI | % payment
24.48 | 27.68 | 27.68 | 100%
3.9) Payment of cost of foodgrain to FCI
Sl. No. | District | Allocation | Bills raised by FCI | Payment to FCI | Pending Bills | % Bill paid
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Dadra & Nagar Haveli | 24.48 | 27.68 | 27.68 | 0 | 100%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 1.4.2017 (Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2017-18 | Opening Balance as on 1.4.2017 | % of OB on allocation 2017-18
1 | 2 | 3 | 4 | 5
1 | Dadra & Nagar Haveli | 1131.16 | 0 | 0%
4.1.2) District-wise unspent balance as on 31.03.2018 Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2017-18 | Unspent Balance as on 31.03.2018 | % of UB on allocation 2017-18
1 | 2 | 3 | 4 | 5
1 | Dadra & Nagar Haveli | 1131.16 | -517.98 | -45.79%
4.2) Cooking cost allocation and disbursed to Dists
Allocation | OB as on 1.4.17 | Disbursed to Dist | Total Availibility | % Availibility
1131.16 | 0 | 634.45 | 634.45 | 56.09%
4.3) District-wise Cooking Cost availability (Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2017-18 | Opening Balance as on 1.4.2017 | Cooking assistance received | Total Availibility of cooking cost | % Availibility of cooking cost
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Dadra & Nagar Haveli | 1131.16 | 0 | 634.45 | 634.45 | 56.09%
4.4) Cooking Cost Utilisation
Allocation | Disbursed | % Disbursed | Utilisation | % Utilisation
1131.16 | 634.45 | 56.09% | 1152.43 | 101.9%
4.5) District-wise Utilisation of Cooking cost (Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2017-18 | Utilisation of Cooking assistance | % Utilisation
1 | 2 | 3 | 4 | 5
1 | Dadra & Nagar Haveli | 1131.16 | 1152.43 | 101.9%
5. Reconciliation of Utilisation and Performance during 2017-18 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost (Source data: para 3.7 and 4.5 above)
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | Dadra & Nagar Haveli | 102.2% | 101.9% | -0.3366%
5.2 Reconciliation of Food grains utilisation during 2017-18 (Source data: para 2.7 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 01.4.15 to 31.03.18 | Expected consumption of food grains | Actual consumption of food grains | % consumption
1 | 2 | 3 | 4 | 5 | 6 |  |  |  | Expected -Cm _FG | Pry | Upry | Total
1 | Dadra & Nagar Haveli | 7715400 | 932.085 | 952.754 | 102.2% |  |  |  |  | 450.45 | 481.635 | 932.085
5.3 Reconciliation of Cooking Cost utilisation during 2017-18(Source data: para 2.5 and 4.5 above)
(Rs. in Lakh)
Sr. No. | District | No. of Meals served during 01.4.17 to 31.03.18 | Expected expenditure of cooking cost | Actual expenditure of cooking cost | % consumption
1 | 2 | 3 | 4 | 5 | 6 |  |  |  | Expected -Ex _CC | Pry | Upry | Total
1 | Dadra & Nagar Haveli | 7715400 | 1131.1631 | 1152.43 | 101.9% |  |  |  |  | 186.0359 | 198.4336 | 384.4695
6. ANALYSIS of HONORIUM, To COOK-CUM-HELPERS
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers (Refer table AT_8 and AT-8A,AWP&B, 2018-19)
S.No. | Name of District | PAB Approval for 2017-18 | Engaged by State | Not engaged
1 | 2 | 3 | 4 | 5 = (4 - 3)
1 | Dadra & Nagar Haveli | 925 | 925 | 0
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers (Refer table AT_8 and AT-8A,AWP&B, 2018-19)
S.No. | Name of District | Allocation for 2017-18 | Opening Balance as on 1.4.2017 | Amount released | Total availability | % Availibilty
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Dadra & Nagar Haveli | 298.58 | 0 | 273.1 | 273.1 | 91.47%
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers Refer table AT_8 and AT-8A,AWP&B, 2018-19
S.No. | Name of District | Allocation for 2017-18 | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation
1 | 2 | 3 | 4 | 5 | 6
1 | Dadra & Nagar Haveli | 298.58 | 273.1 | 273.1 | 91.47%
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers (Refer table AT_8 and AT-8A,AWP&B, 2018-19)
S.No. | Name of District | Allocation for 2017-18 | Total Availability | Unspent balance as on 31.03.2018 | % of UB as on Allocation 2017-18
1 | 2 | 3 | 4 | 5 | 6
1 | Dadra & Nagar Haveli | 298.58 | 273.1 | -20.5 | -6.866%
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
7.1) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2017-18 | 30 | 30 | 0 | 0%
2 | Opening Balance as on 1.4.2017 | 0 | 0 | 0 | 0%
3 | Released during 2017-18 | 30 | 30 | 0 | 0%
4 | Total Availibility | 30 | 30 | 0 | 0%
7.2) Utilisation of MME during 2017-18 (Source data: Table AT-10 of AWP&B 2018-19)(Rs. In lakh)
(As on 31.12.17)
Sl. No. | Activity | Allocated for 2017-18 | Total Availibility | Expenditure | Exp as % of allocation
1 | 2 | 3 | 4 | 5 | 6
1 | School Level Expenses | 15 | 15 | 15 | 100%
2 | Management, Supervision, Training & Internal Monitoring, External Monitoring & Evaluation | 15 | 15 | 15 | 100%
Total |  | 30 | 30 | 30 | 100%
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
8.1) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Activity | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2017-18 | 6.99 | 6.99 | 0 | 0%
2 | Opening Balance as on 1.4.2017 | 0 | 0 | 0 | 0%
3 | Released during 2017-18 | 6.02 | 6.02 | 0 | 0%
4 | Total Availibility | 6.02 | 6.02 | 0 | 0%
8.2) Utilisation of TA during 2017-18 (Source data: Table AT-9 of AWP&B 2018-19)
(Rs. In lakh)
Allocated for 2017-18 | Total availibility of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7
6.99 | 6.02 | 913.73 | 6.853 | 6.02 | 0.83298 | 86.12%
9. INFRASTRUCTURE DEVELOPMENT DURING 2017-18 (Primary + Upper primary)
Kitchen-cum-Stores
9.1) Releasing details
Releases for Kitchen sheds by GoI
Schools | Installment | Dated | Units | Amount (in lakh)
Primary + Upper Primary | 2011-12 |  | 50 | 65.52
2012-13
2013-14
2014-15
2015-16
| 2016-17 |  | *100 | 0
2017-18
| Grand Total |  | 50 | 65.52
*100 units was approved by PAB -2016-17 waiting for details proposal from UT. This year no requirement.
9.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-18 | 50 | 65.52 | 50 | 16.24 | 0% | 75.21%
9.3) Achievement ( under MDM Funds) (Source data: Table AT-10 of AWP&B 2018-19)
Sanctioned by GoI during 2006-07 to 2017-18 |  | Achievement (C) upto 31.12.18 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
50 | 65.52 | 50 | 16.24 | 100% | 24.79%
10. Kitchen Devices
10.1) Releasing details
Releases for Kitchen devices by GoI
Schools | Installment | Dated | Units | Amount (in lakh)
Primary + Upper Primary | 2006-07
2007-08
2008-09
2009-10
| 2012-13 |  | 283 | 14.15
2013-14
2014-15
2015-16
2016-17
2017-18
| Grand Total |  | 283 | 14.15
10.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-18 | 283 | 14.15 | 283 | 14.15 | 0% | 0%
10.3) Achievement ( under MDM Funds) (Source data: Table AT-12 of AWP&B 2018-19)
Sactioned during 2006-07 to 2017-18 |  | Achievement (C+IP) upto 31.03-2018 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
283 | 14.15 | 283 | 14.15 | 100% | 100%
Benchmark (85%)
100%
68%