## Haryana
Government of India
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2018-19
State : Haryana
Part-D: ANALYSIS SHEET
Section-A : REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2017-18 (1.4.17 to 31.03.18)
1. Calculation of Bench mark for utilisation.
1.1) No. of children
Stage | MDM PAB Approval for 2017-18 | Average number of children availed MDM during 1.4.17 to 31.03.18 (AT-5&5A) | Diff | Diff in %
1 | 2 | 3 | 4=(3-2) | 5=(4/2)*100
Primary | 841135 | 927837 | 86702 | 10.31%
Up Primary | 579943 | 621827 | 41884 | 7.222%
NCLP | 5415 | 1675 | -3740 | -69.07%
Total | 1426493 | 1551339 | 124846 | 8.752%
1.2) No. of School working days
PY | 242 | 225 | -17 | -7.025%
UP.PY | 242 | 225 | -17 | -7.025%
NCLP | 302 | 235 | -67 | -22.19%
i) Base period 01.04.17 to 31.03.18
Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Diff. | Diff in %
PY | 203554670 | 208369711 | 4815041 | 2.365%
UP PY | 140346206 | 139911022.575 | -435183.425 | -0.3101%
NCLP | 1635330 | 393678 | -1241652 | -75.93%
Total | 345536206 | 348674411.575 | 3138205.575 | 0.9082%
ii) Base period 01.04.17 to 31.03.18 (As per PAB aaproval = 242 days for Py & U Py and 302 for NCLP )
Stage | No. of Meals as per PAB approval (01.04.17 to 31.3.18) | No. of Meals claimed to have served by the State |  | Diff in %
PY | 203554670 | 208369711 |  | 102.4%
U PY | 140346206 | 139911022.575 |  | 99.69%
NCLP | 1635330 | 393678 |  | 24.07%
Total | 343900876 | 348280733.575 |  | 101.3%
2. COVERAGE
2.1 Institutions- (Primary) (Source data : Table AT-3A of AWP&B 2018-19)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Ambala | 503 | 503 | 0 | 0%
2 | Bhiwani | 656 | 656 | 0 | 0%
3 | Faridabad | 247 | 247 | 0 | 0%
4 | Fatehabad | 387 | 387 | 0 | 0%
5 | Gurugram | 392 | 392 | 0 | 0%
6 | Hissar | 509 | 509 | 0 | 0%
7 | Jhajjar | 301 | 301 | 0 | 0%
8 | jind | 432 | 432 | 0 | 0%
9 | Kaithal | 373 | 373 | 0 | 0%
10 | karnal | 489 | 489 | 0 | 0%
11 | Kurukshetra | 492 | 492 | 0 | 0%
12 | Mahendergarh | 476 | 476 | 0 | 0%
13 | Mewat | 482 | 482 | 0 | 0%
14 | Palwal | 360 | 360 | 0 | 0%
15 | Panchkula | 133 | 133 | 0 | 0%
16 | Panipat | 249 | 249 | 0 | 0%
17 | Rewari | 220 | 220 | 0 | 0%
18 | Rohtak | 231 | 231 | 0 | 0%
19 | sirsa | 529 | 529 | 0 | 0%
20 | Sonipat | 438 | 438 | 0 | 0%
21 | Yamunanagar | 254 | 254 | 0 | 0%
| TOTAL | 8153 | 8153 | 0 | 0%
2.2 Institutions- (Primary with Upper Primary) (Source data : Table AT-3B of AWP&B 2018-19)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Ambala | 173 | 173 | 0 | 0
2 | Bhiwani | 307 | 307 | 0 | 0
3 | Faridabad | 368 | 368 | 0 | 0
4 | Fatehabad | 142 | 142 | 0 | 0
5 | Gurugram | 121 | 121 | 0 | 0
6 | Hissar | 262 | 262 | 0 | 0
7 | Jhajjar | 179 | 179 | 0 | 0
8 | jind | 216 | 216 | 0 | 0
9 | Kaithal | 149 | 149 | 0 | 0
10 | karnal | 170 | 170 | 0 | 0
11 | Kurukshetra | 189 | 189 | 0 | 0
12 | Mahendergarh | 145 | 145 | 0 | 0
13 | Mewat | 81 | 81 | 0 | 0
14 | Palwal | 105 | 105 | 0 | 0
15 | Panchkula | 144 | 144 | 0 | 0
16 | Panipat | 123 | 123 | 0 | 0
17 | Rewari | 189 | 189 | 0 | 0
18 | Rohtak | 144 | 144 | 0 | 0
19 | sirsa | 187 | 187 | 0 | 0
20 | Sonipat | 217 | 217 | 0 | 0
21 | Yamunanagar | 499 | 499 | 0 | 0
| TOTAL | 4110 | 4110 | 0 | 0
2.2A Institutions- (Upper Primary) (Source data : Table AT-3C of AWP&B 2018-19)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Ambala | 144 | 144 | 0 | 0%
2 | Bhiwani | 159 | 159 | 0 | 0%
3 | Faridabad | 130 | 130 | 0 | 0%
4 | Fatehabad | 88 | 88 | 0 | 0%
5 | Gurugram | 91 | 91 | 0 | 0%
6 | Hissar | 99 | 99 | 0 | 0%
7 | Jhajjar | 53 | 53 | 0 | 0%
8 | jind | 100 | 100 | 0 | 0%
9 | Kaithal | 73 | 73 | 0 | 0%
10 | karnal | 120 | 120 | 0 | 0%
11 | Kurukshetra | 118 | 118 | 0 | 0%
12 | Mahendergarh | 135 | 135 | 0 | 0%
13 | Mewat | 343 | 343 | 0 | 0%
14 | Palwal | 144 | 144 | 0 | 0%
15 | Panchkula | 143 | 143 | 0 | 0%
16 | Panipat | 58 | 58 | 0 | 0%
17 | Rewari | 251 | 251 | 0 | 0%
18 | Rohtak | 37 | 37 | 0 | 0%
19 | sirsa | 122 | 122 | 0 | 0%
20 | Sonipat | 81 | 81 | 0 | 0%
21 | Yamunanagar | 238 | 238 | 0 | 0%
| TOTAL | 2727 | 2727 | 0 | 0%
2.3 Coverage Chidlren vs. Enrolment ( Primary) (Source data : Table AT-4 & 5 of AWP&B 2018-19)
Sl. No. | Districts | Enrolment as on 30.9.2017 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Ambala | 35353 | 35168.2844 | -184.7156 | -0.5225%
2 | Bhiwani | 52382 | 51441.5289 | -940.4711 | -1.795%
3 | Faridabad | 46268 | 45378.5733 | -889.4267 | -1.922%
4 | Fatehabad | 44521 | 43489.28 | -1031.72 | -2.317%
5 | Gurugram | 52691 | 44264.7867 | -8426.2133 | -15.99%
6 | Hissar | 57775 | 54003.7467 | -3771.2533 | -6.527%
7 | Jhajjar | 20053 | 17336.9911 | -2716.0089 | -13.54%
8 | jind | 46966 | 44915.8311 | -2050.1689 | -4.365%
9 | Kaithal | 43371 | 42135.6044 | -1235.3956 | -2.848%
10 | karnal | 51840 | 48125.52 | -3714.48 | -7.165%
11 | Kurukshetra | 34269 | 34006.3022 | -262.6978 | -0.7666%
12 | Mahendergarh | 24644 | 23667.5289 | -976.4711 | -3.962%
13 | Mewat | 107457 | 101575.28 | -5881.72 | -5.474%
14 | Palwal | 55139 | 54828.24 | -310.76 | -0.5636%
15 | Panchkula | 25268 | 24578.6889 | -689.3111 | -2.728%
16 | Panipat | 41046 | 41028.0356 | -17.9644 | -0.04377%
17 | Rewari | 22962 | 22731.2356 | -230.7644 | -1.005%
18 | Rohtak | 24433 | 23925.5822 | -507.4178 | -2.077%
19 | sirsa | 94500 | 93664.4444 | -835.5556 | -0.8842%
20 | Sonipat | 43640 | 41747.7467 | -1892.2533 | -4.336%
21 | Yamunanagar | 40299 | 39824.0533 | -474.9467 | -1.179%
| TOTAL | 964877 | 927837.2844 | -37039.7156 | -3.839%
2.4 Coverage Chidlren vs. Enrolment ( Upper Primary) (Source data : Table AT- 4A & 5-A of AWP&B 2018-19)
Sl. No. | Districts | Enrolment as on 30.9.2017 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Ambala | 28068 | 27433.6632 | -634.3368 | -2.26%
2 | Bhiwani | 36491 | 35666.3034 | -824.6966 | -2.26%
3 | Faridabad | 28609 | 27962.4366 | -646.5634 | -2.26%
4 | Fatehabad | 28754 | 28104.1596 | -649.8404 | -2.26%
5 | Gurugram | 33634 | 32873.8716 | -760.1284 | -2.26%
6 | Hissar | 42471 | 41511.1554 | -959.8446 | -2.26%
7 | Jhajjar | 15192 | 14848.6608 | -343.3392 | -2.26%
8 | jind | 37447 | 36600.6978 | -846.3022 | -2.26%
9 | Kaithal | 29050 | 28393.47 | -656.53 | -2.26%
10 | karnal | 37748 | 36894.8952 | -853.1048 | -2.26%
11 | Kurukshetra | 25595 | 25016.553 | -578.447 | -2.26%
12 | Mahendergarh | 16796 | 16416.4104 | -379.5896 | -2.26%
13 | Mewat | 50640 | 49495.536 | -1144.464 | -2.26%
14 | Palwal | 31252 | 30545.7048 | -706.2952 | -2.26%
15 | Panchkula | 17959 | 17553.1266 | -405.8734 | -2.26%
16 | Panipat | 26038 | 25449.5412 | -588.4588 | -2.26%
17 | Rewari | 18649 | 18227.5326 | -421.4674 | -2.26%
18 | Rohtak | 19235 | 18800.289 | -434.711 | -2.26%
19 | sirsa | 53200 | 51997.68 | -1202.32 | -2.26%
20 | Sonipat | 29860 | 29185.164 | -674.836 | -2.26%
21 | Yamunanagar | 29517 | 28849.9158 | -667.0842 | -2.26%
| TOTAL | 636205 | 621826.767 | -14378.233 | -2.26%
[9 empty] | 1601082 | 1549664.0514 | 0.96789
2.5 No. of children ( Primary) (Source data : Table AT-5 of AWP&B 2018-19)
Sl. No. | Districts | No. of children as per PAB Approval for 2017-18 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Ambala | 35353 | 35168.2844 | -184.7156 | -0.5225%
2 | Bhiwani | 48976 | 51441.5289 | 2465.5289 | 5.034%
3 | Faridabad | 30104 | 45378.5733 | 15274.5733 | 50.74%
4 | Fatehabad | 45003 | 43489.28 | -1513.72 | -3.364%
5 | Gurugram | 38332 | 44264.7867 | 5932.7867 | 15.48%
6 | Hissar | 55201 | 54003.7467 | -1197.2533 | -2.169%
7 | Jhajjar | 16357 | 17336.9911 | 979.9911 | 5.991%
8 | jind | 46252 | 44915.8311 | -1336.1689 | -2.889%
9 | Kaithal | 44651 | 42135.6044 | -2515.3956 | -5.633%
10 | karnal | 47644 | 48125.52 | 481.52 | 1.011%
11 | Kurukshetra | 32555 | 34006.3022 | 1451.3022 | 4.458%
12 | Mahendergarh | 26392 | 23667.5289 | -2724.4711 | -10.32%
13 | Mewat | 90959 | 101575.28 | 10616.28 | 11.67%
14 | Palwal | 45304 | 54828.24 | 9524.24 | 21.02%
15 | Panchkula | 24210 | 24578.6889 | 368.6889 | 1.523%
16 | Panipat | 41674 | 41028.0356 | -645.9644 | -1.55%
17 | Rewari | 19100 | 22731.2356 | 3631.2356 | 19.01%
18 | Rohtak | 24269 | 23925.5822 | -343.4178 | -1.415%
19 | sirsa | 56189 | 93664.4444 | 37475.4444 | 66.7%
20 | Sonipat | 36587 | 41747.7467 | 5160.7467 | 14.11%
21 | Yamunanagar | 36023 | 39824.0533 | 3801.0533 | 10.55%
| TOTAL | 841135 | 927837.2844 | 86702.2844 | 10.31%
2.6 No. of children ( Upper Primary) (Source data : Table AT-5-A of AWP&B 2018-19)
Sl. No. | Districts | No. of children as per PAB Approval for 2017-18 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Ambala | 28068 | 27433.6632 | -634.3368 | -2.26%
2 | Bhiwani | 35337 | 35666.3034 | 329.3034 | 0.9319%
3 | Faridabad | 21162 | 27962.4366 | 6800.4366 | 32.14%
4 | Fatehabad | 30263 | 28104.1596 | -2158.8404 | -7.134%
5 | Gurugram | 25527 | 32873.8716 | 7346.8716 | 28.78%
6 | Hissar | 40434 | 41511.1554 | 1077.1554 | 2.664%
7 | Jhajjar | 13580 | 14848.6608 | 1268.6608 | 9.342%
8 | jind | 35220 | 36600.6978 | 1380.6978 | 3.92%
9 | Kaithal | 32371 | 28393.47 | -3977.53 | -12.29%
10 | karnal | 35813 | 36894.8952 | 1081.8952 | 3.021%
11 | Kurukshetra | 24218 | 25016.553 | 798.553 | 3.297%
12 | Mahendergarh | 17522 | 16416.4104 | -1105.5896 | -6.31%
13 | Mewat | 45598 | 49495.536 | 3897.536 | 8.548%
14 | Palwal | 25806 | 30545.7048 | 4739.7048 | 18.37%
15 | Panchkula | 16771 | 17553.1266 | 782.1266 | 4.664%
16 | Panipat | 24029 | 25449.5412 | 1420.5412 | 5.912%
17 | Rewari | 15613 | 18227.5326 | 2614.5326 | 16.75%
18 | Rohtak | 19209 | 18800.289 | -408.711 | -2.128%
19 | sirsa | 38249 | 51997.68 | 13748.68 | 35.95%
20 | Sonipat | 28065 | 29185.164 | 1120.164 | 3.991%
21 | Yamunanagar | 27088 | 28849.9158 | 1761.9158 | 6.504%
| TOTAL | 579943 | 621826.767 | 41883.767 | 7.222%
2.7 Number of meal to be served and actual number of meal served during 2017-18 (Source data: Table AT-5 & 5A of AWP&B 2018-19)
Sr. No. | District | No of meals to be served during 1.4.17 to 31.03.18 | No of meal served during 1.4.17 to 31.03.18 | % Meals Served
1 | 2 | 3 | 4 | 5
1 | Ambala | 15347882 | 14085438.22 | 91.77%
2 | Bhiwani | 20403746 | 19599262.265 | 96.06%
3 | Faridabad | 12875982 | 16501727.235 | 128.2%
4 | Fatehabad | 18214372 | 16108523.91 | 88.44%
5 | Gurugram | 16619598 | 17356198.11 | 104.4%
6 | Hissar | 23143670 | 21490852.965 | 92.86%
7 | Jhajjar | 7244754 | 7241771.68 | 99.96%
8 | jind | 19716224 | 18341219.005 | 93.03%
9 | Kaithal | 18639324 | 15869041.75 | 85.14%
10 | karnal | 20196594 | 19129593.42 | 94.72%
11 | Kurukshetra | 13739066 | 13280142.425 | 96.66%
12 | Mahendergarh | 10627188 | 9018886.34 | 84.87%
13 | Mewat | 33046794 | 33990933.6 | 102.9%
14 | Palwal | 17208620 | 19209137.58 | 111.6%
15 | Panchkula | 9917402 | 9479658.485 | 95.59%
16 | Panipat | 15900126 | 14957454.77 | 94.07%
17 | Rewari | 8400546 | 9215722.835 | 109.7%
18 | Rohtak | 10521676 | 9613321.025 | 91.37%
19 | sirsa | 22853996 | 32773978 | 143.4%
20 | Sonipat | 15645784 | 15959904.9 | 102%
21 | Yamunanagar | 15272862 | 15451643.055 | 101.2%
| TOTAL | 345536206 | 348674411.575 | 100.9%
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 1.4.2017 | 337.774 | 337.774 | 0 | 0%
2 | Allocation for 2017-18 | 41407.3979 | 41407.3979 | 0 | 0%
3 | Lifting as on 31.03.2018 | 29813.15 | 29813.15 | 0 | 0%
3.2) District-wise opening balance as on 1.4.2017 (Source data: Table AT-6 & 6A of AWP&B 2018-19)
(in MTs)
S.No. | Name of District | Allocation for 2017-18 | Opening Stock as on 1.4.2017 | % of OS on allocation 2017-18
1 | 2 | 3 | 4 | 5
1 | Ambala | 1874.411 | 23 | 1.227%
2 | Bhiwani | 2467.9523 | 0 | 0%
3 | Faridabad | 1496.6974 | 0 | 0%
4 | Fatehabad | 2187.6195 | 0 | 0%
5 | Gurugram | 1854.2645 | -43.55 | -2.349%
6 | Hissar | 2803.6184 | 45.68 | 1.629%
7 | Jhajjar | 888.7934 | 0 | 0%
8 | jind | 2397.7844 | 0 | 0%
9 | Kaithal | 2255.6215 | 0 | 0%
10 | karnal | 2452.9967 | 30.01 | 1.223%
11 | Kurukshetra | 1666.9444 | 0 | 0%
12 | Mahendergarh | 1274.735 | 74.484 | 5.843%
13 | Mewat | 3856.4152 | 82 | 2.126%
14 | Palwal | 2033.1146 | 30.86 | 1.518%
15 | Panchkula | 1194.6693 | 0 | 0%
16 | Panipat | 1880.7635 | 62.95 | 3.347%
17 | Rewari | 1028.9719 | 23.19 | 2.254%
18 | Rohtak | 1284.5965 | 0 | 0%
19 | sirsa | 2748.2125 | 0 | 0%
20 | Sonipat | 1904.1649 | 0 | 0%
21 | Yamunanagar | 1855.051 | 9.15 | 0.4932%
| TOTAL | 41407.3979 | 337.774 | 0.8157%
3.3) District-wise unspent balance as on 31.03.2018 (Source data: Table AT-6 & 6A of AWP&B 2018-19)
(in MTs)
S.No. | Name of District | Allocation for 2017-18 | Unspent Balance as on 31.03.2018 | % of UB on allocation 2017-18
1 | 2 | 3 | 4 | 5
1 | Ambala | 1874.411 | -1.14 | -0.06082%
2 | Bhiwani | 2467.9523 | 0 | 0%
3 | Faridabad | 1496.6974 | 150 | 10.02%
4 | Fatehabad | 2187.6195 | 0 | 0%
5 | Gurugram | 1854.2645 | -140.55 | -7.58%
6 | Hissar | 2803.6184 | -86.81 | -3.096%
7 | Jhajjar | 888.7934 | 10 | 1.125%
8 | jind | 2397.7844 | 0 | 0%
9 | Kaithal | 2255.6215 | 0 | 0%
10 | karnal | 2452.9967 | 30.01 | 1.223%
11 | Kurukshetra | 1666.9444 | 0 | 0%
12 | Mahendergarh | 1274.735 | 117.764 | 9.238%
13 | Mewat | 3856.4152 | 447 | 11.59%
14 | Palwal | 2033.1146 | 38.01 | 1.87%
15 | Panchkula | 1194.6693 | 0 | 0%
16 | Panipat | 1880.7635 | -597.54 | -31.77%
17 | Rewari | 1028.9719 | 439.85 | 42.75%
18 | Rohtak | 1284.5965 | 12.4 | 0.9653%
19 | sirsa | 2748.2125 | 0 | 0%
20 | Sonipat | 1904.1649 | 0 | 0%
21 | Yamunanagar | 1855.051 | -22.246 | -1.199%
| TOTAL | 41407.3979 | 396.748 | 0.9582%
3.4) Foodgrains Allocation & Lifting
(in MTs)
Allocation | Unspent balance as on 31.3.18 | Lifting upto 31.03.18 | Total Availibility | % Availibility |  |  |  |  | Bench mark (85%)
41407.3979 | 337.774 | 29813.15 | 30150.924 | 72.82% |  |  |  |  | 41407.3979
3.5) District-wise Foodgrains availability as on 31.03.18 (Source data: Table AT-6 & 6A of AWP&B 2018-19)
(in MTs)
Sl. No. | District | Allocation | OB as on 1.4.2017 | Lifted from FCI | Total Availibility | % Availibility
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ambala | 1874.411 | 23 | 1544.95 | 1567.95 | 83.65%
2 | Bhiwani | 2467.9523 | 0 | 1773.5 | 1773.5 | 71.86%
3 | Faridabad | 1496.6974 | 0 | 1082.15 | 1082.15 | 72.3%
4 | Fatehabad | 2187.6195 | 0 | 1510.44 | 1510.44 | 69.04%
5 | Gurugram | 1854.2645 | -43.55 | 891 | 847.45 | 45.7%
6 | Hissar | 2803.6184 | 45.68 | 1985.45 | 2031.13 | 72.45%
7 | Jhajjar | 888.7934 | 0 | 748.59 | 748.59 | 84.23%
8 | jind | 2397.7844 | 0 | 1700.41 | 1700.41 | 70.92%
9 | Kaithal | 2255.6215 | 0 | 1565.301 | 1565.301 | 69.4%
10 | karnal | 2452.9967 | 30.01 | 2028.65 | 2058.66 | 83.92%
11 | Kurukshetra | 1666.9444 | 0 | 1016.84 | 1016.84 | 61%
12 | Mahendergarh | 1274.735 | 74.484 | 866.41 | 940.894 | 73.81%
13 | Mewat | 3856.4152 | 82 | 2605 | 2687 | 69.68%
14 | Palwal | 2033.1146 | 30.86 | 1290.72 | 1321.58 | 65%
15 | Panchkula | 1194.6693 | 0 | 867.72 | 867.72 | 72.63%
16 | Panipat | 1880.7635 | 62.95 | 951 | 1013.95 | 53.91%
17 | Rewari | 1028.9719 | 23.19 | 1117.27 | 1140.46 | 110.8%
18 | Rohtak | 1284.5965 | 0 | 949.214 | 949.214 | 73.89%
19 | sirsa | 2748.2125 | 0 | 2250.8 | 2250.8 | 81.9%
20 | Sonipat | 1904.1649 | 0 | 1575.3 | 1575.3 | 82.73%
21 | Yamunanagar | 1855.051 | 9.15 | 1492.435 | 1501.585 | 80.95%
| TOTAL | 41407.3979 | 337.774 | 29813.15 | 30150.924 | 72.82%
3.6) Foodgrains Allocation, Lifting (availibility) & Utilisation
Allocation | T. Availibility | % T. Availibility | Utilisation | % Utilisation
41407.3979 | 30150.924 | 72.82% | 29754.176 | 71.86%
3.7) District-wise Utilisation of foodgrains (Source data: Table AT-6 & 6A of AWP&B 2018-19)
Sl. No. | District | Allocation | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5
1 | Ambala | 1874.411 | 1569.09 | 83.71%
2 | Bhiwani | 2467.9523 | 1773.5 | 71.86%
3 | Faridabad | 1496.6974 | 932.15 | 62.28%
4 | Fatehabad | 2187.6195 | 1510.44 | 69.04%
5 | Gurugram | 1854.2645 | 988 | 53.28%
6 | Hissar | 2803.6184 | 2117.94 | 75.54%
7 | Jhajjar | 888.7934 | 738.59 | 83.1%
8 | jind | 2397.7844 | 1700.41 | 70.92%
9 | Kaithal | 2255.6215 | 1565.301 | 69.4%
10 | karnal | 2452.9967 | 2028.65 | 82.7%
11 | Kurukshetra | 1666.9444 | 1016.84 | 61%
12 | Mahendergarh | 1274.735 | 823.13 | 64.57%
13 | Mewat | 3856.4152 | 2240 | 58.09%
14 | Palwal | 2033.1146 | 1283.57 | 63.13%
15 | Panchkula | 1194.6693 | 867.72 | 72.63%
16 | Panipat | 1880.7635 | 1611.49 | 85.68%
17 | Rewari | 1028.9719 | 700.61 | 68.09%
18 | Rohtak | 1284.5965 | 936.814 | 72.93%
19 | sirsa | 2748.2125 | 2250.8 | 81.9%
20 | Sonipat | 1904.1649 | 1575.3 | 82.73%
21 | Yamunanagar | 1855.051 | 1523.831 | 82.14%
| TOTAL | 41407.3979 | 29754.176 | 71.86%
3.8) Cost of Foodgrains, Payment to FCI
Allocation | Bills submited by FCI | Payment made to FCI | % payment
1173.8997 | 821.3326 | 817.0951 | 99.48%
3.9) Payment of cost of foodgrain to FCI
Sl. No. | District | Allocation | Bills raised by FCI | Payment to FCI | Pending Bills | % Bill paid
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ambala | 53.1396 | 42.0192 | 42.02 | -0.00082 | 100%
2 | Bhiwani | 69.9664 | 48.7498 | 48.75 | -0.00025 | 100%
3 | Faridabad | 42.4314 | 20.09 | 20.09 | 0 | 100%
4 | Fatehabad | 62.019 | 40.2879 | 40.2879 | 0 | 100%
5 | Gurugram | 52.5684 | 26.49 | 24.9444 | 1.5456 | 94.17%
6 | Hissar | 79.4826 | 53.0554 | 53.0554 | 0 | 100%
7 | Jhajjar | 25.1973 | 19.9482 | 19.9482 | 0 | 100%
8 | jind | 67.9772 | 45.8574 | 45.86 | -0.00256 | 100%
9 | Kaithal | 63.9469 | 36.7468 | 36.75 | -0.00319 | 100%
10 | karnal | 69.5425 | 55.1243 | 55.12 | 0.00428 | 99.99%
11 | Kurukshetra | 47.2579 | 26.723 | 26.723 | 0 | 100%
12 | Mahendergarh | 36.1387 | 20.1731 | 20.17 | 0.0031 | 99.98%
13 | Mewat | 109.3294 | 75.27 | 75.27 | 1e-05 | 100%
14 | Palwal | 57.6388 | 30.6093 | 27.92 | 2.6893 | 91.21%
15 | Panchkula | 33.8689 | 22.8736 | 22.8736 | 0 | 100%
16 | Panipat | 53.3196 | 25.68 | 25.68 | 0 | 100%
17 | Rewari | 29.1714 | 31.0904 | 31.09 | 0.00041 | 100%
18 | Rohtak | 36.4183 | 25.2947 | 25.2947 | 0 | 100%
19 | sirsa | 77.9118 | 61.0578 | 61.0578 | 0 | 100%
20 | Sonipat | 53.9831 | 36.8703 | 36.87 | 0.000305 | 100%
21 | Yamunanagar | 52.5907 | 77.3214 | 77.32 | 0.00138 | 100%
| TOTAL | 1173.8997 | 821.3326 | 817.0951 | 4.2376 | 99.48%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 1.4.2017 (Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2017-18 | Opening Balance as on 1.4.2017 | % of OB on allocation 2017-18
1 | 2 | 3 | 4 | 5
1 | Ambala | 773.1129 | 157.68 | 20.4%
2 | Bhiwani | 1017.9816 | 188.96 | 18.56%
3 | Faridabad | 617.3678 | 250 | 40.49%
4 | Fatehabad | 902.3883 | 157 | 17.4%
5 | Gurugram | 764.8846 | 210 | 27.46%
6 | Hissar | 1156.4266 | 314.99 | 27.24%
7 | Jhajjar | 366.5787 | 120 | 32.74%
8 | jind | 989.0065 | 562 | 56.82%
9 | Kaithal | 930.3966 | 210 | 22.57%
10 | karnal | 1011.7876 | 183.65 | 18.15%
11 | Kurukshetra | 687.5689 | 175.51 | 25.53%
12 | Mahendergarh | 525.8295 | 270 | 51.35%
13 | Mewat | 1591.0443 | 345.26 | 21.7%
14 | Palwal | 838.7396 | 154.74 | 18.45%
15 | Panchkula | 492.7896 | 50 | 10.15%
16 | Panipat | 775.8831 | 99.3 | 12.8%
17 | Rewari | 424.3986 | 180 | 42.41%
18 | Rohtak | 529.8411 | 84.03 | 15.86%
19 | sirsa | 1133.6233 | 348.25 | 30.72%
20 | Sonipat | 785.4013 | 123.14 | 15.68%
21 | Yamunanagar | 765.1528 | 330 | 43.13%
| TOTAL | 17080.2034 | 4514.51 | 26.43%
4.1.2) District-wise unspent balance as on 31.03.2017 Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2017-18 | Unspent Balance as on 31.03.2018 | % of UB on allocation 2017-18
1 | 2 | 3 | 4 | 5
1 | Ambala | 773.1129 | 257.3603 | 33.29%
2 | Bhiwani | 1017.9816 | 0.01 | 0.0009823%
3 | Faridabad | 617.3678 | 198.3436 | 32.13%
4 | Fatehabad | 902.3883 | -153.357 | -16.99%
5 | Gurugram | 764.8846 | 282.5555 | 36.94%
6 | Hissar | 1156.4266 | -245.13 | -21.2%
7 | Jhajjar | 366.5787 | 0.01 | 0.002728%
8 | jind | 989.0065 | 183.388 | 18.54%
9 | Kaithal | 930.3966 | 221.82 | 23.84%
10 | karnal | 1011.7876 | 75.5738 | 7.469%
11 | Kurukshetra | 687.5689 | 147.0014 | 21.38%
12 | Mahendergarh | 525.8295 | 403.2238 | 76.68%
13 | Mewat | 1591.0443 | -134.055 | -8.426%
14 | Palwal | 838.7396 | 120.408 | 14.36%
15 | Panchkula | 492.7896 | 24.216 | 4.914%
16 | Panipat | 775.8831 | 81.85 | 10.55%
17 | Rewari | 424.3986 | -87.34 | -20.58%
18 | Rohtak | 529.8411 | -45.5653 | -8.6%
19 | sirsa | 1133.6233 | 11.4608 | 1.011%
20 | Sonipat | 785.4013 | 185.71 | 23.65%
21 | Yamunanagar | 765.1528 | 230.3757 | 30.11%
| TOTAL | 17080.2034 | 1757.8597 | 10.29%
4.2) Cooking cost allocation and disbursed to Dists
Allocation | OB as on 1.4.17 | Disbursed to Dist | Total Availibility | % Availibility
17080.2034 | 4514.51 | 12129.812 | 16644.322 | 97.45% | [5 empty] | Bench mark (85%)
14518.1729
4.3) District-wise Cooking Cost availability (Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2017-18 | Opening Balance as on 1.4.2017 | Cooking assistance received | Total Availibility of cooking cost | % Availibility of cooking cost
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ambala | 773.1129 | 157.68 | 515.378 | 673.058 | 87.06%
2 | Bhiwani | 1017.9816 | 188.96 | 350.12 | 539.08 | 52.96%
3 | Faridabad | 617.3678 | 250 | 469.35 | 719.35 | 116.5%
4 | Fatehabad | 902.3883 | 157 | 567.508 | 724.508 | 80.29%
5 | Gurugram | 764.8846 | 210 | 606.12 | 816.12 | 106.7%
6 | Hissar | 1156.4266 | 314.99 | 927.34 | 1242.33 | 107.4%
7 | Jhajjar | 366.5787 | 120 | 388.01 | 508.01 | 138.6%
8 | jind | 989.0065 | 562 | 513.908 | 1075.908 | 108.8%
9 | Kaithal | 930.3966 | 210 | 495.82 | 705.82 | 75.86%
10 | karnal | 1011.7876 | 183.65 | 740.6 | 924.25 | 91.35%
11 | Kurukshetra | 687.5689 | 175.51 | 449.73 | 625.24 | 90.93%
12 | Mahendergarh | 525.8295 | 270 | 492.756 | 762.756 | 145.1%
13 | Mewat | 1591.0443 | 345.26 | 941.14 | 1286.4 | 80.85%
14 | Palwal | 838.7396 | 154.74 | 713.87 | 868.61 | 103.6%
15 | Panchkula | 492.7896 | 50 | 498.756 | 548.756 | 111.4%
16 | Panipat | 775.8831 | 99.3 | 640.22 | 739.52 | 95.31%
17 | Rewari | 424.3986 | 180 | 441.16 | 621.16 | 146.4%
18 | Rohtak | 529.8411 | 84.03 | 412.11 | 496.14 | 93.64%
19 | sirsa | 1133.6233 | 348.25 | 789.84 | 1138.09 | 100.4%
20 | Sonipat | 785.4013 | 123.14 | 527.28 | 650.42 | 82.81%
21 | Yamunanagar | 765.1528 | 330 | 648.796 | 978.796 | 127.9%
| TOTAL | 17080.2034 | 4514.51 | 12129.812 | 16644.322 | 97.45%
4.4) Cooking Cost Utilisation
Allocation | Total available | % available | Utilisation | % Utilisation
17080.2034 | 16644.322 | 97.45% | 14886.4623 | 87.16%
4.5) District-wise Utilisation of Cooking cost (Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2017-18 | Utilisation of Cooking assistance | % Utilisation
1 | 2 | 3 | 4 | 5
1 | Ambala | 773.1129 | 415.6977 | 53.77%
2 | Bhiwani | 1017.9816 | 539.07 | 52.95%
3 | Faridabad | 617.3678 | 521.0064 | 84.39%
4 | Fatehabad | 902.3883 | 877.865 | 97.28%
5 | Gurugram | 764.8846 | 533.5645 | 69.76%
6 | Hissar | 1156.4266 | 1487.46 | 128.6%
7 | Jhajjar | 366.5787 | 508 | 138.6%
8 | jind | 989.0065 | 892.52 | 90.24%
9 | Kaithal | 930.3966 | 484 | 52.02%
10 | karnal | 1011.7876 | 848.6762 | 83.88%
11 | Kurukshetra | 687.5689 | 478.2386 | 69.55%
12 | Mahendergarh | 525.8295 | 359.5322 | 68.37%
13 | Mewat | 1591.0443 | 1420.455 | 89.28%
14 | Palwal | 838.7396 | 748.202 | 89.21%
15 | Panchkula | 492.7896 | 524.54 | 106.4%
16 | Panipat | 775.8831 | 657.67 | 84.76%
17 | Rewari | 424.3986 | 708.5 | 166.9%
18 | Rohtak | 529.8411 | 541.7053 | 102.2%
19 | sirsa | 1133.6233 | 1126.6292 | 99.38%
20 | Sonipat | 785.4013 | 464.71 | 59.17%
21 | Yamunanagar | 765.1528 | 748.4203 | 97.81%
| TOTAL | 17080.2034 | 14886.4623 | 87.16%
5. Reconciliation of Utilisation and Performance during 2016-17 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost (Source data: para 3.7 and 4.5 above)
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | Ambala | 83.71% | 53.77% | -29.94%
2 | Bhiwani | 71.86% | 52.95% | -18.91%
3 | Faridabad | 62.28% | 84.39% | 22.11%
4 | Fatehabad | 69.04% | 97.28% | 28.24%
5 | Gurugram | 53.28% | 69.76% | 16.47%
6 | Hissar | 75.54% | 128.6% | 53.08%
7 | Jhajjar | 83.1% | 138.6% | 55.48%
8 | jind | 70.92% | 90.24% | 19.33%
9 | Kaithal | 69.4% | 52.02% | -17.37%
10 | karnal | 82.7% | 83.88% | 1.178%
11 | Kurukshetra | 61% | 69.55% | 8.555%
12 | Mahendergarh | 64.57% | 68.37% | 3.802%
13 | Mewat | 58.09% | 89.28% | 31.19%
14 | Palwal | 63.13% | 89.21% | 26.07%
15 | Panchkula | 72.63% | 106.4% | 33.81%
16 | Panipat | 85.68% | 84.76% | -0.9187%
17 | Rewari | 68.09% | 166.9% | 98.85%
18 | Rohtak | 72.93% | 102.2% | 29.31%
19 | sirsa | 81.9% | 99.38% | 17.48%
20 | Sonipat | 82.73% | 59.17% | -23.56%
21 | Yamunanagar | 82.14% | 97.81% | 15.67%
| TOTAL | 71.86% | 87.16% | 15.3%
5.2 Reconciliation of Food grains utilisation during 2017-18 (Source data: para 2.7 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 01.4.17 to 31.03.18 | Expected consumption of food grains | Actual consumption of food grains | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | Ambala | 14085438.22 | 1717.1725 | 1569.09 | 91.38%
2 | Bhiwani | 19599262.265 | 2361.1721 | 1773.5 | 75.11%
3 | Faridabad | 16501727.235 | 1972.0225 | 932.15 | 47.27%
4 | Fatehabad | 16108523.91 | 1927.0242 | 1510.44 | 78.38%
5 | Gurugram | 17356198.11 | 2117.8624 | 988 | 46.65%
6 | Hissar | 21490852.965 | 2616.0858 | 2117.94 | 80.96%
7 | Jhajjar | 7241771.68 | 891.2246 | 738.59 | 82.87%
8 | jind | 18341219.005 | 2245.8798 | 1700.41 | 75.71%
9 | Kaithal | 15869041.75 | 1906.3307 | 1565.301 | 82.11%
10 | karnal | 19129593.42 | 2328.0269 | 2028.65 | 87.14%
11 | Kurukshetra | 13280142.425 | 1609.4505 | 1016.84 | 63.18%
12 | Mahendergarh | 9018886.34 | 1086.5733 | 823.13 | 75.75%
13 | Mewat | 33990933.6 | 3955.9181 | 2240 | 56.62%
14 | Palwal | 19209137.58 | 2264.5529 | 1283.57 | 56.68%
15 | Panchkula | 9479658.485 | 1145.4385 | 867.72 | 75.75%
16 | Panipat | 14957454.77 | 1782.0528 | 1611.49 | 90.43%
17 | Rewari | 9215722.835 | 1126.632 | 700.61 | 62.19%
18 | Rohtak | 9613321.025 | 1172.8354 | 936.814 | 79.88%
19 | sirsa | 32773978 | 3862.3717 | 2250.8 | 58.28%
20 | Sonipat | 15959904.9 | 1924.3236 | 1575.3 | 81.86%
21 | Yamunanagar | 15451643.055 | 1869.7259 | 1523.831 | 81.5%
| TOTAL | 348674411.575 | 41882.6762 | 29754.176 | 71.04% |  |  | 106.5
5.3 Reconciliation of Cooking Cost utilisation during 2016-17 (Source data: para 2.5 and 4.7 above)
(Rs. in Lakh)
Sr. No. | District | No. of Meals served during 01.4.17 to 31.03.18 | Expected expenditure of cooking cost | Actual expenditure of cooking cost | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | Ambala | 14085438.22 | 708.2664 | 415.6977 | 58.69%
2 | Bhiwani | 19599262.265 | 973.9604 | 539.07 | 55.35%
3 | Faridabad | 16501727.235 | 813.4798 | 521.0064 | 64.05%
4 | Fatehabad | 16108523.91 | 794.9125 | 877.865 | 110.4%
5 | Gurugram | 17356198.11 | 873.5304 | 533.5645 | 61.08%
6 | Hissar | 21490852.965 | 1079.0424 | 1487.46 | 137.9%
7 | Jhajjar | 7241771.68 | 367.5746 | 508 | 138.2%
8 | jind | 18341219.005 | 926.3131 | 892.52 | 96.35%
9 | Kaithal | 15869041.75 | 786.3563 | 484 | 61.55%
10 | karnal | 19129593.42 | 960.2299 | 848.6762 | 88.38%
11 | Kurukshetra | 13280142.425 | 663.8587 | 478.2386 | 72.04%
12 | Mahendergarh | 9018886.34 | 448.2007 | 359.5322 | 80.22%
13 | Mewat | 33990933.6 | 1632.1237 | 1420.455 | 87.03%
14 | Palwal | 19209137.58 | 934.2294 | 748.202 | 80.09%
15 | Panchkula | 9479658.485 | 472.4737 | 524.54 | 111%
16 | Panipat | 14957454.77 | 735.1289 | 657.67 | 89.46%
17 | Rewari | 9215722.835 | 464.6838 | 708.5 | 152.5%
18 | Rohtak | 9613321.025 | 483.7465 | 541.7053 | 112%
19 | sirsa | 32773978 | 1593.4046 | 1126.6292 | 70.71%
20 | Sonipat | 15959904.9 | 793.7606 | 464.71 | 58.55%
21 | Yamunanagar | 15451643.055 | 771.2231 | 748.4203 | 97.04%
| TOTAL | 348674411.575 | 17276.4996 | 14886.4623 | 86.17% |  |  | 3.5587 | 5.3251
6. ANALYSIS of HONORIUM, To COOK-CUM-HELPERS
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2018-19)
S.No. | Name of District | PAB Approval for 2017-18 | Engaged by State | Not engaged
1 | 2 | 3 | 4 | 5 = (4 - 3)
1 | Ambala | 1612 | 1610 | -2
2 | Bhiwani | 2085 | 2050 | -35
3 | Faridabad | 759 | 752 | -7
4 | Fatehabad | 1472 | 1474 | 2
5 | Gurugram | 943 | 937 | -6
6 | Hissar | 2063 | 2114 | 51
7 | Jhajjar | 1050 | 1038 | -12
8 | jind | 1800 | 1800 | 0
9 | Kaithal | 1449 | 1451 | 2
10 | karnal | 1814 | 1822 | 8
11 | Kurukshetra | 972 | 973 | 1
12 | Mahendergarh | 1384 | 1354 | -30
13 | Mewat | 2387 | 2401 | 14
14 | Palwal | 1075 | 981 | -94
15 | Panchkula | 903 | 922 | 19
16 | Panipat | 1118 | 1088 | -30
17 | Rewari | 1276 | 1272 | -4
18 | Rohtak | 1035 | 1019 | -16
19 | sirsa | 1954 | 1854 | -100
20 | Sonipat | 1464 | 1479 | 15
21 | Yamunanagar | 1808 | 1802 | -6
| TOTAL | 30423 | 30193 | -230
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2018-19)
S.No. | Name of District | Allocation for 2017-18 | Opening Balance as on 1.4.2017 | Amount released | Total availability | % Availibilty
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ambala | 403 | 0 | 417.51 | 417.51 | 103.6%
2 | Bhiwani | 521.25 | 0 | 547.76 | 547.76 | 105.1%
3 | Faridabad | 189.75 | 0 | 250.71 | 250.71 | 132.1%
4 | Fatehabad | 368 | 0 | 366.94 | 366.94 | 99.71%
5 | Gurugram | 235.75 | 0 | 234.22 | 234.22 | 99.35%
6 | Hissar | 515.75 | 0 | 546.33 | 546.33 | 105.9%
7 | Jhajjar | 262.5 | 0 | 228.73 | 228.73 | 87.14%
8 | jind | 450 | 0 | 244.94 | 244.94 | 54.43%
9 | Kaithal | 362.25 | 0 | 410.41 | 410.41 | 113.3%
10 | karnal | 453.5 | 0 | 469.55 | 469.55 | 103.5%
11 | Kurukshetra | 243 | 0 | 276.16 | 276.16 | 113.6%
12 | Mahendergarh | 346 | 0 | 394.79 | 394.79 | 114.1%
13 | Mewat | 596.75 | 0 | 511.97 | 511.97 | 85.79%
14 | Palwal | 268.75 | 0 | 307.37 | 307.37 | 114.4%
15 | Panchkula | 225.75 | 0 | 228.31 | 228.31 | 101.1%
16 | Panipat | 279.5 | 0 | 322.95 | 322.95 | 115.5%
17 | Rewari | 319 | 0 | 297.33 | 297.33 | 93.21%
18 | Rohtak | 258.75 | 0 | 163.8 | 163.8 | 63.3%
19 | sirsa | 488.5 | 0 | 515.2896 | 515.2896 | 105.5%
20 | Sonipat | 366 | 0 | 387.78 | 387.78 | 106%
21 | Yamunanagar | 452 | 0 | 482.91 | 482.91 | 106.8%
| TOTAL | 7605.75 | 0 | 7605.7596 | 7605.7596 | 100%
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers
Refer table AT_8 and AT-8A,AWP&B, 2018-19
S.No. | Name of District | Allocation for 2017-18 | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation
1 | 2 | 3 | 4 | 5 | 6
1 | Ambala | 403 | 417.51 | 349.85 | 86.81%
2 | Bhiwani | 521.25 | 547.76 | 500.27 | 95.98%
3 | Faridabad | 189.75 | 250.71 | 267.5817 | 141%
4 | Fatehabad | 368 | 366.94 | 344.2697 | 93.55%
5 | Gurugram | 235.75 | 234.22 | 242.82 | 103%
6 | Hissar | 515.75 | 546.33 | 670.89 | 130.1%
7 | Jhajjar | 262.5 | 228.73 | 205.73 | 78.37%
8 | jind | 450 | 244.94 | 244.94 | 54.43%
9 | Kaithal | 362.25 | 410.41 | 341.71 | 94.33%
10 | karnal | 453.5 | 469.55 | 465.29 | 102.6%
11 | Kurukshetra | 243 | 276.16 | 198.095 | 81.52%
12 | Mahendergarh | 346 | 394.79 | 362.485 | 104.8%
13 | Mewat | 596.75 | 511.97 | 440.17 | 73.76%
14 | Palwal | 268.75 | 307.37 | 304.495 | 113.3%
15 | Panchkula | 225.75 | 228.31 | 278.77 | 123.5%
16 | Panipat | 279.5 | 322.95 | 293.845 | 105.1%
17 | Rewari | 319 | 297.33 | 297.32 | 93.2%
18 | Rohtak | 258.75 | 163.8 | 157.435 | 60.84%
19 | sirsa | 488.5 | 515.2896 | 504.3 | 103.2%
20 | Sonipat | 366 | 387.78 | 350.72 | 95.83%
21 | Yamunanagar | 452 | 482.91 | 467.265 | 103.4%
| TOTAL | 7605.75 | 7605.7596 | 7288.2515 | 95.83%
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2018-19)
S.No. | Name of District | Allocation for 2017-18 | Total Availability | Unspent balance as on 31.03.2018 | % of UB as on Allocation 2017-18
1 | 2 | 3 | 4 | 5 | 6
1 | Ambala | 403 | 417.51 | 67.66 | 16.79%
2 | Bhiwani | 521.25 | 547.76 | 47.49 | 9.111%
3 | Faridabad | 189.75 | 250.71 | -16.8717 | -8.892%
4 | Fatehabad | 368 | 366.94 | 22.6703 | 6.16%
5 | Gurugram | 235.75 | 234.22 | -8.6 | -3.648%
6 | Hissar | 515.75 | 546.33 | -124.56 | -24.15%
7 | Jhajjar | 262.5 | 228.73 | 23 | 8.762%
8 | jind | 450 | 244.94 | 0 | 0%
9 | Kaithal | 362.25 | 410.41 | 68.7 | 18.96%
10 | karnal | 453.5 | 469.55 | 4.26 | 0.9394%
11 | Kurukshetra | 243 | 276.16 | 78.065 | 32.13%
12 | Mahendergarh | 346 | 394.79 | 32.305 | 9.337%
13 | Mewat | 596.75 | 511.97 | 71.8 | 12.03%
14 | Palwal | 268.75 | 307.37 | 2.875 | 1.07%
15 | Panchkula | 225.75 | 228.31 | -50.46 | -22.35%
16 | Panipat | 279.5 | 322.95 | 29.105 | 10.41%
17 | Rewari | 319 | 297.33 | 0.01 | 0.003135%
18 | Rohtak | 258.75 | 163.8 | 6.365 | 2.46%
19 | sirsa | 488.5 | 515.2896 | 10.9896 | 2.25%
20 | Sonipat | 366 | 387.78 | 37.06 | 10.13%
21 | Yamunanagar | 452 | 482.91 | 15.645 | 3.461%
| TOTAL | 7605.75 | 7605.7596 | 317.5081 | 4.175%
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
7.1) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2017-18 | 245.42 | 245.42 | 0 | 0%
2 | Opening Balance as on 1.4.2017 | 185.35 | 185.35 | 0 | 0%
3 | Released during 2017-18 | 59.88 | 59.88 | 0 | 0%
4 | Total Availibility | 245.23 | 245.23 | 0 | 0%
7.2) Utilisation of MME during 2017-18 (Source data: Table AT-10 of AWP&B 2018-19)
(Rs. In lakh)
Sl. No. | Activity | Allocated for 2017-18 | Total Availibility | Expenditure | Exp as % of allocation
1 | 2 | 3 | 4 | 5 | 6
1 | School Level Expenses | 117.95 | 245.23 | 42 | 35.61%
2 | Management, Supervision, Training & Internal Monitoring, External Monitoring & Evaluation | 127.47 |  | 87.73 | 68.82%
Total |  | 245.42 | 245.23 | 129.73 | 52.86%
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
8.1) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Activity | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2017-18 | 310.56 | 310.56 | 0 | 0%
2 | Opening Balance as on 1.4.2017 | 45.84 | 45.84 | 0 | 0%
3 | Released during 2017-18 | 264.03 | 264.03 | 0 | 0%
4 | Total Availibility | 309.87 | 309.87 | 0 | 0%
8.2) Utilisation of TA during 2017-18 (Source data: Table AT-9 of AWP&B 2018-19)
(Rs. In lakh)
Allocated for 2017-18 | Total availibility of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7 | 8= (2-5)
310.56 | 309.87 | 29813.15 | 223.5986 | 215.47 | 8.1286 | 69.3811 | 94.4
9. INFRASTRUCTURE DEVELOPMENT DURING 2017-18 (Primary + Upper primary)
9. INFRASTRUCTURE DEVELOPMENT DURING 2017-18
9.1) Kitchen cum stores
9.1.1) Releasing details
Releases for Kitchen sheds by GoI as on 31.03.2018
Schools | Year | Dated | Units | Amount (in lakh)
PY& UPY | (2006-07) |  | 3185 | 1911.29
| (2007-08) |  | 873 | 523.8
| (2008-09) |  | 0 | 0
| (2009-10) |  | 7425 | 9275.45
| (2010-11) |  | 0 | 0
| (2011-12) |  | 0 | 0
| (2012-13) |  | 0 | 0
| Total |  | 11483 | 11710.54
9.1.2) Reconciliation of amount sanctioned (Refer AT-11, AWP&B, 2018-19)
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-17 | 11483 | 11710.54 | 11483 | 11710.54 | 100% | 100%
9.1.3) Achievement ( under MDM Funds)
Sanctioned by GoI during 2006-17 |  | Achievement (C) upto 31.03.2018 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
11483 | 11710.54 | 9132 | 8457.86 | 79.53% | 72.22%
9.2 Kitchen Devices
9.2.1) Releasing details
Releases for Kitchen devices by GoI as on 31.03.2018
Schools | Installment | Dated | Units | Amount (in lakh)
PY & UPY | (2006-07) |  | 6645 | 332.24
| (2007-08) |  | 2862 | 143.1
| (2008-09) |  | 0 | 0
| (2009-10) |  | 1976 | 98.8
| (2010-11) |  | 0 | 0
| (2011-12) |  | 3822 | 191.1
| (2012-13) |  | 0 | 0
| (2013-14) | N | 161 | 8.06
|  | R | 7796 | 389.8
| (2014-15) | N | 0 | 0
|  | R | 6707 | 335.35
| Total |  | 29969 | 1498.45
9.2.2) Reconciliation of amount sanctioned (Refer AT-11, AWP&B, 2018-19
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-2017 | 29969 | 1498.45 | 29969 | 1498.45 | 100% | 100%
9.2.3) Achievement ( under MDM Funds)
Sanctioned during 2006-07 to 2017 |  | Achievement (C+IP) upto 31..03.2018 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 |  | 6
29969 | 1498.45 | 20825 | 1041.25 | 69.49% | 69.49%
29969
Note on E763: hp: pl chek
Benchmark (85%)
100%
68%

## Sheet1
S.No. | Name of District | Allocation for 2016-17 | Unspent Balance as on 31.12.2016 | % of UB on allocation 2016-17
1 | 2 | 3 | 4 | 5
1 | Ambala | 2070.548 | 0 | 0%
2 | Bhiwani | 2906.9762 | 0 | 0%
3 | Faridabad | 2167.1558 | 0 | 0%
4 | Fatehabad | 2221.4832 | 0 | 0%
5 | Gurgaon | 2384.9906 | -776.17 | -32.54%
8 | Jind | 2901.1144 | 0 | 0
9 | Kaithal | 2343.837 | 0 | 0
11 | Kurukshetra | 1787.72 | 0 | 0
12 | Mahendargarh | 1426.9284 | 0 | 0
14 | Palwal | 2611.3288 | 5.35 | 0.0020488
16 | Panipat | 1903.4462 | 0 | 0
| Rohtak | 1694.3566 | 0 | 0
| Sirsa | 3126.3992 | 0 | 0
| Sonipat | 2280.0114 | 0 | 0