## Sikkim
Government of India | [8 empty] | 1
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2018-19
State : Sikkim
Part-D: ANALYSIS SHEET
REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2017-18 (1.4.17 to 31.03.18)
I. PAB- MDM Approval VS Performance
1.1 No. of children
S.no | Stage | MDM PAB Approval for 2017-18 | Average number of children availed MDM during 1.4.17 to 31.03.18 (AT-5&5A) | Difference | Difference in %
1 | 2 | 3 | 4 | 5=(4-3) | 6
1 | Primary | 34677.9105 | 31347.5364 | -3330.3742 | -9.604%
2 | Up Primary | 29538.8737 | 26676.0955 | -2862.7782 | -9.692%
| Total | 64216.7842 | 58023.6318 | -6193.1524 | -9.644%
1.2 No. of Working Days Approved for FY 2017-18
S.no | Stage | No of working days approved for FY 2017-18
1 | Primary | 233
2 | Upper Primary | 233
1.2.1) No. of School working days approved for 12 Months(April- March 2018)
S.no | Stage | No of Working days approved for 12 months | No. of working days served MDM | Difference (Less/Excess)
1 | Primary | 223 | 220 | -3 |  |  |  |  | 0.98655
2 | Upper Primary | 223 | 220 | -3
1.3) No. of Meals (Primary & Upper Primary)
i) Base period 01.04.17 to 31.03.18
S. No | Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Difference | Diff in %
1 | PY | 7733174.0474 | 6896458 | -836716.0474 | -10.82%
2 | UP PY | 6587168.8316 | 5868741 | -718427.8316 | -10.91%
3 | Total | 14320342.8789 | 12765199 | -1555143.8789 | -10.86%
ii) Base period 01.04.17 to 31.03.18
S. No | Stage | No. of Meals as per PAB approval (01.04.17 to 31.3.18) | No. of Meals served by State during the period 01.04.17 to 31.03.18 | Bench Mark as per State's claim
1 | PY | 7733174.0474 | 6896458 | 89.18%
2 | U PY | 6587168.8316 | 5868741 | 89.09%
3 | Total | 14320342.8789 | 12765199 | 89.14%
2. COVERAGE UNDER MDM
2.1 Institutions- (Primary) (Source: Table AT-3 of AWP&B 2018-19)
Sl. No. | Districts | No. of Existing Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | East | 140 | 140 | 0 | 0%
2 | West | 144 | 144 | 0 | 0%
3 | North | 62 | 62 | 0 | 0%
4 | South | 149 | 149 | 0 | 0%
| TOTAL | 495 | 495 | 0 | 0%
868
2.2 Institutions- (Upper Primary) (Source :Table AT-3A & 3B of AWP&B 2018-19)
Sl. No. | Districts | No. of Existing Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | East | 133 | 133 | 0 | 0%
2 | West | 98 | 98 | 0 | 0%
3 | North | 33 | 33 | 0 | 0%
4 | South | 109 | 109 | 0 | 0%
| TOTAL | 373 | 373 | 0 | 0%
2.3 PAB Approval VS. Coverage of children ( Primary) Source : Table AT-5 of AWP&B 2018-19)
Sl. No. | Districts | No. of children as per PAB Approval for 2017-18 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | East | 14654.8789 | 12961.2909 | -1693.588 | -11.56%
2 | West | 8190.9368 | 7539.4 | -651.5368 | -7.954%
3 | North | 2701.0316 | 2533.0045 | -168.027 | -6.221%
4 | South | 9131.0632 | 8313.8409 | -817.2222 | -8.95%
| TOTAL | 34677.9105 | 31347.5364 | -3330.3742 | -9.604%
2.4 PAB Approval VS Coverage of children ( Upper Primary) (Source : Table AT-5-A of AWP&B 2018-19
Sl. No. | Districts | No. of children as per PAB Approval for 2017-18 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | East | 12242.8 | 10962.0455 | -1280.7545 | -10.46%
2 | West | 7882.7105 | 7083.6227 | -799.0878 | -10.14%
3 | North | 1946.9053 | 1765.9818 | -180.9234 | -9.293%
4 | South | 7466.4579 | 6864.4455 | -602.0124 | -8.063%
| TOTAL | 29538.8737 | 26676.0955 | -2862.7782 | -9.692%
2.5 Enrolment Vs Coverage of children ( Primary) (Source : Table AT-4 of AWP&B 2018-19)
Sl. No. | Districts | Enrollment | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | East | 15244 | 12961.2909 | -2282.7091 | -14.97%
2 | West | 8567 | 7539.4 | -1027.6 | -11.99%
3 | North | 2576 | 2533.0045 | -42.9955 | -1.669%
4 | South | 9593 | 8313.8409 | -1279.1591 | -13.33%
| TOTAL | 35980 | 31347.5364 | -4632.4636 | -12.88% |  |  |  | 66657 | 58023.6318 | 87.05%
2.6 Enrolment Vs. Coverage of children (U.Primary) (Source : Table AT-4A of AWP&B 2018-19)
Sl. No. | Districts | Enrollment | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | East | 12878 | 10962.0455 | -1915.9545 | -14.88%
2 | West | 8004 | 7083.6227 | -920.3773 | -11.5%
3 | North | 1858 | 1765.9818 | -92.0182 | -4.953%
4 | South | 7937 | 6864.4455 | -1072.5545 | -13.51%
| TOTAL | 30677 | 26676.0955 | -4000.9045 | -13.04%
2.7 Number of meal to be served and actual number of meal served during 2017-18
|  |  | (Source: Table AT-5 & 5A of AWP&B 2018-19) |  |  |  |  | Meals to be served |  |  | Meals served
Sr. No. | District | No of meals to be served during 1.4.17 to 31.03.18 | No of meal served during 1.4.17 to 31.03.18 | % Meals Served |  |  |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 |  |  |  | 3268038.0053 | 2730144.4 | 5998182.4053 | 2851484 | 2411650 | 5263134
1 | East | 5998182.4053 | 5263134 | 87.75% |  |  |  | 1826578.9158 | 1757844.4474 | 3584423.3632 | 1658668 | 1558397 | 3217065
2 | West | 3584423.3632 | 3217065 | 89.75% |  |  |  | 602330.0421 | 434159.8737 | 1036489.9158 | 557261 | 388516 | 945777
3 | North | 1036489.9158 | 945777 | 91.25% |  |  |  | 2036227.0842 | 1665020.1105 | 3701247.1947 | 1829045 | 1510178 | 3339223
4 | South | 3701247.1947 | 3339223 | 90.22% |  |  |  | 7733174.0474 | 6587168.8316 | 14320342.8789 | 6896458 | 5868741 | 12765199
| TOTAL | 14320342.8789 | 12765199 | 89.14%
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. | Details | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 1.4.2017 | 0 | 0 | 0 | 0%
2 | Allocation for 2017-18 | 1761.39 | 1761.39 | 0 | 0%
3 | Lifting as on 31.03.2018 | 1761.39 | 1761.39 | 0 | 0%
3.2) ANALYSIS ON OPENING STOCK AND UNSPENT STOCK OF FOODGRAINS
3.2.1) District-wise opening balance as on 1.4.2017 (Source: Table AT-6 & 6A of AWP&B 2018-19)
|  |  |  | (in MTs) |  |  |  | Allocatio |  |  | Opening Balance
S.No. | Name of District | Allocation for 2017-18 | Opening balance as on 1.4.2017 | % of OB on allocation 2017-18 |  |  |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 |  |  |  | 326.53 | 408.13 | 734.66 | 0 | 0 | 0
1 | East | 734.66 | 0 | 0% |  |  |  | 186.75 | 260.87 | 447.62 | 0 | 0 | 0
2 | West | 447.62 | 0 | 0% |  |  |  | 56.27 | 60.54 | 116.81 | 0 | 0 | 0
3 | North | 116.81 | 0 | 0% |  |  |  | 203.75 | 258.55 | 462.3 | 0 | 0 | 0
4 | South | 462.3 | 0 | 0% |  |  |  | 773.3 | 988.09 | 1761.39 | 0 | 0 | 0
| TOTAL | 1761.39 | 0 | 0%
3.2.2) District-wise Closing balance as on 31.03.2018 (Source: Table AT-6 & 6A of AWP&B 2018-19)
|  |  |  | (in MTs) |  |  |  | Lifted From FCI
S.No. | Name of District | Allocation for 2017-18 | Closing Balance as on 31.03.2018 | % of Closing Balance on allocation 2017-18 |  |  |  | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 |  |  |  | 326.53 | 408.13 | 734.66
1 | East | 734.66 | 0 | 0% |  |  |  | 186.75 | 260.87 | 447.62
2 | West | 447.62 | 0 | 0% |  |  |  | 56.27 | 60.54 | 116.81
3 | North | 116.81 | 0 | 0% |  |  |  | 203.75 | 258.55 | 462.3
4 | South | 462.3 | 0 | 0% |  |  |  | 773.3 | 988.09 | 1761.39
| TOTAL | 1761.39 | 0 | 0%
3.3) Foodgrains : Allocation & Lifting
(in MTs)
Allocation | Unspent balance as on 01.04.17 | Lifting upto 31.03.18 | Total Availability | % Availability
1761.39 | 0 | 1761.39 | 1761.39 | 100%
Source: Table AT-6 & 6A of AWP&B 2018-19
3.4) District-wise Foodgrains availability as on 31.03.18 (Source : Table AT-6 & 6A of AWP&B 2018-19)
[6 empty] | (in MTs) |  | Utilisation
Sl. No. | District | Allocation | OB as on 1.4.2016 | Lifted from FCI | Total Availability | % Availability |  | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 326.53 | 408.13 | 734.66
1 | East | 734.66 | 0 | 734.66 | 734.66 | 100% |  | 186.75 | 260.87 | 447.62
2 | West | 447.62 | 0 | 447.62 | 447.62 | 100% |  | 56.27 | 60.54 | 116.81
3 | North | 116.81 | 0 | 116.81 | 116.81 | 100% |  | 203.75 | 258.55 | 462.3
4 | South | 462.3 | 0 | 462.3 | 462.3 | 100% |  | 773.3 | 988.09 | 1761.39
| TOTAL | 1761.39 | 0 | 1761.39 | 1761.39 | 100%
3.5) Foodgrains Allocation, Lifting (Availability) & Utilisation
Allocation | Total Availability | % Total Availability | Utilisation | % Utilisation
1761.39 | 1761.39 | 100% | 1761.39 | 100%
3.6) District-wise Utilisation of foodgrains (Source: Table AT-6 & 6A of AWP&B 2018-19)
Sl. No. | District | Allocation | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5
1 | East | 734.66 | 734.66 | 100%
2 | West | 447.62 | 447.62 | 100%
3 | North | 116.81 | 116.81 | 100%
4 | South | 462.3 | 462.3 | 100%
| TOTAL | 1761.39 | 1761.39 | 100%
3.7) Cost of Foodgrains: Allocation, Releases (Availability) & Utilisation
Allocation | Total Availability | % Availability | Bills submited by FCI | Payment made to FCI | % payment
52.84 | 52.8417 | 100% | 52.8417 | 52.8417 | 100%
3.8) Payment of cost of foodgrain to FCI
Sl. No. | District | Allocation | Bills raised by FCI | Payment to FCI by State | % of Bills paid
1 | 2 | 3 | 4 | 5 | 6
1 | East | 22.04 | 22.0398 | 22.0398 | 100%
2 | West | 13.43 | 13.4286 | 13.4286 | 100%
3 | North | 3.5 | 3.5043 | 3.5043 | 100%
4 | South | 13.87 | 13.869 | 13.869 | 100%
| TOTAL | 52.84 | 52.8417 | 52.8417 | 100%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
Verification of Cooking Cost Allocation
| Centre (85,81,264x220xRs.1.5) |  |  | 283.1817
| State Share (85,81,264*220*Rs. 1.0) |  |  | 188.7878
| Total |  |  | 471.9695
| Actual Allocation shown in State Plan |  |  | 477.18
| Diff. (Excess/Deficit) |  |  | 5.2105
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 1.4.2017 (Source : Table AT-7 & 7A of AWP&B 2018-19)
| *(Refer col.8 of table AT-7 and AT-7A, AWP&B 2018-19 |  |  | (Rs. In lakhs) |  |  |  | Allocation |  |  | Opening Balance
S.No. | Name of District | Allocation for 2017-18 | Opening Balance as on 1.4.2017 | % of OB on allocation 2017-18 |  |  |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 |  |  |  | 134.9582 | 169.8325 | 304.7906 | 0 | 57.92 | 57.92
1 | East | 304.7906 | 57.92 | 19% |  |  |  | 75.4475 | 109.3548 | 184.8023 | 0 | 0 | 0
2 | West | 184.8023 | 0 | 0% |  |  |  | 24.8759 | 27.0053 | 51.8813 | 0 | 0 | 0
3 | North | 51.8813 | 0 | 0% |  |  |  | 84.0956 | 103.5374 | 187.633 | 0 | 0 | 0
4 | South | 187.633 | 0 | 0% |  |  |  | 319.3772 | 409.73 | 729.1072 | 0 | 57.92 | 57.92
| TOTAL | 729.1072 | 57.92 | 7.944%
4.2.2) District-wise closing balance as on 31.03.2018 (Source : Table AT-7 & 7A of AWP&B 2018-19)
|  |  |  | (Rs. In lakhs) |  |  |  | Closing Balance / Unspent |  |  | Cooking Cost Received
S.No. | Name of District | Allocation for 2017-18 | Closing Balance as on 31.03.2018 | % of UB on allocation 2017-18 |  |  |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 |  |  |  | 10.2776 | 27.1179 | 37.3955 | 137.4633 | 126.1525 | 263.6158
1 | East | 304.7906 | 37.3955 | 12.27% |  |  |  | 5.7444 | 9.2815 | 15.0258 | 76.8311 | 110.3458 | 187.1769
2 | West | 184.8023 | 15.0258 | 8.131% |  |  |  | 1.8945 | 2.194 | 4.0885 | 25.3393 | 27.1477 | 52.487
3 | North | 51.8813 | 4.0885 | 7.881% |  |  |  | 6.4035 | 6.8625 | 13.266 | 85.6462 | 102.5499 | 188.1961
4 | South | 187.633 | 13.266 | 7.07% |  |  |  | 24.32 | 45.4559 | 69.7759 | 325.28 | 366.1959 | 691.4759
| TOTAL | 729.1072 | 69.7759 | 9.57%
4.3) Cooking cost allocation and disbursed to Districts
Allocation | Availability | Bench mark
100% | 110.4% | 85%
47718.17 | 52695.2695 | 40560.4445
Allocation | OB as on 1.4.17 | Disbursed to Dist | Total Availability | % Availability
729.1072 | 57.92 | 691.4759 | 749.3959 | 102.8%
4.4) District-wise Cooking Cost availability (Source : Table AT-7 & 7A of AWP&B 2018-19)
[6 empty] | (Rs. In lakhs) |  | Expenditure
S.No. | Name of District | Allocation for 2017-18 | Opening Balance as on 1.4.2017 | Cooking assistance received | Total Availability of cooking cost | % Availability of cooking cost |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 127.1857 | 156.9546 | 284.1403 |  |  | 0
1 | East | 304.7906 | 57.92 | 263.6158 | 321.5358 | 105.5% |  | 71.0868 | 101.0644 | 172.1511 |  |  | 0
2 | West | 184.8023 | 0 | 187.1769 | 187.1769 | 101.3% |  | 23.4448 | 24.9537 | 48.3985 |  |  | 0
3 | North | 51.8813 | 0 | 52.487 | 52.487 | 101.2% |  | 79.2428 | 95.6874 | 174.9302 |  |  | 0
4 | South | 187.633 | 0 | 188.1961 | 188.1961 | 100.3% |  | 300.96 | 378.66 | 679.62 | 0 | 0 | 0
| TOTAL | 729.1072 | 57.92 | 691.4759 | 749.3959 | 102.8%
4.5) Cooking Cost Utilisation
Allocation | Availability | % Availability | Utilisation | % Utilisation
729.1072 | 749.3959 | 102.8% | 679.62 | 93.21%
47718.17 | 52695.2695 | 21852.2148 | 35788.6275
4.6) District-wise Utilisation of Cooking cost
| (Refer col. 14 of Table AT-7 & 7A of AWP&B 2018-19) |  |  | (Rs. In lakhs)
S.No. | Name of District | Allocation for 2017-18 | Utilisation of Cooking assistance | % Utilisation
1 | 2 | 3 | 4 | 5
1 | East | 304.7906 | 284.1403 | 93.22%
2 | West | 184.8023 | 172.1511 | 93.15%
3 | North | 51.8813 | 48.3985 | 93.29%
4 | South | 187.633 | 174.9302 | 93.23%
| TOTAL | 729.1072 | 679.62 | 93.21%
5. Reconciliation of Utilisation and Performance during 2017-18 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | East | 100% | 93.22% | -6.7753
2 | West | 100% | 93.15% | -6.8458
3 | North | 100% | 93.29% | -6.713
4 | South | 100% | 93.23% | -6.77
| TOTAL | 100% | 93.21% | -6.7874
5.2 Reconciliation of Food grains utilisation during 2017-18 (Source data: para 2.5 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 01.4.17 to 31.03.18 | Expected consumption of food grains | Actual consumption of food grains | % consumption |  |  |  | Name of District | NO. OF MEALS PRY | NO. OF MEAL UPPR PRY | TOTAL NO. OF MEALS AS PER Performance | Formulae for Pry | Formulae for Upr Pry | Expected Consumption of foodgrains
1 | 2 | 3 | 4 | 5 | 6 |  |  |  | East | 2851484 | 2411650 | 5263134 | 285.1484 | 361.7475 | 646.8959
1 | East | 5263134 | 646.8959 | 734.66 | 113.6% |  |  |  | West | 1658668 | 1558397 | 3217065 | 165.8668 | 233.7595 | 399.6264
2 | West | 3217065 | 399.6264 | 447.62 | 112% |  |  |  | North | 557261 | 388516 | 945777 | 55.7261 | 58.2774 | 114.0035
3 | North | 945777 | 114.0035 | 116.81 | 102.5% |  |  |  | South | 1829045 | 1510178 | 3339223 | 182.9045 | 226.5267 | 409.4312
4 | South | 3339223 | 409.4312 | 462.3 | 112.9% |  |  |  | Total | 6896458 | 5868741 | 12765199 | 689.6458 | 880.3111 | 1569.957
| TOTAL | 12765199 | 1569.957 | 1761.39 | 112.2%
5.3 Reconciliation of Cooking Cost utilisation during 2017-18 (Source data: para 2.5 and 3.7 above)
Sr. No. | District | No. of Meals served during 01.4.17 to 31.03.18 | Expected Utilisation of Cooking Cost (Rs. In Lakhs) | Actual utilisation of Cooking cost (Rs. In Lakhs) | % Utilisation |  |  |  | Name of District | Pry / Average No. of children availed MDM [Col. 8/Col. 9] | Expected Utilisation of Cooking Cost / Pry | Average No. of children availed Upr Pry MDM [Col. 8/Col. 9] | Expected Utilisation of Cooking Cost Upr Pry | Expected Utilisation of Cooking Cost (In Lakhs) |  | Name of District | Actual utilisation of Cooking cost (Rs. In Lakhs) Pry | Actual utilisation of Cooking cost (Rs. In Lakhs) Upry Pry | Actual utilisation of Cooking cost (Rs. In Lakhs) Pry + Upr Pry
1 | East | 5263134 | 284.1403 | 284.1403 | 100% |  |  |  | East |  | 0 |  | 0 | 0 |  | West | 129.12 | 148.84 | 277.96
2 | West | 3217065 | 172.1511 | 172.1511 | 100% |  |  |  | West |  | 0 |  | 0 | 0 |  | Sepahijala | 73.46 | 97.69 | 171.15
3 | North | 945777 | 48.3985 | 48.3985 | 100% |  |  |  | North |  | 0 |  | 0 | 0 |  | Khowai | 23.53 | 24.12 | 47.65
4 | South | 3339223 | 174.9302 | 174.9302 | 100% |  |  |  | South |  | 0 |  | 0 | 0 |  | Gomati | 80.9 | 88.23 | 169.13
Total |  | 12765199 | 679.62 | 679.62 | 100% |  |  |  | Total | 0 | 0 | 0 | 0 | 0 |  | Total | 307.01 | 358.88 | 665.89
6. ANALYSIS OF HONORARIUM TO COOK-CUM-HELPERS
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers | [7 empty] | Allocation |  |  | Opening Balance
S.No. | Name of District | Allocation for 2017-18 | Opening Balance as on 1.4.2017 | Amount released | Total availability | % Availibilty |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | East | 70.3 | 0.63 | 69.67 | 70.3 | 100% |  | 47.4 | 22.9 | 70.3 | 0.63 | 0 | 0.63
2 | West | 43.9 | 0 | 43.9 | 43.9 | 100% |  | 23.3 | 20.6 | 43.9 | 0 | 0 | 0
3 | North | 17.7 | 0 | 17.7 | 17.7 | 100% |  | 9.4 | 8.3 | 17.7 | 0 | 0 | 0
4 | South | 57.2 | 0 | 57.2 | 57.2 | 100% |  | 39.3 | 17.9 | 57.2 | 0 | 0 | 0
| Total | 189.1 | 0.63 | 188.47 | 189.1 | 100% |  | 119.4 | 69.7 | 189.1 | 0.63 | 0 | 0.63
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers
Refer table AT-8 and AT-8A ,AWP&B, 2018-19 | [7 empty] | Releases |  |  | Expenditure
S.No. | Name of District | Allocation for 2017-18 | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation |  |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | East | 70.3 | 70.3 | 70.1 | 99.72% |  |  | 46.77 | 22.9 | 69.67 | 47.2 | 22.9 | 70.1
2 | West | 43.9 | 43.9 | 42.4 | 96.58% |  |  | 23.3 | 20.6 | 43.9 | 21.8 | 20.6 | 42.4
3 | North | 17.7 | 17.7 | 15 | 84.75% |  |  | 9.4 | 8.3 | 17.7 | 6.7 | 8.3 | 15
4 | South | 57.2 | 57.2 | 57.1 | 99.83% |  |  | 39.3 | 17.9 | 57.2 | 39.2 | 17.9 | 57.1
| Total | 189.1 | 189.1 | 184.6 | 97.62% |  |  | 118.77 | 69.7 | 188.47 | 114.9 | 69.7 | 184.6
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
Refer table AT_8 and AT-8A,AWP&B, 2018-19 | [7 empty] | closing balamce
S.No. | Name of District | Allocation for 2017-18 | Total Availability | Closing balance as on 31.03.2018 | % of Closing Balance as on Allocation 2017-18 |  |  | Pry | U. Pry. | Total
1 | East | 70.3 | 70.3 | 0.2 | 0.2845% |  |  | 0.2 | 0 | 0.2
2 | West | 43.9 | 43.9 | 1.5 | 3.417% |  |  | 1.5 | 0 | 1.5
3 | North | 17.7 | 17.7 | 2.7 | 15.25% |  |  | 2.7 | 0 | 2.7
4 | South | 57.2 | 57.2 | 0.1 | 0.1748% |  |  | 0.1 | 0 | 0.1
| Total | 189.1 | 189.1 | 4.5 | 2.38% |  |  | 4.5 | 0 | 4.5
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
Verification of Cooking Cost Allocation
| Centre (85,81,264x220xRs.1.5) |  |  | 283.1817
| State Share (85,81,264*220*Rs. 1.0) |  |  | 188.7878
| Total |  |  | 471.9695
| Actual Allocation shown in State Plan |  |  | 477.18
| Diff. (Excess/Deficit) |  |  | 5.2105
7.1) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2017-18 | 16.36 | 16.36 | 0 | 0%
2 | Opening Balance as on 1.4.2017 | 0 | 0 | 0 | 0%
3 | Releasing during 2017-18 | 16.36 | 16.36 | 0 | 0%
4 | Total Availability | 16.36 | 16.36 | 0 | 0%
7.2) Utilisation of MME during 2017-18 (Source data: Table AT-9 of AWP&B 2018-19)
|  |  | (Rs. In lakhs) | (As on 31.03.18)
Sl. No. | Activity | Allocated for 2015-16 | Total Availability | Expenditure | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | School Level Expenses | 8.18 | 8.18 | 16.36 | 100% | 0
2 | Management, Supervision, Training & Internal Monitoring | 8.18 | 8.18
Total |  | 16.36 | 16.36 | 16.36 | 100% | 0
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
Verification of Cooking Cost Allocation
| Centre (85,81,264x220xRs.1.5) |  |  | 283.1817
| State Share (85,81,264*220*Rs. 1.0) |  |  | 188.7878
| Total |  |  | 471.9695
| Actual Allocation shown in State Plan |  |  | 477.18
| Diff. (Excess/Deficit) |  |  | 5.2105
8.1) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Releases during 2017-18 | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2017-18 | 32.06 | 32.06 | 0 | 0%
2 | Opening Balance as on 1.4.2017 | 0 | 0 | 0 | 0%
3 | Releasing during 2016-2017 | 32.06 | 32.06 | 0 | 0%
4 | Total Availability | 32.06 | 32.06 | 0 | 0%
8.3) Utilisation of TA during 2015-16 (Source data: Table AT-8 of AWP&B 2018-19
|  |  | (Rs. In lakhs) |  |  | (As on 31.03.18)
Allocated for 2017-18 | Total Availability of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7 | 8= (2-5)
32.06 | 32.06 | 1761.39 | 32.0573 | 32.06 | -0.002702 | 100% | 0
Source: Table AT-11 of AWP&B 2018-19
9. INFRASTRUCTURE DEVELOPMENT DURING 2015-16 (Primary + Upper primary)
9.1 KITCHEN-CUM -STORES
9.1.1) Releasing details
Releases for Kitchen -cum-stores by GoI as on 31.3.2018
Schools | Installment |  | Units | Amount (in lakh)
Primary + Upper Primary | 2006-07 |  | 800 | 480
| 2007-08 |  | 0 | 0
| 2008-09 |  | 59 | 35.4
| 2009-10 |  | 0 | 0
| 2010-11 |  | 0 | 0
| 2011-12 |  | 0 | 0
| 2013-14 |  | 77 | 168.94
| 2014-15 |  | 0 | 0
2015-16
| 2016-17 |  | 0 | 0
2017-18*
| Grand Total |  | 936 | 684.34
* 12 KS sanctioned, funds yet to be release to State Govt.
9.1.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-07 to 2017-18 | 936 | 684.33 | 936 | 684.33 | 0% | 0%
9.1.3) Achievement ( under MDM Funds) (Source data: Table AT-10 of AWP&B 2018-19)
Sactioned by GoI during 2006-07 to 2017-18 |  | Achievement (C+IP) upto 31.03.18 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
936 | 684.33 | 936 | 684.34 | 100% | 100%
9.2 KITCHEN DEVICES
9.2.1) Releasing details
Releases for Kitchen devices by GoI as on 31.03.2018
Schools | Installment |  | Units | Replacement | Amount (in lakh)
Primary + Upper Primary | 2006-07 |  | 446 |  | 22.3
| 2007-08 |  | 336 |  | 16.8
| 2009-10 |  | 0 |  | 0
| 2010-11 |  | 0 |  | 0
| 2011-12 |  | 97 |  | 4.85
| 2012-13 |  |  | 443 | 22.15
| 2013-14 |  |  | 336 | 16.8
2014-15
2015-16
| 2016-17 |  | 0 | 0
2017-18*
| Grand Total |  | 879 | 779 | 82.9
* 97 KD sanctioned, funds yet to be released to State
9.2.2) Reconciliation of amount sanctioned
Year | GoI records |  | State Plan |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-16-17 | 1658 | 82.9 | 1658 | 82.9 | 0% | 0%
9.2.3) Achievement ( under MDM Funds) (Source data: Table AT-11 of AWP&B 2018-19)
Sactioned during 2006-07 to 2017-18 |  | Achievement (C+IP) upto 31.03.18 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
1658 | 82.9 | 1658 | 82.9 | 100% | 100%
Benchmark (85%)
68%