## Slide 1: PAB - MDM Meeting for Review of Implementation of MDMS in Himalayan States: 08.05.2019
Mid Day Meal Scheme
Primary School, Malla Dhouladevi, Almora (Uttarakhand)

## Slide 2: No. of Schools (Primary & U. Primary)
Chart: %age coverage against approval
| Himachal Pradesh | Uttarakhand
%age | 1 | 0.98
Name of States | PAB Approval | Coverage | %age
Himachal Pradesh | 15494 | 15505 | 100%
Uttarakhand | 17664 | 17344 | 98%

## Slide 3: Coverage of children (Primary & U. Primary)
Chart: 
| Himachal Pradesh | Uttarakhand
%age Coverage (Pry) | 0.93 | 0.92
%age Coverage U.Pry | 0.92 | 0.9
State | Children (Pry) |  |  | Children (U. Pry) |  | 
 | PAB Approval | Coverage | %age | PAB Approval | Coverage | %age
Himachal Pradesh | 297582 | 276601 | 93% | 208462 | 191049 | 92%
Uttarakhand | 365687 | 334750 | 92% | 259866 | 233156 | 90%

## Slide 4: Working Days (Primary & U. Primary)
State | Working Days (Pry) |  |  | Working Days (U. Pry) |  | 
 | PAB Approval | Coverage | %age | PAB Approval | Coverage | %age
Himachal Pradesh | 237 | 234 | 99% | 237 | 234 | 99%
Uttarakhand | 235 | 227 | 97% | 235 | 225 | 96%
Chart: 
| Himachal Pradesh | Uttarakhand
%age Coverage (Pry) | 0.99 | 0.97
%age Coverage (U. Pry) | 0.99 | 0.96

## Slide 5
Engagement of Cook-cum-helpers (Primary & U. Primary)
State | PAB Approval | Engaged | %age
Himachal Pradesh | 23476 | 21764 | 93%
Uttarakhand | 32989 | 26532 | 80%
Chart: %age CCH engaged against PAB approval
| Himachal Pradesh | Uttarakhand
%age Coverage (Pry) | 0.93 | 0.8

## Slide 6
Construction of Kitchen-cum-stores (Primary & U. Primary)
State | PAB Approval | Constructed | %age
Himachal Pradesh | 14959 | 14829 | 99%
Uttarakhand | 15933 | 15666 | 98%
Chart: %age Completion of Construction of KS against PAB approval
| Himachal Pradesh | Uttarakhand
%age Procurement of KDs against PAB approval | 0.99 | 0.98

## Slide 7
Procurement of Kitchen devices (Primary & U. Primary)
State | PAB Approval | Procured | %age
Himachal Pradesh | 15828 | 15828 | 100%
Uttarakhand | 18199 | 18199 | 100%
Chart: %age Procurement of KDs against PAB approval
| Himachal Pradesh | Uttarakhand
%age Coverage | 1 | 1

## Slide 8: Performance Grade Index (PGI)
State | Score (children taking MDM) (1.3.7) out of 10 | Score (MDM served days ) (1.3.8) out of 10
Himachal Pradesh | 10 | 10
Uttarakhand | 10 | 10
Performance Grading Index (PGI):
Score against the weightage of 10 for indicator No. 1.3.7 i.e. “% of elementary school’s children taking MDM against target approved in PAB – in Govt. and aided schools”.
Score against the weightage of 10 for indicator No 1.3.8 i.e. “% of days Mid Day Meal served against total working days – Govt. and aided elementary schools.”

## Slide 9: Performance Score Card – Himachal Pradesh
Component | PAB Approval / Allocation | Utilization | % Utilization
Institutions | 15505 | 15505 | 100%
Children | 509804 | 467649 | 92%
Working Days | 237 | 234 | 99%
Food Grain (MTs) | 14464 | 13122 | 91%
Cooking Cost (Rs. in lakhs) | 6281 | 5460 | 87%
Cook cum Helpers Engaged | 23476 | 21764 | 93%
Honorarium to Cook Cum Helpers (Rs. in lakhs) | 3881 | 3863 | 100%
TA (Rs. in lakh) | 204 | 204 | 100%
MME (Rs. in lakh) | 150 | 149 | 99%
Kitchen cum Stores | 14959 | 14829 | 99%
Kitchen Devices | 15828 | 15828 | 100%
No. of Children Health Check-up | 13095 | 10657 | 81%
Annual Data Entry | 15436 | 15390 | 100%
Monthly Data Entry | 15436 | 15133 | 98%

## Slide 10: Performance Score Card – Uttarakhand
Ministry of HRD, Govt. of India
Component | PAB Approval / Allocation | Utilization | % Utilization
Institutions | 17664 | 17344 | 98%
Children | 625553 | 567906 | 91%
Working Days | 235 | 226 | 96%
Food Grain (in MTs) | 17754 | 17377 | 98%
Cooking Cost (Rs. in lakhs) | 7714 | 6497 | 84%
Cook cum Helpers Engaged | 32989 | 26532 | 80%
Honorarium to Cook Cum Helpers (Rs. in lakh) | 6598 | 5831 | 88%
TA (Rs. in lakh) | 447 | 386 | 86%
MME (Rs. in lakh) | 196 | 192 | 98%
Kitchen cum Stores | 15933 | 15666 | 98%
Kitchen Devices | 18199 | 18199 | 100%
No. of Children Health Check-up | 716910 | 716910 | 100%
Annual Data Entry | 17344 | 17344 | 100%
Monthly Data Entry | 17344 | 17344 | 100%

## Slide 11: Focus of this year

## Slide 12: Focus of this year

## Slide 13: Focus of this year
Usage of Jails, Temples, Gurudwaras etc. for Mid Day Meal:
  Temples, Gurudwaras, Jails etc. can be involved in Mid Day Meal Scheme.
  Temples, Gurudwaras have greater reach among community, this can help in wider publicity for Mid Day Meal Scheme.
  Temples, Gurudwaras can adopt some schools for providing meals.
  Enhanced sense of ownership of the Mid Day Meal Scheme among the local community.
Uploading of videos, testimonials on Shagun web-portal:
  Shagun web-portal is an innovation for repository of best practices which collates videos, testimonials, case studies and images of state-level innovations and success stories.
  Accordingly, relevant videos, testimonials of the innovative activities being carried out by States/UTs related to Mid Day Meal may be shared with this department so that the same may be uploaded on Shagun (https://repository.ssashagun.nic.in) repository after necessary approvals.

## Slide 14: Tithi Bhojan
  Tithi Bhojan, is a community participation programme initiated by Gujarat.
  Community provides full meal or additional items on special occasions, birthdays, marriages, anniversaries, days of national importance and other festivals etc.
  Ministry of Human Resource Development has issued Guidelines on Tithi Bhojan on 26th October, 2018 to all the States and UTs.
  Tithi Bhojan has been adopted by the States & UTs of Assam (Sampriti Bhojan), Andhra Pradesh, Punjab (Priti bhojan), Dadra & Nagar Haveli (Tithi Bhojan), Daman & Diu (Tithi Bhojan), Karnataka (Shalegagi Naavu Neevu), Madhya Pradesh, Maharastra (Sneh Bhojan), Chandigarh (Tithi Bhojan), Puducherry (Anna Dhanam), Haryana (Beti ka Janamdin) and Uttarakhand (Tithi Bhojan).

## Slide 15
1
2
3
4
5
6
Graphical dashboard: Reports are generated and displayed online
Drill down reports from State to school level are available
Daily email alerts are sent to States and UTs level regarding implementation of AMS.
States/UTs are using various technologies (SMS/ IVRS/ Mobile App) for daily data collection.
15
Automated Monitoring System
AMS is used to monitor MDMS on real time basis.
Schools need to share the daily data on number of meals and reasons if meals are not served.

## Slide 16
Chart: % schools data entered
| Himachal Pradesh | Uttarakhand
Annual | 1 | 1
Monthly | 0.98 | 1
Daily (AMS) : Average (Apr, 2018-Mar, 2019) | 0.78 | 0.65
Status of implementation of MIS & AMS

## Slide 17: Amendment for involvement of Centralized Kitchens only in urban areas.
Amendment of the Gazette of India notification dated 18th April, 2019 stated that:
In the MDM Rules 2015, in rule 5 for sub-rule (2) the following sub-rule shall be substituted
“(2) Every school shall have the facility for cooking meal in hygienic manner. Schools in urban areas may use the facility of centralized kitchens for cooking meals wherever required in accordance with the guidelines issued by the Central Government and the meal shall be served to the children at respected school only”

## Slide 18
Name of State | Delay in release of fund from State to District / School
Himachal Pradesh | 1 month
Uttarakhand | 2 months
Status of flow of funds from State to school

## Slide 19: Focus of this year

## Slide 20: Social Audit- Mid Day Meal Scheme
“Social audit" means the process in which people collectively monitor and evaluate the planning and implementation of a programme or scheme.
Importance:
  Helps to ensure accountability and participation of all the stakeholders in the implementation of Mid Day Meal Scheme
  It creates a sense of ownership and increases the reach of the scheme up to the beneficiaries.
  Social audit enables the State Governments to identify and resolve gaps in the implementation of Mid Day meal Scheme.
  Status :
  Social Audit carried out in Uttarakhand and Tripura in 2018-19.
Social intervention for Community Participation under MDMS

## Slide 21: Recommendations
Ministry of HRD, Govt. of India
S. No | State | PAB Approval for FY 2018-19 (Rs. in Lakhs) | Proposal for FY 2019-20 (Rs. in Lakhs) | Recommendations for FY - 2019-20 (Rs. in Lakhs)
1 | Himachal Pradesh | 8736.34 | 8847.82 | 8564.01
2 | Uttarakhand | 11021.79 | 12189.70 | 12189.70

## Slide 22
Thank you