## Maharashtra
Government of India
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2019-20
State : Maharashtra
Part-D: ANALYSIS SHEET
Section-A : REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2018-19
1. Calculation of Bench mark for utilisation.
1.1) No. of children
Stage | MDM PAB Approval for 2018-19 | Average number of children availed MDM during 2018-19 | Diff | Diff in %
Primary | 5900000 | 5464881 | -435119 | -7.375%
Up Primary | 3950000 | 3421277 | -528723 | -13.39%
NCLP | 5589 | 1240 | -4349 | -77.81%
Total | 9855589 | 8887398 | -968191 | -9.824%
1.2) No. of School working days
PY | 231 | 222 | -9 | -3.896%
UP.PY | 231 | 222 | -9 | -3.896%
NCLP | 289 | 265 | -24 | -8.304%
1.3) Number of meals served vis-à-vis PAB approval during 2018-19
Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Diff. | Diff in %
PY | 1362900000 | 1204640589 | -158259411 | -11.61%
UP PY | 912450000 | 754704250 | -157745750 | -17.29%
NCLP | 1615221 | 746546 | -868675 | -53.78%
Total | 2276965221 | 1960091385 | -316873836 | -13.92%
2. COVERAGE
2.1 Institutions- (Primary) (Source data : Table AT-3A of AWP&B 2019-20)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Ahmednagar | 3170 | 3170 | 0 | 0%
2 | Akola | 640 | 640 | 0 | 0%
3 | Amravati | 1032 | 1032 | 0 | 0%
4 | Aurangabad | 1474 | 1474 | 0 | 0%
5 | Beed | 1938 | 1938 | 0 | 0%
6 | Bhandara | 598 | 598 | 0 | 0%
7 | Buldhana | 969 | 969 | 0 | 0%
8 | Chandrapur | 1072 | 1072 | 0 | 0%
9 | Dhule | 1146 | 1146 | 0 | 0%
10 | Gadchiroli | 1109 | 1109 | 0 | 0%
11 | Gondiya | 646 | 646 | 0 | 0%
12 | Hingoli | 525 | 525 | 0 | 0%
13 | Jalgaon | 1514 | 1514 | 0 | 0%
14 | Jalna | 1025 | 1025 | 0 | 0%
15 | Kolhapur | 1215 | 1215 | 0 | 0%
16 | Latur | 848 | 848 | 0 | 0%
17 | Mumbai | 580 | 551 | 29 | 5%
18 | Nagpur | 1373 | 1373 | 0 | 0%
19 | Nanded | 1616 | 1616 | 0 | 0%
20 | Nandurbar | 1275 | 1275 | 0 | 0%
21 | Nashik | 2766 | 2766 | 0 | 0%
22 | Osmanabad | 611 | 611 | 0 | 0%
23 | Parbhani | 673 | 673 | 0 | 0%
24 | Pune | 3113 | 3113 | 0 | 0%
25 | Raigad | 2080 | 2080 | 0 | 0%
26 | Ratnagiri | 1671 | 1671 | 0 | 0%
27 | Sangli | 1301 | 1301 | 0 | 0%
28 | Satara | 1976 | 1976 | 0 | 0%
29 | Sindhudurga | 944 | 944 | 0 | 0%
30 | Solapur | 2237 | 2237 | 0 | 0%
31 | Thane | 1236 | 1236 | 0 | 0%
32 | Palghar | 1633 | 1633 | 0 | 0%
33 | Wardha | 712 | 712 | 0 | 0%
34 | Washim | 518 | 518 | 0 | 0%
35 | Yavatmal | 1378 | 1378 | 0 | 0%
| TOTAL | 46614 | 46585 | 29 | 0.06221%
2.2 Institutions- (Primary with Upper Primary) (Source data : Table AT-3B of AWP&B 2019-20)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Ahmednagar | 1150 | 1150 | 0 | 0%
2 | Akola | 688 | 688 | 0 | 0%
3 | Amravati | 1189 | 1189 | 0 | 0%
4 | Aurangabad | 1313 | 1313 | 0 | 0%
5 | Beed | 1129 | 1129 | 0 | 0%
6 | Bhandara | 471 | 471 | 0 | 0%
7 | Buldhana | 926 | 926 | 0 | 0%
8 | Chandrapur | 833 | 833 | 0 | 0%
9 | Dhule | 493 | 493 | 0 | 0%
10 | Gadchiroli | 578 | 578 | 0 | 0%
11 | Gondiya | 611 | 611 | 0 | 0%
12 | Hingoli | 473 | 473 | 0 | 0%
13 | Jalgaon | 1143 | 1143 | 0 | 0%
14 | Jalna | 807 | 807 | 0 | 0%
15 | Kolhapur | 1508 | 1508 | 0 | 0%
16 | Latur | 1112 | 1112 | 0 | 0%
17 | Mumbai | 1562 | 1484 | -78 | -4.994%
18 | Nagpur | 1314 | 1314 | 0 | 0%
19 | Nanded | 1292 | 1292 | 0 | 0%
20 | Nandurbar | 415 | 415 | 0 | 0%
21 | Nashik | 1483 | 1483 | 0 | 0%
22 | Osmanabad | 784 | 784 | 0 | 0%
23 | Parbhani | 820 | 820 | 0 | 0%
24 | Pune | 2000 | 2000 | 0 | 0%
25 | Raigad | 1013 | 1013 | 0 | 0%
26 | Ratnagiri | 1190 | 1190 | 0 | 0%
27 | Sangli | 1089 | 1089 | 0 | 0%
28 | Satara | 1266 | 1266 | 0 | 0%
29 | Sindhudurga | 645 | 645 | 0 | 0%
30 | Solapur | 1631 | 1631 | 0 | 0%
31 | Thane | 1279 | 1279 | 0 | 0%
32 | Palghar | 697 | 697 | 0 | 0%
33 | Wardha | 488 | 488 | 0 | 0%
34 | Washim | 533 | 533 | 0 | 0%
35 | Yavatmal | 1184 | 1184 | 0 | 0%
| TOTAL | 35109 | 35031 | -78 | -0.2222%
2.2A Institutions- (Upper Primary) (Source data : Table AT-3C of AWP&B 2019-20)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Ahmednagar | 214 | 214 | 0 | 0%
2 | Akola | 110 | 110 | 0 | 0%
3 | Amravati | 176 | 176 | 0 | 0%
4 | Aurangabad | 240 | 240 | 0 | 0%
5 | Beed | 137 | 137 | 0 | 0%
6 | Bhandara | 61 | 61 | 0 | 0%
7 | Buldhana | 111 | 111 | 0 | 0%
8 | Chandrapur | 126 | 126 | 0 | 0%
9 | Dhule | 37 | 37 | 0 | 0%
10 | Gadchiroli | 98 | 98 | 0 | 0%
11 | Gondiya | 91 | 91 | 0 | 0%
12 | Hingoli | 33 | 33 | 0 | 0%
13 | Jalgaon | 95 | 95 | 0 | 0%
14 | Jalna | 81 | 81 | 0 | 0%
15 | Kolhapur | 330 | 330 | 0 | 0%
16 | Latur | 200 | 200 | 0 | 0%
17 | Mumbai | 247 | 157 | -90 | -36.44%
18 | Nagpur | 120 | 120 | 0 | 0%
19 | Nanded | 113 | 113 | 0 | 0%
20 | Nandurbar | 15 | 15 | 0 | 0%
21 | Nashik | 210 | 210 | 0 | 0%
22 | Osmanabad | 143 | 143 | 0 | 0%
23 | Parbhani | 102 | 102 | 0 | 0%
24 | Pune | 278 | 278 | 0 | 0%
25 | Raigad | 90 | 90 | 0 | 0%
26 | Ratnagiri | 163 | 163 | 0 | 0%
27 | Sangli | 132 | 132 | 0 | 0%
28 | Satara | 188 | 188 | 0 | 0%
29 | Sindhudurga | 71 | 71 | 0 | 0%
30 | Solapur | 215 | 215 | 0 | 0%
31 | Thane | 212 | 212 | 0 | 0%
32 | Palghar | 55 | 55 | 0 | 0%
33 | Wardha | 52 | 52 | 0 | 0%
34 | Washim | 60 | 60 | 0 | 0%
35 | Yavatmal | 218 | 218 | 0 | 0%
| TOTAL | 4824 | 4734 | -90 | -1.866%
2.3 Coverage Chidlren vs. Enrolment ( Primary) (Source data : Table AT-4 & 5 of AWP&B 2019-20)
Sl. No. | Districts | Enrolment as on 30.9.2018 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Ahmednagar | 305802 | 265411.3602 | -40390.6398 | -13.21%
2 | Akola | 90248 | 90087.6802 | -160.3198 | -0.1776%
3 | Amravati | 151351 | 136432.6034 | -14918.3966 | -9.857%
4 | Aurangabad | 295186 | 239617.5973 | -55568.4027 | -18.82%
5 | Beed | 227622 | 189267.1351 | -38354.8649 | -16.85%
6 | Bhandara | 67797 | 61211.0227 | -6585.9773 | -9.714%
7 | Buldhana | 172077 | 147291.4595 | -24785.5405 | -14.4%
8 | Chandrapur | 107401 | 91388.556 | -16012.444 | -14.91%
9 | Dhule | 173445 | 137200.1461 | -36244.8539 | -20.9%
10 | Gadchiroli | 63492 | 58055.027 | -5436.973 | -8.563%
11 | Gondiya | 72271 | 62241.3874 | -10029.6126 | -13.88%
12 | Hingoli | 89675 | 69017.0262 | -20657.9738 | -23.04%
13 | Jalgaon | 321182 | 243943.7297 | -77238.2703 | -24.05%
14 | Jalna | 157533 | 134188.0183 | -23344.9817 | -14.82%
15 | Kolhapur | 232607 | 197478.2489 | -35128.7511 | -15.1%
16 | Latur | 187461 | 153723.65 | -33737.35 | -18%
17 | Mumbai | 366496 | 237490.5964 | -129005.4036 | -35.2%
18 | Nagpur | 203376 | 184690.2166 | -18685.7834 | -9.188%
19 | Nanded | 262808 | 196451.4369 | -66356.5631 | -25.25%
20 | Nandurbar | 121735 | 102162.473 | -19572.527 | -16.08%
21 | Nashik | 428438 | 349288.9144 | -79149.0856 | -18.47%
22 | Osmanabad | 114655 | 98373.8378 | -16281.1622 | -14.2%
23 | Parbhani | 156648 | 123846.8153 | -32801.1847 | -20.94%
24 | Pune | 454334 | 386006.1577 | -68327.8423 | -15.04%
25 | Raigad | 104856 | 96890.9957 | -7965.0043 | -7.596%
26 | Ratnagiri | 77492 | 72786.6802 | -4705.3198 | -6.072%
27 | Sangli | 181929 | 163198.6982 | -18730.3018 | -10.3%
28 | Satara | 168153 | 158823.6545 | -9329.3455 | -5.548%
29 | Sindhudurga | 35783 | 33300.2281 | -2482.7719 | -6.938%
30 | Solapur | 325000 | 292197.8784 | -32802.1216 | -10.09%
31 | Thane | 312891 | 261583.7748 | -51307.2252 | -16.4%
32 | Palghar | 157172 | 133309.5955 | -23862.4045 | -15.18%
33 | Wardha | 55679 | 47327.8288 | -8351.1712 | -15%
34 | Washim | 80732 | 75124.6816 | -5607.3184 | -6.946%
35 | Yavatmal | 176345 | 154161.4709 | -22183.5291 | -12.58%
| TOTAL | 6499672 | 5464881.018 | -1034790.982 | -15.92%
2.4 Coverage Chidlren vs. Enrolment ( Up Pry) (Source : Table AT- 4A & 5-A of AWP&B 2019-20)
Sl. No. | Districts | Enrolment as on 30.9.2018 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Ahmednagar | 195925 | 164710.9068 | -31214.0932 | -15.93%
2 | Akola | 64419 | 63560.8333 | -858.1667 | -1.332%
3 | Amravati | 106670 | 93032.7888 | -13637.2112 | -12.78%
4 | Aurangabad | 185397 | 147149.7557 | -38247.2443 | -20.63%
5 | Beed | 135551 | 109911.6712 | -25639.3288 | -18.91%
6 | Bhandara | 47123 | 42494.1227 | -4628.8773 | -9.823%
7 | Buldhana | 112603 | 94661.7973 | -17941.2027 | -15.93%
8 | Chandrapur | 72652 | 60515.7328 | -12136.2672 | -16.7%
9 | Dhule | 99098 | 80810.6347 | -18287.3653 | -18.45%
10 | Gadchiroli | 36065 | 31835.1261 | -4229.8739 | -11.73%
11 | Gondiya | 48712 | 41865.6036 | -6846.3964 | -14.05%
12 | Hingoli | 47401 | 35108.262 | -12292.738 | -25.93%
13 | Jalgaon | 202392 | 142786.955 | -59605.045 | -29.45%
14 | Jalna | 94345 | 76878.2968 | -17466.7032 | -18.51%
15 | Kolhapur | 159322 | 129728.543 | -29593.457 | -18.57%
16 | Latur | 124020 | 92510.7591 | -31509.2409 | -25.41%
17 | Mumbai | 333182 | 200831.148 | -132350.852 | -39.72%
18 | Nagpur | 160037 | 144246.6129 | -15790.3871 | -9.867%
19 | Nanded | 155854 | 102796.2883 | -53057.7117 | -34.04%
20 | Nandurbar | 60655 | 48867.1757 | -11787.8243 | -19.43%
21 | Nashik | 256002 | 198608.1982 | -57393.8018 | -22.42%
22 | Osmanabad | 73578 | 60551.6171 | -13026.3829 | -17.7%
23 | Parbhani | 89610 | 69017.379 | -20592.621 | -22.98%
24 | Pune | 328415 | 260471.3739 | -67943.6261 | -20.69%
25 | Raigad | 73372 | 56897.2565 | -16474.7435 | -22.45%
26 | Ratnagiri | 58489 | 51230.6306 | -7258.3694 | -12.41%
27 | Sangli | 119912 | 106012.1577 | -13899.8423 | -11.59%
28 | Satara | 114376 | 101599.9182 | -12776.0818 | -11.17%
29 | Sindhudurga | 26400 | 23988.6316 | -2411.3684 | -9.134%
30 | Solapur | 204378 | 161699.3829 | -42678.6171 | -20.88%
31 | Thane | 201183 | 164150.4324 | -37032.5676 | -18.41%
32 | Palghar | 88820 | 69549.8784 | -19270.1216 | -21.7%
33 | Wardha | 50583 | 41496.6802 | -9086.3198 | -17.96%
34 | Washim | 55809 | 49206.9731 | -6602.0269 | -11.83%
35 | Yavatmal | 106945 | 89949.2703 | -16995.7297 | -15.89%
| TOTAL | 4289295 | 3421277.4054 | -868017.5946 | -20.24%
2.5 No. of children ( Primary) (Source data : Table AT-5 of AWP&B 2019-20)
Sl. No. | Districts | No. of children as per PAB Approval for 2018-19 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Ahmednagar | 276759 | 265411.3602 | -11347.6398 | -4.1%
2 | Akola | 84809 | 90087.6802 | 5278.6802 | 6.224%
3 | Amravati | 140280 | 136432.6034 | -3847.3966 | -2.743%
4 | Aurangabad | 267133 | 239617.5973 | -27515.4027 | -10.3%
5 | Beed | 213154 | 189267.1351 | -23886.8649 | -11.21%
6 | Bhandara | 61267 | 61211.0227 | -55.9773 | -0.09137%
7 | Buldhana | 156172 | 147291.4595 | -8880.5405 | -5.686%
8 | Chandrapur | 97098 | 91388.556 | -5709.444 | -5.88%
9 | Dhule | 153816 | 137200.1461 | -16615.8539 | -10.8%
10 | Gadchiroli | 57280 | 58055.027 | 775.027 | 1.353%
11 | Gondiya | 66379 | 62241.3874 | -4137.6126 | -6.233%
12 | Hingoli | 90374 | 69017.0262 | -21356.9738 | -23.63%
13 | Jalgaon | 292339 | 243943.7297 | -48395.2703 | -16.55%
14 | Jalna | 142265 | 134188.0183 | -8076.9817 | -5.677%
15 | Kolhapur | 210790 | 197478.2489 | -13311.7511 | -6.315%
16 | Latur | 178520 | 153723.65 | -24796.35 | -13.89%
17 | Mumbai | 324781 | 237490.5964 | -87290.4036 | -26.88%
18 | Nagpur | 186390 | 184690.2166 | -1699.7834 | -0.9119%
19 | Nanded | 228888 | 196451.4369 | -32436.5631 | -14.17%
20 | Nandurbar | 109859 | 102162.473 | -7696.527 | -7.006%
21 | Nashik | 386328 | 349288.9144 | -37039.0856 | -9.587%
22 | Osmanabad | 101858 | 98373.8378 | -3484.1622 | -3.421%
23 | Parbhani | 141727 | 123846.8153 | -17880.1847 | -12.62%
24 | Pune | 411010 | 386006.1577 | -25003.8423 | -6.084%
25 | Raigad | 106012 | 96890.9957 | -9121.0043 | -8.604%
26 | Ratnagiri | 74399 | 72786.6802 | -1612.3198 | -2.167%
27 | Sangli | 159296 | 163198.6982 | 3902.6982 | 2.45%
28 | Satara | 147196 | 158823.6545 | 11627.6545 | 7.899%
29 | Sindhudurga | 35240 | 33300.2281 | -1939.7719 | -5.504%
30 | Solapur | 281935 | 292197.8784 | 10262.8784 | 3.64%
31 | Thane | 288274 | 261583.7748 | -26690.2252 | -9.259%
32 | Palghar | 145377 | 133309.5955 | -12067.4045 | -8.301%
33 | Wardha | 50350 | 47327.8288 | -3022.1712 | -6.002%
34 | Washim | 71785 | 75124.6816 | 3339.6816 | 4.652%
35 | Yavatmal | 160860 | 154161.4709 | -6698.5291 | -4.164%
| TOTAL | 5900000 | 5464881.018 | -435118.982 | -7.375%
2.6 No. of children ( Upper Primary) (Source data : Table AT-5-A of AWP&B 2019-20)
Sl. No. | Districts | No. of children as per PAB Approval for 2018-19 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Ahmednagar | 186104 | 164710.9068 | -21393.0932 | -11.5%
2 | Akola | 63411 | 63560.8333 | 149.8333 | 0.2363%
3 | Amravati | 100183 | 93032.7888 | -7150.2112 | -7.137%
4 | Aurangabad | 167304 | 147149.7557 | -20154.2443 | -12.05%
5 | Beed | 126987 | 109911.6712 | -17075.3288 | -13.45%
6 | Bhandara | 43547 | 42494.1227 | -1052.8773 | -2.418%
7 | Buldhana | 104789 | 94661.7973 | -10127.2027 | -9.664%
8 | Chandrapur | 67379 | 60515.7328 | -6863.2672 | -10.19%
9 | Dhule | 89732 | 80810.6347 | -8921.3653 | -9.942%
10 | Gadchiroli | 33446 | 31835.1261 | -1610.8739 | -4.816%
11 | Gondiya | 47112 | 41865.6036 | -5246.3964 | -11.14%
12 | Hingoli | 52778 | 35108.262 | -17669.738 | -33.48%
13 | Jalgaon | 194758 | 142786.955 | -51971.045 | -26.68%
14 | Jalna | 87143 | 76878.2968 | -10264.7032 | -11.78%
15 | Kolhapur | 150705 | 129728.543 | -20976.457 | -13.92%
16 | Latur | 115944 | 92510.7591 | -23433.2409 | -20.21%
17 | Mumbai | 302242 | 200831.148 | -101410.852 | -33.55%
18 | Nagpur | 150379 | 144246.6129 | -6132.3871 | -4.078%
19 | Nanded | 133786 | 102796.2883 | -30989.7117 | -23.16%
20 | Nandurbar | 56478 | 48867.1757 | -7610.8243 | -13.48%
21 | Nashik | 233796 | 198608.1982 | -35187.8018 | -15.05%
22 | Osmanabad | 67342 | 60551.6171 | -6790.3829 | -10.08%
23 | Parbhani | 82247 | 69017.379 | -13229.621 | -16.09%
24 | Pune | 271281 | 260471.3739 | -10809.6261 | -3.985%
25 | Raigad | 76244 | 56897.2565 | -19346.7435 | -25.37%
26 | Ratnagiri | 53009 | 51230.6306 | -1778.3694 | -3.355%
27 | Sangli | 113769 | 106012.1577 | -7756.8423 | -6.818%
28 | Satara | 98444 | 101599.9182 | 3155.9182 | 3.206%
29 | Sindhudurga | 28688 | 23988.6316 | -4699.3684 | -16.38%
30 | Solapur | 177139 | 161699.3829 | -15439.6171 | -8.716%
31 | Thane | 196514 | 164150.4324 | -32363.5676 | -16.47%
32 | Palghar | 82662 | 69549.8784 | -13112.1216 | -15.86%
33 | Wardha | 38075 | 41496.6802 | 3421.6802 | 8.987%
34 | Washim | 54553 | 49206.9731 | -5346.0269 | -9.8%
35 | Yavatmal | 102030 | 89949.2703 | -12080.7297 | -11.84%
| TOTAL | 3950000 | 3421277.4054 | -528722.5946 | -13.39%
2.7 Number of meal to be served and actual number of meal served during 2018-19 (Source data: Table AT-5 & 5A of AWP&B 2019-20)
Sr. No. | District | No of meals to be served during 2018-19 | No of meal served during 2018-19 | % Meals Served
1 | 2 | 3 | 4 | 5
1 | Ahmednagar | 106921353 | 101508855 | 94.94%
2 | Akola | 34238820 | 34109970 | 99.62%
3 | Amravati | 55846935 | 53385628 | 95.59%
4 | Aurangabad | 100354947 | 85475585 | 85.17%
5 | Beed | 78869663 | 66439131 | 84.24%
6 | Bhandara | 24212034 | 22815132 | 94.23%
7 | Buldhana | 60281991 | 53713623 | 89.1%
8 | Chandrapur | 37994187 | 35241795 | 92.76%
9 | Dhule | 56476916 | 47845481 | 84.72%
10 | Gadchiroli | 20957706 | 19958464 | 95.23%
11 | Gondiya | 26216421 | 23111752 | 88.16%
12 | Hingoli | 33068112 | 23844691 | 72.11%
13 | Jalgaon | 112924007 | 85969165 | 76.13%
14 | Jalna | 52993248 | 46223523 | 87.23%
15 | Kolhapur | 83505345 | 72312701 | 86.6%
16 | Latur | 68021184 | 54171570 | 79.64%
17 | Mumbai | 144842313 | 97745749 | 67.48%
18 | Nagpur | 77793639 | 71379248 | 91.75%
19 | Nanded | 83777694 | 66432995 | 79.3%
20 | Nandurbar | 38423847 | 33528582 | 87.26%
21 | Nashik | 143248644 | 121633159 | 84.91%
22 | Osmanabad | 39085200 | 35281451 | 90.27%
23 | Parbhani | 52012544 | 42798922 | 82.29%
24 | Pune | 157609221 | 143518012 | 91.06%
25 | Raigad | 42101136 | 35371298 | 84.02%
26 | Ratnagiri | 29431248 | 27531843 | 93.55%
27 | Sangli | 63128590 | 59801164 | 94.73%
28 | Satara | 56742840 | 57293186 | 101%
29 | Sindhudurga | 14767368 | 13061860 | 88.45%
30 | Solapur | 106046094 | 100765192 | 95.02%
31 | Thane | 112357104 | 94645839 | 84.24%
32 | Palghar | 52677009 | 44768184 | 84.99%
33 | Wardha | 20426175 | 19719041 | 96.54%
34 | Washim | 29184078 | 27725959 | 95%
35 | Yavatmal | 60727590 | 54343815 | 89.49%
| TOTAL | 2277265203 | 1973472565 | 86.66%
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 1.4.2018 | 1936.9052 | 1936.9052 | 0 | 0%
2 | Allocation for 2018-19 | 273444.7804 | 273444.7804 | 0 | 0%
3.2) District-wise opening balance as on 1.4.2018 (Source data: Table AT-6 & 6A of AWP&B 2019-20)
(in MTs)
S.No. | Name of District | Allocation | Opening Stock as on 01.04.2018 | % of OS on allocation
1 | 2 | 3 | 4 | 5
1 | Ahmednagar | 12841.6365 | 84.3718 | 0.657%
2 | Akola | 4156.279 | 29.3221 | 0.7055%
3 | Amravati | 6756.8062 | 12.6948 | 0.1879%
4 | Aurangabad | 11967.8559 | -157.4879 | -1.316%
5 | Beed | 9368.5207 | 36.2984 | 0.3875%
6 | Bhandara | 2924.1712 | 12.2765 | 0.4198%
7 | Buldhana | 7238.512 | 219.1213 | 3.027%
8 | Chandrapur | 4577.6461 | 205.011 | 4.479%
9 | Dhule | 6694.9626 | 249.6065 | 3.728%
10 | Gadchiroli | 2482.0719 | -57.1265 | -2.302%
11 | Gondiya | 3165.7857 | 209.7041 | 6.624%
12 | Hingoli | 3916.3971 | -9.9915 | -0.2551%
13 | Jalgaon | 13562.0856 | 954.4859 | 7.038%
14 | Jalna | 6305.8264 | 184.5371 | 2.926%
15 | Kolhapur | 10091.1773 | -61.0675 | -0.6052%
16 | Latur | 8141.2716 | -603.0336 | -7.407%
17 | Mumbai | 17975.1264 | -2110.4949 | -11.74%
18 | Nagpur | 9516.2414 | -193.544 | -2.034%
19 | Nanded | 9922.9977 | -90.1167 | -0.9082%
20 | Nandurbar | 4494.7056 | 475.8252 | 10.59%
21 | Nashik | 17025.2082 | 452.5655 | 2.658%
22 | Osmanabad | 4686.3201 | 197.9333 | 4.224%
23 | Parbhani | 6164.9348 | 154.7529 | 2.51%
24 | Pune | 18894.2176 | 719.4229 | 3.808%
25 | Raigad | 5090.7318 | 0.77507 | 0.01523%
26 | Ratnagiri | 3555.3787 | 176.6414 | 4.968%
27 | Sangli | 7629.4197 | 47.2662 | 0.6195%
28 | Satara | 6811.3122 | 442.5275 | 6.497%
29 | Sindhudurga | 1808.0832 | 34.9413 | 1.933%
30 | Solapur | 12650.5648 | 91.511 | 0.7234%
31 | Thane | 13524.0009 | -374.6099 | -2.77%
32 | Palghar | 6222.447 | 162.702 | 2.615%
33 | Wardha | 2482.3837 | 117.3024 | 4.725%
34 | Washim | 3548.4949 | 366.3079 | 10.32%
35 | Yavatmal | 7251.2055 | -43.5216 | -0.6002%
| TOTAL | 273444.7804 | 1936.9052 | 0.7083%
3.3) District-wise unspent balance as on 31.03.2019 (Source data: Table AT-6 & 6A of AWP&B 2019-20)
(in MTs)
S.No. | Name of District | Allocation | Unspent Balance as on 31.03.2019 | % of UB on allocation
1 | 2 | 3 | 4 | 5
1 | Ahmednagar | 12841.6365 | 685.4976 | 5.338%
2 | Akola | 4156.279 | 181.7498 | 4.373%
3 | Amravati | 6756.8062 | 370.5905 | 5.485%
4 | Aurangabad | 11967.8559 | 302.7888 | 2.53%
5 | Beed | 9368.5207 | 624.5693 | 6.667%
6 | Bhandara | 2924.1712 | 341.9779 | 11.69%
7 | Buldhana | 7238.512 | 937.8031 | 12.96%
8 | Chandrapur | 4577.6461 | 579.869 | 12.67%
9 | Dhule | 6694.9626 | 1021.884 | 15.26%
10 | Gadchiroli | 2482.0719 | 275.3125 | 11.09%
11 | Gondiya | 3165.7857 | 507.3607 | 16.03%
12 | Hingoli | 3916.3971 | 698.4998 | 17.84%
13 | Jalgaon | 13562.0856 | 1581.9953 | 11.66%
14 | Jalna | 6305.8264 | 1031.8074 | 16.36%
15 | Kolhapur | 10091.1773 | 1106.092 | 10.96%
16 | Latur | 8141.2716 | 393.7969 | 4.837%
17 | Mumbai | 17975.1264 | -189.4071 | -1.054%
18 | Nagpur | 9516.2414 | 580.0494 | 6.095%
19 | Nanded | 9922.9977 | 993.9847 | 10.02%
20 | Nandurbar | 4494.7056 | 692.3413 | 15.4%
21 | Nashik | 17025.2082 | 673.2886 | 3.955%
22 | Osmanabad | 4686.3201 | 399.0153 | 8.514%
23 | Parbhani | 6164.9348 | 613.4927 | 9.951%
24 | Pune | 18894.2176 | 690.7605 | 3.656%
25 | Raigad | 5090.7318 | 958.6568 | 18.83%
26 | Ratnagiri | 3555.3787 | 339.1371 | 9.539%
27 | Sangli | 7629.4197 | 765.5802 | 10.03%
28 | Satara | 6811.3122 | 920.2898 | 13.51%
29 | Sindhudurga | 1808.0832 | 277.5449 | 15.35%
30 | Solapur | 12650.5648 | 1166.2186 | 9.219%
31 | Thane | 13524.0009 | 506.5917 | 3.746%
32 | Palghar | 6222.447 | 201.5799 | 3.24%
33 | Wardha | 2482.3837 | 172.8552 | 6.963%
34 | Washim | 3548.4949 | 1016.7243 | 28.65%
35 | Yavatmal | 7251.2055 | 726.95 | 10.03%
| TOTAL | 273444.7804 | 22147.2487 | 8.099%
3.4) Foodgrains Allocation & Lifting
(in MTs)
Allocation | Opening balance as on 01.4.18 | Lifting upto 31.03.18 | Total Availibility | % Availibility
273444.7804 | 1936.9052 | 255459.1197 | 257396.0249 | 94.13%
Source: Table AT-6 & 6A of AWP&B 2019-20
3.5) District-wise Foodgrains availability as on 31.03.19 (Source data: Table AT-6 & 6A of AWP&B 2019-20)
(in MTs)
Sl. No. | District | Allocation | OB as on 01.04.2018 | Lifted from FCI | Total Availibility | % Availibility
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ahmednagar | 12841.6365 | 84.3718 | 12695.6 | 12779.9718 | 99.52%
2 | Akola | 4156.279 | 29.3221 | 4268.95 | 4298.2721 | 103.4%
3 | Amravati | 6756.8062 | 12.6948 | 6760.6731 | 6773.3679 | 100.2%
4 | Aurangabad | 11967.8559 | -157.4879 | 10633.84 | 10476.3521 | 87.54%
5 | Beed | 9368.5207 | 36.2984 | 8450.06 | 8486.3584 | 90.58%
6 | Bhandara | 2924.1712 | 12.2765 | 3078.65 | 3090.9265 | 105.7%
7 | Buldhana | 7238.512 | 219.1213 | 7140.79 | 7359.9113 | 101.7%
8 | Chandrapur | 4577.6461 | 205.011 | 4601.02 | 4806.031 | 105%
9 | Dhule | 6694.9626 | 249.6065 | 6431.59 | 6681.1965 | 99.79%
10 | Gadchiroli | 2482.0719 | -57.1265 | 2681.6552 | 2624.5288 | 105.7%
11 | Gondiya | 3165.7857 | 209.7041 | 3073.54 | 3283.2441 | 103.7%
12 | Hingoli | 3916.3971 | -9.9915 | 3494.95 | 3484.9585 | 88.98%
13 | Jalgaon | 13562.0856 | 954.4859 | 10797.86 | 11752.3459 | 86.66%
14 | Jalna | 6305.8264 | 184.5371 | 6311.44 | 6495.9771 | 103%
15 | Kolhapur | 10091.1773 | -61.0675 | 9831.93 | 9770.8625 | 96.83%
16 | Latur | 8141.2716 | -603.0336 | 7431.6058 | 6828.5722 | 83.88%
17 | Mumbai | 17975.1264 | -2110.4949 | 13934.93 | 11824.4351 | 65.78%
18 | Nagpur | 9516.2414 | -193.544 | 9476.5939 | 9283.0499 | 97.55%
19 | Nanded | 9922.9977 | -90.1167 | 8868.4398 | 8778.323 | 88.46%
20 | Nandurbar | 4494.7056 | 475.8252 | 4111.8 | 4587.6252 | 102.1%
21 | Nashik | 17025.2082 | 452.5655 | 14588.59 | 15041.1555 | 88.35%
22 | Osmanabad | 4686.3201 | 197.9333 | 4401.35 | 4599.2833 | 98.14%
23 | Parbhani | 6164.9348 | 154.7529 | 5475.36 | 5630.1129 | 91.32%
24 | Pune | 18894.2176 | 719.4229 | 17214.371 | 17933.7939 | 94.92%
25 | Raigad | 5090.7318 | 0.77507 | 5149.33 | 5150.1051 | 101.2%
26 | Ratnagiri | 3555.3787 | 176.6414 | 3484.34 | 3660.9814 | 103%
27 | Sangli | 7629.4197 | 47.2662 | 7871.53 | 7918.7962 | 103.8%
28 | Satara | 6811.3122 | 442.5275 | 7324.68 | 7767.2075 | 114%
29 | Sindhudurga | 1808.0832 | 34.9413 | 1822.26 | 1857.2013 | 102.7%
30 | Solapur | 12650.5648 | 91.511 | 12946.09 | 13037.601 | 103.1%
31 | Thane | 13524.0009 | -374.6099 | 12154.5708 | 11779.9609 | 87.1%
32 | Palghar | 6222.447 | 162.702 | 5287.7 | 5450.402 | 87.59%
33 | Wardha | 2482.3837 | 117.3024 | 2488.07 | 2605.3724 | 105%
34 | Washim | 3548.4949 | 366.3079 | 3971.67 | 4337.9779 | 122.2%
35 | Yavatmal | 7251.2055 | -43.5216 | 7203.29 | 7159.7684 | 98.74%
| TOTAL | 273444.7804 | 1936.9052 | 255459.1197 | 257396.0249 | 94.13%
3.6) Foodgrains Allocation, Lifting (availibility) & Utilisation
Allocation | T. Availibility | % T. Availibility | Utilisation | % Utilisation
273444.7804 | 257396.0249 | 94.13% | 235248.7811 | 86.03%
3.7) District-wise Utilisation of foodgrains (Source data: Table AT-6 & 6A of AWP&B 2019-20)
Sl. No. | District | Allocation | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5
1 | Ahmednagar | 12841.6365 | 12094.4742 | 94.18%
2 | Akola | 4156.279 | 4116.5222 | 99.04%
3 | Amravati | 6756.8062 | 6402.7774 | 94.76%
4 | Aurangabad | 11967.8559 | 10173.5633 | 85.01%
5 | Beed | 9368.5207 | 7861.789 | 83.92%
6 | Bhandara | 2924.1712 | 2748.9486 | 94.01%
7 | Buldhana | 7238.512 | 6422.1082 | 88.72%
8 | Chandrapur | 4577.6461 | 4226.162 | 92.32%
9 | Dhule | 6694.9626 | 5659.3125 | 84.53%
10 | Gadchiroli | 2482.0719 | 2349.2163 | 94.65%
11 | Gondiya | 3165.7857 | 2775.8834 | 87.68%
12 | Hingoli | 3916.3971 | 2786.4587 | 71.15%
13 | Jalgaon | 13562.0856 | 10170.3506 | 74.99%
14 | Jalna | 6305.8264 | 5464.1696 | 86.65%
15 | Kolhapur | 10091.1773 | 8664.7705 | 85.86%
16 | Latur | 8141.2716 | 6434.7753 | 79.04%
17 | Mumbai | 17975.1264 | 12013.8422 | 66.84%
18 | Nagpur | 9516.2414 | 8703.0006 | 91.45%
19 | Nanded | 9922.9977 | 7784.3383 | 78.45%
20 | Nandurbar | 4494.7056 | 3895.2839 | 86.66%
21 | Nashik | 17025.2082 | 14367.8669 | 84.39%
22 | Osmanabad | 4686.3201 | 4200.2681 | 89.63%
23 | Parbhani | 6164.9348 | 5016.6202 | 81.37%
24 | Pune | 18894.2176 | 17243.0334 | 91.26%
25 | Raigad | 5090.7318 | 4191.4482 | 82.33%
26 | Ratnagiri | 3555.3787 | 3321.8443 | 93.43%
27 | Sangli | 7629.4197 | 7153.2159 | 93.76%
28 | Satara | 6811.3122 | 6846.9177 | 100.5%
29 | Sindhudurga | 1808.0832 | 1579.6564 | 87.37%
30 | Solapur | 12650.5648 | 11871.3823 | 93.84%
31 | Thane | 13524.0009 | 11273.3692 | 83.36%
32 | Palghar | 6222.447 | 5248.8221 | 84.35%
33 | Wardha | 2482.3837 | 2432.5172 | 97.99%
34 | Washim | 3548.4949 | 3321.2536 | 93.6%
35 | Yavatmal | 7251.2055 | 6432.8184 | 88.71%
| TOTAL | 273444.7804 | 235248.7811 | 86.03%
3.8) Cost of Foodgrains, Payment to FCI
Allocation | Bills submited by FCI | Payment made to FCI | % payment
8136.82 | 7663.77 | 7462.62 | 97.38%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 01.04.2018 (Source data: Table AT-7 & 7A of AWP&B 2019-20)
(Rs. In lakh)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2018 | % of OB on allocation
1 | 2 | 3 | 4 | 5
1 | Ahmednagar | 5404.6628 | -123.57 | -2.286%
2 | Akola | 1829.7832 | 20.5204 | 1.121%
3 | Amravati | 3011.2336 | 32.5784 | 1.082%
4 | Aurangabad | 4599.24 | 30.1348 | 0.6552%
5 | Beed | 3781.89 | 1.7206 | 0.0455%
6 | Bhandara | 1318.0414 | -3.4072 | -0.2585%
7 | Buldhana | 3206.1143 | 19.2449 | 0.6003%
8 | Chandrapur | 2048.9393 | 12.1893 | 0.5949%
9 | Dhule | 2773.02 | -38.3987 | -1.385%
10 | Gadchiroli | 1209.5481 | -18.5238 | -1.531%
11 | Gondiya | 1440.4794 | 14.4436 | 1.003%
12 | Hingoli | 1656.8 | 2.6261 | 0.1585%
13 | Jalgaon | 5165.8211 | 20.3078 | 0.3931%
14 | Jalna | 2853.3499 | 48.4386 | 1.698%
15 | Kolhapur | 4520.43 | 38.7382 | 0.857%
16 | Latur | 3867.43 | 16.9185 | 0.4375%
17 | Mumbai | 8387.32 | 125.2193 | 1.493%
18 | Nagpur | 4534.3599 | -23.1196 | -0.5099%
19 | Nanded | 4191.66 | 66.0947 | 1.577%
20 | Nandurbar | 2150.2382 | 6.9959 | 0.3254%
21 | Nashik | 7177.09 | 204.8958 | 2.855%
22 | Osmanabad | 2056.2201 | 15.2252 | 0.7404%
23 | Parbhani | 2464.99 | 54.4741 | 2.21%
24 | Pune | 7999.58 | 70.7592 | 0.8845%
25 | Raigad | 2208.8169 | 11.11 | 0.503%
26 | Ratnagiri | 1546.7484 | 82.1101 | 5.309%
27 | Sangli | 3322.0559 | 9.7279 | 0.2928%
28 | Satara | 2964.0694 | 117.4236 | 3.962%
29 | Sindhudurga | 792.5191 | 19.2923 | 2.434%
30 | Solapur | 5516.8638 | 45.0954 | 0.8174%
31 | Thane | 5521.89 | 38.002 | 0.6882%
32 | Palghar | 2554.05 | 30.4088 | 1.191%
33 | Wardha | 1078.552 | 54.9212 | 5.092%
34 | Washim | 1541.8616 | -15.917 | -1.032%
35 | Yavatmal | 3150.8517 | 18.8071 | 0.5969%
| TOTAL | 117846.52 | 1005.4878 | 0.8532%
4.1.2) District-wise unspent balance as on 31.03.2019 Source data: Table AT-7 & 7A of AWP&B 2019-20)
(Rs. In lakh)
S.No. | Name of District | Allocation | Unspent Balance as on 31.03.2019 | % of UB on allocation
1 | 2 | 3 | 4 | 5
1 | Ahmednagar | 5404.6628 | 25.8273 | 0.4779%
2 | Akola | 1829.7832 | 61.733 | 3.374%
3 | Amravati | 3011.2336 | 261.8413 | 8.695%
4 | Aurangabad | 4599.24 | 208.7528 | 4.539%
5 | Beed | 3781.89 | 367.3924 | 9.715%
6 | Bhandara | 1318.0414 | 120.244 | 9.123%
7 | Buldhana | 3206.1143 | 434.8944 | 13.56%
8 | Chandrapur | 2048.9393 | 224.854 | 10.97%
9 | Dhule | 2773.02 | 275.4749 | 9.934%
10 | Gadchiroli | 1209.5481 | 170.1753 | 14.07%
11 | Gondiya | 1440.4794 | 248.8078 | 17.27%
12 | Hingoli | 1656.8 | 448.5225 | 27.07%
13 | Jalgaon | 5165.8211 | 766.7812 | 14.84%
14 | Jalna | 2853.3499 | 527.4001 | 18.48%
15 | Kolhapur | 4520.43 | 794.2935 | 17.57%
16 | Latur | 3867.43 | 1088.274 | 28.14%
17 | Mumbai | 8387.32 | 3293.2357 | 39.26%
18 | Nagpur | 4534.3599 | 730.1303 | 16.1%
19 | Nanded | 4191.66 | 874.9907 | 20.87%
20 | Nandurbar | 2150.2382 | 464.4128 | 21.6%
21 | Nashik | 7177.09 | 1138.5774 | 15.86%
22 | Osmanabad | 2056.2201 | 246.3451 | 11.98%
23 | Parbhani | 2464.99 | 339.4971 | 13.77%
24 | Pune | 7999.58 | 578.2934 | 7.229%
25 | Raigad | 2208.8169 | 398.6099 | 18.05%
26 | Ratnagiri | 1546.7484 | 185.5622 | 12%
27 | Sangli | 3322.0559 | 223.6651 | 6.733%
28 | Satara | 2964.0694 | 106.4366 | 3.591%
29 | Sindhudurga | 792.5191 | 125.4814 | 15.83%
30 | Solapur | 5516.8638 | 403.2925 | 7.31%
31 | Thane | 5521.89 | 661.4426 | 11.98%
32 | Palghar | 2554.05 | 303.5373 | 11.88%
33 | Wardha | 1078.552 | 76.7101 | 7.112%
34 | Washim | 1541.8616 | 82.8452 | 5.373%
35 | Yavatmal | 3150.8517 | 374.3781 | 11.88%
| TOTAL | 117846.52 | 16632.712 | 14.11%
4.2) Cooking cost allocation and disbursed to Districts
(Rs. In lakh)
Allocation | OB as on 01.4.18 | Disbursed to Dist | Total Availibility | % Availibility
117846.52 | 1005.4878 | 117846.5155 | 118852.0033 | 100.9%
4.3) District-wise Cooking Cost availability (Source data: Table AT-7 & 7A of AWP&B 2019-20)
(Rs. In lakh)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2018 | Cooking assistance received | Total Availibility of cooking cost | % Availibility of cooking cost
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ahmednagar | 5404.6628 | -123.57 | 5404.6628 | 5281.0928 | 97.71%
2 | Akola | 1829.7832 | 20.5204 | 1829.7832 | 1850.3036 | 101.1%
3 | Amravati | 3011.2336 | 32.5784 | 3011.2336 | 3043.812 | 101.1%
4 | Aurangabad | 4599.24 | 30.1348 | 4599.24 | 4629.3748 | 100.7%
5 | Beed | 3781.89 | 1.7206 | 3781.89 | 3783.6106 | 100%
6 | Bhandara | 1318.0414 | -3.4072 | 1318.0414 | 1314.6343 | 99.74%
7 | Buldhana | 3206.1143 | 19.2449 | 3206.1143 | 3225.3593 | 100.6%
8 | Chandrapur | 2048.9393 | 12.1893 | 2048.9393 | 2061.1286 | 100.6%
9 | Dhule | 2773.02 | -38.3987 | 2773.02 | 2734.6213 | 98.62%
10 | Gadchiroli | 1209.5481 | -18.5238 | 1209.5481 | 1191.0243 | 98.47%
11 | Gondiya | 1440.4794 | 14.4436 | 1440.4794 | 1454.9229 | 101%
12 | Hingoli | 1656.8 | 2.6261 | 1656.8 | 1659.4261 | 100.2%
13 | Jalgaon | 5165.8211 | 20.3078 | 5165.8211 | 5186.1289 | 100.4%
14 | Jalna | 2853.3499 | 48.4386 | 2853.3499 | 2901.7885 | 101.7%
15 | Kolhapur | 4520.43 | 38.7382 | 4520.43 | 4559.1682 | 100.9%
16 | Latur | 3867.43 | 16.9185 | 3867.43 | 3884.3485 | 100.4%
17 | Mumbai | 8387.32 | 125.2193 | 8387.32 | 8512.5393 | 101.5%
18 | Nagpur | 4534.3599 | -23.1196 | 4534.3599 | 4511.2403 | 99.49%
19 | Nanded | 4191.66 | 66.0947 | 4191.66 | 4257.7547 | 101.6%
20 | Nandurbar | 2150.2382 | 6.9959 | 2150.2382 | 2157.234 | 100.3%
21 | Nashik | 7177.09 | 204.8958 | 7177.09 | 7381.9858 | 102.9%
22 | Osmanabad | 2056.2201 | 15.2252 | 2056.2201 | 2071.4454 | 100.7%
23 | Parbhani | 2464.99 | 54.4741 | 2464.9855 | 2519.4596 | 102.2%
24 | Pune | 7999.58 | 70.7592 | 7999.58 | 8070.3392 | 100.9%
25 | Raigad | 2208.8169 | 11.11 | 2208.8169 | 2219.927 | 100.5%
26 | Ratnagiri | 1546.7484 | 82.1101 | 1546.7484 | 1628.8585 | 105.3%
27 | Sangli | 3322.0559 | 9.7279 | 3322.0559 | 3331.7838 | 100.3%
28 | Satara | 2964.0694 | 117.4236 | 2964.0694 | 3081.493 | 104%
29 | Sindhudurga | 792.5191 | 19.2923 | 792.5191 | 811.8115 | 102.4%
30 | Solapur | 5516.8638 | 45.0954 | 5516.8638 | 5561.9592 | 100.8%
31 | Thane | 5521.89 | 38.002 | 5521.89 | 5559.892 | 100.7%
32 | Palghar | 2554.05 | 30.4088 | 2554.05 | 2584.4588 | 101.2%
33 | Wardha | 1078.552 | 54.9212 | 1078.552 | 1133.4732 | 105.1%
34 | Washim | 1541.8616 | -15.917 | 1541.8616 | 1525.9446 | 98.97%
35 | Yavatmal | 3150.8517 | 18.8071 | 3150.8517 | 3169.6588 | 100.6%
| TOTAL | 117846.52 | 1005.4878 | 117846.5155 | 118852.0033 | 100.9%
4.4) Cooking Cost Utilisation |  |  |  | (Rs. In lakh)
Allocation | Total available | % available | Utilisation | % Utilisation
117846.52 | 118852.0033 | 100.9% | 102219.2912 | 86.74%
4.5) District-wise Utilisation of Cooking cost (Source data: Table AT-7 & 7A of AWP&B 2019-20)
(Rs. In lakh)
S.No. | Name of District | Allocation | Utilisation of Cooking assistance | % Utilisation
1 | 2 | 3 | 4 | 5
1 | Ahmednagar | 5404.6628 | 5255.2655 | 97.24%
2 | Akola | 1829.7832 | 1788.5706 | 97.75%
3 | Amravati | 3011.2336 | 2781.9706 | 92.39%
4 | Aurangabad | 4599.24 | 4420.622 | 96.12%
5 | Beed | 3781.89 | 3416.2182 | 90.33%
6 | Bhandara | 1318.0414 | 1194.3903 | 90.62%
7 | Buldhana | 3206.1143 | 2790.4649 | 87.04%
8 | Chandrapur | 2048.9393 | 1836.2745 | 89.62%
9 | Dhule | 2773.02 | 2459.1463 | 88.68%
10 | Gadchiroli | 1209.5481 | 1020.849 | 84.4%
11 | Gondiya | 1440.4794 | 1206.1152 | 83.73%
12 | Hingoli | 1656.8 | 1210.9036 | 73.09%
13 | Jalgaon | 5165.8211 | 4419.3477 | 85.55%
14 | Jalna | 2853.3499 | 2374.3883 | 83.21%
15 | Kolhapur | 4520.43 | 3764.8747 | 83.29%
16 | Latur | 3867.43 | 2796.0744 | 72.3%
17 | Mumbai | 8387.32 | 5219.3036 | 62.23%
18 | Nagpur | 4534.3599 | 3781.11 | 83.39%
19 | Nanded | 4191.66 | 3382.764 | 80.7%
20 | Nandurbar | 2150.2382 | 1692.8212 | 78.73%
21 | Nashik | 7177.09 | 6243.4084 | 86.99%
22 | Osmanabad | 2056.2201 | 1825.1002 | 88.76%
23 | Parbhani | 2464.99 | 2179.9626 | 88.44%
24 | Pune | 7999.58 | 7492.0459 | 93.66%
25 | Raigad | 2208.8169 | 1821.317 | 82.46%
26 | Ratnagiri | 1546.7484 | 1443.2963 | 93.31%
27 | Sangli | 3322.0559 | 3108.1187 | 93.56%
28 | Satara | 2964.0694 | 2975.0564 | 100.4%
29 | Sindhudurga | 792.5191 | 686.3301 | 86.6%
30 | Solapur | 5516.8638 | 5158.6667 | 93.51%
31 | Thane | 5521.89 | 4898.4494 | 88.71%
32 | Palghar | 2554.05 | 2280.9216 | 89.31%
33 | Wardha | 1078.552 | 1056.7632 | 97.98%
34 | Washim | 1541.8616 | 1443.0994 | 93.59%
35 | Yavatmal | 3150.8517 | 2795.2807 | 88.72%
| TOTAL | 117846.52 | 102219.2912 | 86.74%
5. Reconciliation of Utilisation and Performance during 2018-19 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost (Source data: para 3.7 and 4.5 above)
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | Ahmednagar | 94.18% | 97.24% | 3.054%
2 | Akola | 99.04% | 97.75% | -1.296%
3 | Amravati | 94.76% | 92.39% | -2.374%
4 | Aurangabad | 85.01% | 96.12% | 11.11%
5 | Beed | 83.92% | 90.33% | 6.414%
6 | Bhandara | 94.01% | 90.62% | -3.389%
7 | Buldhana | 88.72% | 87.04% | -1.686%
8 | Chandrapur | 92.32% | 89.62% | -2.701%
9 | Dhule | 84.53% | 88.68% | 4.15%
10 | Gadchiroli | 94.65% | 84.4% | -10.25%
11 | Gondiya | 87.68% | 83.73% | -3.954%
12 | Hingoli | 71.15% | 73.09% | 1.938%
13 | Jalgaon | 74.99% | 85.55% | 10.56%
14 | Jalna | 86.65% | 83.21% | -3.439%
15 | Kolhapur | 85.86% | 83.29% | -2.579%
16 | Latur | 79.04% | 72.3% | -6.741%
17 | Mumbai | 66.84% | 62.23% | -4.607%
18 | Nagpur | 91.45% | 83.39% | -8.066%
19 | Nanded | 78.45% | 80.7% | 2.255%
20 | Nandurbar | 86.66% | 78.73% | -7.937%
21 | Nashik | 84.39% | 86.99% | 2.599%
22 | Osmanabad | 89.63% | 88.76% | -0.8683%
23 | Parbhani | 81.37% | 88.44% | 7.064%
24 | Pune | 91.26% | 93.66% | 2.395%
25 | Raigad | 82.33% | 82.46% | 0.1218%
26 | Ratnagiri | 93.43% | 93.31% | -0.1199%
27 | Sangli | 93.76% | 93.56% | -0.1982%
28 | Satara | 100.5% | 100.4% | -0.1521%
29 | Sindhudurga | 87.37% | 86.6% | -0.7653%
30 | Solapur | 93.84% | 93.51% | -0.3335%
31 | Thane | 83.36% | 88.71% | 5.351%
32 | Palghar | 84.35% | 89.31% | 4.953%
33 | Wardha | 97.99% | 97.98% | -0.01138%
34 | Washim | 93.6% | 93.59% | -0.001509%
35 | Yavatmal | 88.71% | 88.72% | 0.001304%
| TOTAL | 86.03% | 86.74% | 0.7078%
5.2 Reconciliation of Food grains utilisation during 2018-19 (Source data: para 2.7 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 2018-19 | Expected consumption of food grains | Actual consumption of food grains | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | Ahmednagar | 101508855 | 12094.4742 | 12094.4742 | 100%
2 | Akola | 34109970 | 4116.5222 | 4116.5222 | 100%
3 | Amravati | 53385628 | 6425.226 | 6402.7774 | 99.65%
4 | Aurangabad | 85475585 | 10173.5633 | 10173.5633 | 100%
5 | Beed | 66439131 | 7865.0045 | 7861.789 | 99.96%
6 | Bhandara | 22815132 | 2748.9486 | 2748.9486 | 100%
7 | Buldhana | 53713623 | 6422.1082 | 6422.1082 | 100%
8 | Chandrapur | 35241795 | 4226.162 | 4226.162 | 100%
9 | Dhule | 47845481 | 5674.4806 | 5659.3125 | 99.73%
10 | Gadchiroli | 19958464 | 2349.2163 | 2349.2163 | 100%
11 | Gondiya | 23111752 | 2775.8834 | 2775.8834 | 100%
12 | Hingoli | 23844691 | 2786.4587 | 2786.4587 | 100%
13 | Jalgaon | 85969165 | 10187.6022 | 10170.3506 | 99.83%
14 | Jalna | 46223523 | 5464.1696 | 5464.1696 | 100%
15 | Kolhapur | 72312701 | 8664.7705 | 8664.7705 | 100%
16 | Latur | 54171570 | 6434.7753 | 6434.7753 | 100%
17 | Mumbai | 97745749 | 12013.8422 | 12013.8422 | 100%
18 | Nagpur | 71379248 | 8703.0006 | 8703.0006 | 100%
19 | Nanded | 66432995 | 7784.3383 | 7784.3383 | 100%
20 | Nandurbar | 33528582 | 3895.2839 | 3895.2839 | 100%
21 | Nashik | 121633159 | 14367.8669 | 14367.8669 | 100%
22 | Osmanabad | 35281451 | 4200.2681 | 4200.2681 | 100%
23 | Parbhani | 42798922 | 5045.1386 | 5016.6202 | 99.43%
24 | Pune | 143518012 | 17243.0334 | 17243.0334 | 100%
25 | Raigad | 35371298 | 4191.4482 | 4191.4482 | 100%
26 | Ratnagiri | 27531843 | 3321.8443 | 3321.8443 | 100%
27 | Sangli | 59801164 | 7158.6691 | 7153.2159 | 99.92%
28 | Satara | 57293186 | 6846.9177 | 6846.9177 | 100%
29 | Sindhudurga | 13061860 | 1579.6564 | 1579.6564 | 100%
30 | Solapur | 100765192 | 11871.3823 | 11871.3823 | 100%
31 | Thane | 94645839 | 11293.2959 | 11273.3692 | 99.82%
32 | Palghar | 44768184 | 5248.8221 | 5248.8221 | 100%
33 | Wardha | 19719041 | 2432.5172 | 2432.5172 | 100%
34 | Washim | 27725959 | 3321.2536 | 3321.2536 | 100%
35 | Yavatmal | 54343815 | 6432.8184 | 6432.8184 | 100%
| TOTAL | 1973472565 | 235360.763 | 235248.7811 | 99.95%
5.3 Reconciliation of Cooking Cost utilisation during 2018-19 (Source data: para 2.5 and 4.7 above)
(Rs. in Lakh)
Sr. No. | District | No. of Meals served during 2018-19 | Expected expenditure of cooking cost | Actual expenditure of cooking cost | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | Ahmednagar | 101508855 | 5255.2655 | 5255.2655 | 100%
2 | Akola | 34109970 | 1788.5706 | 1788.5706 | 100%
3 | Amravati | 53385628 | 2791.7133 | 2781.9706 | 99.65%
4 | Aurangabad | 85475585 | 4420.622 | 4420.622 | 100%
5 | Beed | 66439131 | 3417.6137 | 3416.2182 | 99.96%
6 | Bhandara | 22815132 | 1194.3903 | 1194.3903 | 100%
7 | Buldhana | 53713623 | 2790.4649 | 2790.4649 | 100%
8 | Chandrapur | 35241795 | 1836.2745 | 1836.2745 | 100%
9 | Dhule | 47845481 | 2465.7292 | 2459.1463 | 99.73%
10 | Gadchiroli | 19958464 | 1020.849 | 1020.849 | 100%
11 | Gondiya | 23111752 | 1206.1152 | 1206.1152 | 100%
12 | Hingoli | 23844691 | 1210.9036 | 1210.9036 | 100%
13 | Jalgaon | 85969165 | 4426.8349 | 4419.3477 | 99.83%
14 | Jalna | 46223523 | 2374.3883 | 2374.3883 | 100%
15 | Kolhapur | 72312701 | 3764.8747 | 3764.8747 | 100%
16 | Latur | 54171570 | 2796.0744 | 2796.0744 | 100%
17 | Mumbai | 97745749 | 5219.3036 | 5219.3036 | 100%
18 | Nagpur | 71379248 | 3781.11 | 3781.11 | 100%
19 | Nanded | 66432995 | 3382.764 | 3382.764 | 100%
20 | Nandurbar | 33528582 | 1692.8212 | 1692.8212 | 100%
21 | Nashik | 121633159 | 6243.4084 | 6243.4084 | 100%
22 | Osmanabad | 35281451 | 1825.1002 | 1825.1002 | 100%
23 | Parbhani | 42798922 | 2192.3396 | 2179.9626 | 99.44%
24 | Pune | 143518012 | 7492.0459 | 7492.0459 | 100%
25 | Raigad | 35371298 | 1821.317 | 1821.317 | 100%
26 | Ratnagiri | 27531843 | 1443.2963 | 1443.2963 | 100%
27 | Sangli | 59801164 | 3110.4854 | 3108.1187 | 99.92%
28 | Satara | 57293186 | 2975.0564 | 2975.0564 | 100%
29 | Sindhudurga | 13061860 | 686.3301 | 686.3301 | 100%
30 | Solapur | 100765192 | 5158.6667 | 5158.6667 | 100%
31 | Thane | 94645839 | 4907.0976 | 4898.4494 | 99.82%
32 | Palghar | 44768184 | 2280.9216 | 2280.9216 | 100%
33 | Wardha | 19719041 | 1056.7632 | 1056.7632 | 100%
34 | Washim | 27725959 | 1443.0994 | 1443.0994 | 100%
35 | Yavatmal | 54343815 | 2795.2807 | 2795.2807 | 100%
| TOTAL | 1973472565 | 102267.8914 | 102219.2912 | 99.95%
6. ANALYSIS of HONORIUM, To COOK-CUM-HELPERS
6.1) District-wise number of cook-cum-Helpers approved by PAB and engaged by State
(Refer table AT_8 and AT-8A,AWP&B, 2019-20)
S.No. | Name of District | PAB Approval | Engaged by State | Not engaged
1 | 2 | 3 | 4 | 5 = (4 - 3)
1 | Ahmednagar | 9554 | 9457 | -97
2 | Akola | 3257 | 3257 | 0
3 | Amravati | 4665 | 4461 | -204
4 | Aurangabad | 7568 | 6290 | -1278
5 | Beed | 6846 | 6146 | -700
6 | Bhandara | 2256 | 2256 | 0
7 | Buldhana | 4609 | 4448 | -161
8 | Chandrapur | 4165 | 4165 | 0
9 | Dhule | 3428 | 3428 | 0
10 | Gadchiroli | 3435 | 3435 | 0
11 | Gondiya | 2560 | 2560 | 0
12 | Hingoli | 2327 | 2305 | -22
13 | Jalgaon | 6714 | 5936 | -778
14 | Jalna | 4219 | 4138 | -81
15 | Kolhapur | 6264 | 5996 | -268
16 | Latur | 5163 | 5163 | 0
17 | Mumbai | 5306 | 5204 | -102
18 | Nagpur | 5765 | 5667 | -98
19 | Nanded | 6004 | 5948 | -56
20 | Nandurbar | 4106 | 3489 | -617
21 | Nashik | 9613 | 9280 | -333
22 | Osmanabad | 3327 | 3327 | 0
23 | Parbhani | 3452 | 3386 | -66
24 | Pune | 9525 | 9525 | 0
25 | Raigad | 5220 | 5004 | -216
26 | Ratnagiri | 5059 | 4474 | -585
27 | Sangli | 5021 | 4972 | -49
28 | Satara | 6234 | 6138 | -96
29 | Sindhudurga | 2629 | 2343 | -286
30 | Solapur | 8813 | 7711 | -1102
31 | Thane | 4196 | 4187 | -9
32 | Palghar | 3778 | 3515 | -263
33 | Wardha | 2311 | 2311 | 0
34 | Washim | 2708 | 2211 | -497
35 | Yavatmal | 5236 | 5236 | 0
| TOTAL | 175333 | 167369 | -7964
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
(Refer table AT_8 and AT-8A, AWP&B, 2019-20)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2018 | Amount released | Total availability | % Availibilty
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ahmednagar | 955.4 | -9.11 | 959.8075 | 950.6975 | 99.51%
2 | Akola | 325.7 | -89.8 | 308.26 | 218.46 | 67.07%
3 | Amravati | 466.5 | 36.55 | 507.2956 | 543.8456 | 116.6%
4 | Aurangabad | 756.8 | 18.24 | 794.2692 | 812.5092 | 107.4%
5 | Beed | 684.6 | -79.21 | 685.4 | 606.19 | 88.55%
6 | Bhandara | 225.6 | -28.51 | 225.36 | 196.85 | 87.26%
7 | Buldhana | 460.9 | 376.31 | 483.0346 | 859.3446 | 186.4%
8 | Chandrapur | 416.5 | 241.64 | 416.5 | 658.14 | 158%
9 | Dhule | 342.8 | -478.81 | 355.6838 | -123.1262 | -35.92%
10 | Gadchiroli | 343.5 | 36.16 | 344.9466 | 381.1066 | 110.9%
11 | Gondiya | 256 | 8.43 | 256 | 264.43 | 103.3%
12 | Hingoli | 232.7 | -7.3 | 231.908 | 224.608 | 96.52%
13 | Jalgaon | 671.4 | -256.53 | 890.7141 | 634.1841 | 94.46%
14 | Jalna | 421.9 | -151.67 | 422.0044 | 270.3344 | 64.08%
15 | Kolhapur | 626.4 | -36.29 | 616.752 | 580.462 | 92.67%
16 | Latur | 516.3 | -169.79 | 516.4091 | 346.6191 | 67.14%
17 | Mumbai | 530.6 | -53.48 | 526.928 | 473.448 | 89.23%
18 | Nagpur | 576.5 | -93.81 | 572.972 | 479.162 | 83.12%
19 | Nanded | 600.4 | -313.76 | 598.384 | 284.624 | 47.41%
20 | Nandurbar | 410.6 | 209.13 | 388.388 | 597.518 | 145.5%
21 | Nashik | 961.3 | 191.68 | 949.312 | 1140.992 | 118.7%
22 | Osmanabad | 332.7 | 36.12 | 332.7 | 368.82 | 110.9%
23 | Parbhani | 345.2 | 169.48 | 394.1432 | 563.6232 | 163.3%
24 | Pune | 952.5 | 72.63 | 952.5 | 1025.13 | 107.6%
25 | Raigad | 522 | 2.37 | 514.224 | 516.594 | 98.96%
26 | Ratnagiri | 505.9 | 163.43 | 484.84 | 648.27 | 128.1%
27 | Sangli | 502.1 | 14.15 | 500.336 | 514.486 | 102.5%
28 | Satara | 623.4 | 494.9 | 619.944 | 1114.844 | 178.8%
29 | Sindhudurga | 262.9 | -22.55 | 252.604 | 230.054 | 87.51%
30 | Solapur | 881.3 | 818.26 | 842.508 | 1660.768 | 188.4%
31 | Thane | 419.6 | 250.85 | 419.276 | 670.126 | 159.7%
32 | Palghar | 377.8 | -5.29 | 368.332 | 363.042 | 96.09%
33 | Wardha | 231.1 | 78.7 | 231.02 | 309.72 | 134%
34 | Washim | 270.8 | 82.5 | 311.8364 | 394.3364 | 145.6%
35 | Yavatmal | 523.6 | 126.91 | 522.8 | 649.71 | 124.1%
| TOTAL | 17533.3 | 1632.53 | 17797.3925 | 19429.9225 | 110.8%
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2019-20)
S.No. | Name of District | Allocation | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation
1 | 2 | 3 | 4 | 5 | 6
1 | Ahmednagar | 955.4 | 950.6975 | 945.7 | 98.98%
2 | Akola | 325.7 | 218.46 | 325.7 | 100%
3 | Amravati | 466.5 | 543.8456 | 446.1 | 95.63%
4 | Aurangabad | 756.8 | 812.5092 | 629 | 83.11%
5 | Beed | 684.6 | 606.19 | 614.6 | 89.78%
6 | Bhandara | 225.6 | 196.85 | 225.6 | 100%
7 | Buldhana | 460.9 | 859.3446 | 444.8 | 96.51%
8 | Chandrapur | 416.5 | 658.14 | 416.5 | 100%
9 | Dhule | 342.8 | -123.1262 | 342.8 | 100%
10 | Gadchiroli | 343.5 | 381.1066 | 343.5 | 100%
11 | Gondiya | 256 | 264.43 | 256 | 100%
12 | Hingoli | 232.7 | 224.608 | 230.5 | 99.05%
13 | Jalgaon | 671.4 | 634.1841 | 593.6 | 88.41%
14 | Jalna | 421.9 | 270.3344 | 413.8 | 98.08%
15 | Kolhapur | 626.4 | 580.462 | 599.6 | 95.72%
16 | Latur | 516.3 | 346.6191 | 516.3 | 100%
17 | Mumbai | 530.6 | 473.448 | 520.4 | 98.08%
18 | Nagpur | 576.5 | 479.162 | 566.7 | 98.3%
19 | Nanded | 600.4 | 284.624 | 594.8 | 99.07%
20 | Nandurbar | 410.6 | 597.518 | 348.9 | 84.97%
21 | Nashik | 961.3 | 1140.992 | 928 | 96.54%
22 | Osmanabad | 332.7 | 368.82 | 332.7 | 100%
23 | Parbhani | 345.2 | 563.6232 | 338.6 | 98.09%
24 | Pune | 952.5 | 1025.13 | 952.5 | 100%
25 | Raigad | 522 | 516.594 | 500.4 | 95.86%
26 | Ratnagiri | 505.9 | 648.27 | 447.4 | 88.44%
27 | Sangli | 502.1 | 514.486 | 497.2 | 99.02%
28 | Satara | 623.4 | 1114.844 | 613.8 | 98.46%
29 | Sindhudurga | 262.9 | 230.054 | 234.3 | 89.12%
30 | Solapur | 881.3 | 1660.768 | 771.1 | 87.5%
31 | Thane | 419.6 | 670.126 | 418.7 | 99.79%
32 | Palghar | 377.8 | 363.042 | 351.5 | 93.04%
33 | Wardha | 231.1 | 309.72 | 231.1 | 100%
34 | Washim | 270.8 | 394.3364 | 221.1 | 81.65%
35 | Yavatmal | 523.6 | 649.71 | 523.6 | 100%
| TOTAL | 17533.3 | 19429.9225 | 16736.9 | 95.46%
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2019-20)
S.No. | Name of District | Allocation | Total Availability | Unspent balance as on 31.03.2019 | % of UB as on Allocation
1 | 2 | 3 | 4 | 5 | 6
1 | Ahmednagar | 955.4 | 950.6975 | 1.285 | 0.1345%
2 | Akola | 325.7 | 218.46 | -107.24 | -32.93%
3 | Amravati | 466.5 | 543.8456 | -25.8674 | -5.545%
4 | Aurangabad | 756.8 | 812.5092 | 88.5682 | 11.7%
5 | Beed | 684.6 | 606.19 | -19.61 | -2.864%
6 | Bhandara | 225.6 | 196.85 | -28.75 | -12.74%
7 | Buldhana | 460.9 | 859.3446 | 215.7322 | 46.81%
8 | Chandrapur | 416.5 | 658.14 | 241.64 | 58.02%
9 | Dhule | 342.8 | -123.1262 | -443.6656 | -129.4%
10 | Gadchiroli | 343.5 | 381.1066 | 27.6801 | 8.058%
11 | Gondiya | 256 | 264.43 | 8.43 | 3.293%
12 | Hingoli | 232.7 | 224.608 | -6.244 | -2.683%
13 | Jalgaon | 671.4 | 634.1841 | -561.6392 | -83.65%
14 | Jalna | 421.9 | 270.3344 | -152.3127 | -36.1%
15 | Kolhapur | 626.4 | 580.462 | -23.426 | -3.74%
16 | Latur | 516.3 | 346.6191 | -169.9036 | -32.91%
17 | Mumbai | 530.6 | 473.448 | -48.584 | -9.156%
18 | Nagpur | 576.5 | 479.162 | -76.806 | -13.32%
19 | Nanded | 600.4 | 284.624 | -311.072 | -51.81%
20 | Nandurbar | 410.6 | 597.518 | 238.746 | 58.15%
21 | Nashik | 961.3 | 1140.992 | 207.664 | 21.6%
22 | Osmanabad | 332.7 | 368.82 | 36.12 | 10.86%
23 | Parbhani | 345.2 | 563.6232 | 55.0392 | 15.94%
24 | Pune | 952.5 | 1025.13 | 72.63 | 7.625%
25 | Raigad | 522 | 516.594 | 12.738 | 2.44%
26 | Ratnagiri | 505.9 | 648.27 | 101.55 | 20.07%
27 | Sangli | 502.1 | 514.486 | 16.502 | 3.287%
28 | Satara | 623.4 | 1114.844 | 499.508 | 80.13%
29 | Sindhudurga | 262.9 | 230.054 | -8.822 | -3.356%
30 | Solapur | 881.3 | 1660.768 | 558.456 | 63.37%
31 | Thane | 419.6 | 670.126 | 51.282 | 12.22%
32 | Palghar | 377.8 | 363.042 | 7.334 | 1.941%
33 | Wardha | 231.1 | 309.72 | 78.62 | 34.02%
34 | Washim | 270.8 | 394.3364 | 17.9634 | 6.633%
35 | Yavatmal | 523.6 | 649.71 | 126.11 | 24.09%
| TOTAL | 17533.3 | 19429.9225 | 679.6556 | 3.876%
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
7.1) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2018-19 | 1753.07 | 1753.07 | 0 | 0%
2 | Opening Balance as on 01.04.2018 | 104.23 | 104.23 | 0 | 0%
3 | Released during 2018-19. | 1648.84 | 1648.84 | 0 | 0%
4 | Total Availibility | 1753.07 | 1753.07 | 0 | 0%
7.2) Utilisation of MME during 2018-19 (Source data: Table AT-10 of AWP&B 2019-20)
|  |  |  | (Rs. In lakh) | (As on 31.03.19)
Sl. No. | Activity | Allocated | Total Availibility | Expenditure | Exp as % of allocation
1 | 2 | 3 | 4 | 5 | 6
1 | School Level Expenses | 876.535 | 876.535 | 1011.2 | 115.4%
2 | Management, Supervision, Training & Internal Monitoring, External Monitoring & Evaluation | 876.535 | 876.535 | 737.04 | 84.09%
Total |  | 1753.07 | 1753.07 | 1748.24 | 99.72%
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
8.1) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Activity | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2018-19 | 2167.48 | 2167.48 | 0 | 0%
2 | Opening Balance as on 01.04.2018 | 0 | 0 | 0 | 0%
3 | Released during 2018-19. | 2167.48 | 2167.48 | 0 | 0%
4 | Total Availibility | 2167.48 | 2167.48 | 0 | 0%
8.2) Utilisation of TA during 2018-19 (Source data: Table AT-9 of AWP&B 2019-20)
(Rs. In lakh)
Allocated for 2018-19 | Total availibility of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7 | 8= (2-5)
2167.48 | 2167.48 | 255459.1197 | 1915.9434 | 1914.13 | 1.8134 | 88.31% | 253.35
9. INFRASTRUCTURE DEVELOPMENT DURING 2018-19 (Primary + Upper primary)
Kitchen-cum-Stores
9.1) Releasing details
9.1.1) Releasing details
Releases for Kitchen sheds by GoI as on 31.3.2019
Schools | Installment | Dated | Units | Amount (Rs in lakh)
Primary + Upper-Primary | 2006-07 |  | 18417 | 11050.2
| 2007-08 |  | 87 | 52.2
| 2008-09 |  | 32355 | 19413
| 2009-10 |  | 1362 | 1421.06
| 2010-11 |  | 7869 | 8260.77
| 2013-14 |  | 6000 | 7834.98
| Grand Total |  | 66090 | 48032.21
9.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-13 | 66090 | 48032.21 | 66090 | 48032.21 | 0% | 0%
9.3) Achievement ( under MDM Funds) (Source data: Table AT-10 of AWP&B 2019-20)
Sanctioned by GoI during 2006-07 to 2018-19 |  | Cosntructed upto 31.03.2019 |  | Achievement as % of allocation
Physical | Financial (Rs in Lakh) | Physical | Financial (Rs in Lakh) | Physical | Financial (Rs in Lakh)
1 | 2 | 3 | 4 | 5 | 6
66090 | 48032.21 | 58090 | 41255.92 | 87.9% | 85.89%
10. Kitchen Devices
Releases for Kitchen Devises by GoI as on 31.03.2019
Schools | Year | Dated | Units | Amount (in lakh)
Primary + Upper Primary | 2006-07 |  | 42450 | 2122.51
| 2007-08 |  | 64539 | 3226.95
| 2008-09 |  | 12797 | 639.85
| 2011-12 |  | 1557 | 77.85
| 2012-13 | Replacement | 42450 | 2122.5
| 2013-14 | Replacement | 64539 | 3226.95
| 2014-15 | Replacement | 12797 | 639.85
| 2014-15 | New | 18793 | 939.65
| 2017-18 | Replacement | 1557 | 77.85
| Grand Total |  | 261479 | 13073.96
10.1) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
For New Units | 140136 | 7006.81 | 140316 | 7015.8 | -0.1284% | -0.1283%
For Replacement | 121343 | 6067.15 | 123020 | 6151 | -1.382% | -1.382%
10.2) Achievement ( under MDM Funds) (Source data: Table AT-11 of AWP&B 2019-20)
Sanctioned during 2006-07 to 2018-19 |  | Achievement (Procured+IP) |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
261479 | 13073.96 | 263336 | 13166.8 | 100.7% | 100.7%
Note on E1051: hp: pl chek
Benchmark (85%)
100%
68%