## Manipur
Government of India
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2019-20
State : Manipur
ANALYSIS SHEET
Section-A : REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2018-19 (1.4.18 to 31.03.19)
1. Calculation of Bench mark for utilisation.
1.1) No. of children
Stage | MDM PAB Approval for 2018-19 | Average number of children availed MDM during 1.4.18 to 31.03.19 (AT-5&5A) | Diff | Diff in %
1 | 2 | 3 | 4=(3-2) | 5=(4/2)*100
Primary | 121595.1591 | 114984 | -6611.1591 | -5.437%
Up Primary | 33978.7426 | 32693 | -1285.7426 | -3.784%
Total | 155575.9017 | 147677 | -7898.9017 | -5.077%
1.2) No. of School working days
PY | 227 | 202 | -25 | -11.01%
UP.PY | 227 | 202 | -25 | -11.01%
1.3) No. of Meals (PY & UP.PY)
Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Diff. | Diff in %
PY | 27602065 | 24772051 | -2830014 | -10.25%
UP PY | 7713233 | 6990803 | -722430 | -9.366%
Total | 35315298 | 31762854 | -3552444 | -10.06%
ii) Base period 01.04.17 to 31.03.18 (As per PAB aaproval = 227 days for Primary & U. Primary)
Stage | No. of Meals as per PAB approval (01.04.18 to 31.3.19) | No. of Meals served as per PAB approval for the period 01.04.18 to 31.03.19 |  | Bench Mark as per State's claim
PY | 27602065 | 24772051 |  | 89.75%
U PY | 7713233 | 6990803 |  | 90.63%
PY & UP PY | 35315298 | 31762854 |  | 89.94%
2. COVERAGE
2.1 Institutions- (Primary) (Source data : Table AT-3A of AWP&B 2019-20)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Imphal West | 245 | 188 | 57 | 23.27%
2 | Imphal East | 236 | 210 | 26 | 11.02%
3 | Jiribam | 124 | 65 | 59 | 47.58%
4 | Thoubal | 160 | 117 | 43 | 26.88%
5 | Kakching | 99 | 73 | 26 | 26.26%
6 | Bishnupur | 174 | 114 | 60 | 34.48%
7 | Ukhrul | 161 | 123 | 38 | 23.6%
8 | Kamjong | 102 | 81 | 21 | 20.59%
9 | Senapati | 275 | 265 | 10 | 3.636%
10 | Kangpokpi | 335 | 328 | 7 | 2.09%
11 | Tamenglong | 214 | 208 | 6 | 2.804%
12 | Noney | 108 | 106 | 2 | 1.852%
13 | Churachandpur | 272 | 272 | 0 | 0%
14 | Pherzwal | 68 | 68 | 0 | 0%
15 | Chandel | 184 | 174 | 10 | 5.435%
16 | Tengnoupal | 100 | 89 | 11 | 11%
TOTAL |  | 2857 | 2481 | 376 | 13.16% |  |  |  | 0.86839
[8 empty] | 3642 | 3306 | 0.90774
2.2 Institutions- (Primary with Upper Primary) (Source data : Table AT-3B of AWP&B 2019-20)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Imphal West | 114 | 127 | -13 | -11.4%
2 | Imphal East | 83 | 88 | -5 | -6.024%
3 | Jiribam | 12 | 13 | -1 | -8.333%
4 | Thoubal | 87 | 89 | -2 | -2.299%
5 | Kakching | 24 | 28 | -4 | -16.67%
6 | Bishnupur | 78 | 78 | 0 | 0%
7 | Ukhrul | 50 | 50 | 0 | 0%
8 | Kamjong | 26 | 27 | -1 | -3.846%
9 | Senapati | 40 | 35 | 5 | 12.5%
10 | Kangpokpi | 62 | 55 | 7 | 11.29%
11 | Tamenglong | 37 | 40 | -3 | -8.108%
12 | Noney | 18 | 20 | -2 | -11.11%
13 | Churachandpur | 81 | 81 | 0 | 0%
14 | Pherzwal | 41 | 41 | 0 | 0%
15 | Chandel | 18 | 28 | -10 | -55.56%
16 | Tengnoupal | 14 | 25 | -11 | -78.57%
| TOTAL | 785 | 825 | -40 | -5.096% |  |  |  | 966 | 1000 | 1.0352
2.2A Institutions- (Upper Primary) (Source data : Table AT-3C of AWP&B 2019-20)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Imphal West | 57 | 52 | 5 | 8.772%
2 | Imphal East | 44 | 44 | 0 | 0%
3 | Jiribam | 8 | 6 | 2 | 25%
4 | Thoubal | 22 | 22 | 0 | 0%
5 | Kakching | 16 | 18 | -2 | -12.5%
6 | Bishnupur | 20 | 19 | 1 | 5%
7 | Ukhrul | 4 | 3 | 1 | 25%
8 | Kamjong | 2 | 2 | 0 | 0%
9 | Senapati | 3 | 4 | -1 | -33.33%
10 | Kangpokpi | 3 | 3 | 0 | 0%
11 | Tamenglong | 0 | 0 | 0 | #DIV/0!
12 | Noney | 0 | 0 | 0 | #DIV/0!
13 | Churachandpur | 0 | 0 | 0 | #DIV/0!
14 | Pherzwal | 0 | 0 | 0 | #DIV/0!
15 | Chandel | 2 | 2 | 0 | 0%
16 | Tengnoupal |  | 0 | 0 | #DIV/0!
| TOTAL | 181 | 175 | 6 | 3.315%
2.3 Coverage Chidlren vs. Enrolment ( Primary) (Source data : Table AT-4 of AWP&B 2019-20)
Sl. No. | Districts | Enrolment as on 30.09.18 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Imphal West | 9521 | 8255 | -1266 | -13.3%
2 | Imphal East | 10225 | 8865 | -1360 | -13.3%
3 | Jiribam | 5383 | 4671 | -712 | -13.23%
4 | Thoubal | 9688 | 8399 | -1289 | -13.31%
5 | Kakching | 3591 | 3115 | -476 | -13.26%
6 | Bishnupur | 7960 | 6896 | -1064 | -13.37%
7 | Ukhrul | 9152 | 7943 | -1209 | -13.21%
8 | Kamjong | 5844 | 5064 | -780 | -13.35%
9 | Senapati | 15024 | 13043 | -1981 | -13.19%
10 | Kangpokpi | 15790 | 13691 | -2099 | -13.29%
11 | Tamenglong | 7407 | 6429 | -978 | -13.2%
12 | Noney | 3765 | 3268 | -497 | -13.2%
13 | Churachandpur | 15205 | 13185 | -2020 | -13.29%
14 | Pherzwal | 4114 | 3560 | -554 | -13.47%
15 | Chandel | 6545 | 5677 | -868 | -13.26%
16 | Tengnoupal | 3371 | 2923 | -448 | -13.29%
| TOTAL | 132585 | 114984 | -17601 | -13.28% |  |  |  | 171169 | 147677 | 0.86276
2.4 Coverage Chidlren vs. Enrolment ( Upper Primary) (Source data : Table AT- 4A of AWP&B 2019-20)
Sl. No. | Districts | Enrolment as on 30.09.18 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Imphal West | 5257 | 4454 | -803 | -15.27%
2 | Imphal East | 5365 | 4541 | -824 | -15.36%
3 | Jiribam | 1763 | 1495 | -268 | -15.2%
4 | Thoubal | 4550 | 3855 | -695 | -15.27%
5 | Kakching | 1952 | 1651 | -301 | -15.42%
6 | Bishnupur | 3210 | 2720 | -490 | -15.26%
7 | Ukhrul | 2237 | 1898 | -339 | -15.15%
8 | Kamjong | 1200 | 1018 | -182 | -15.17%
9 | Senapati | 1716 | 1454 | -262 | -15.27%
10 | Kangpokpi | 2724 | 2308 | -416 | -15.27%
11 | Tamenglong | 1493 | 1267 | -226 | -15.14%
12 | Noney | 747 | 634 | -113 | -15.13%
13 | Churachandpur | 3082 | 2611 | -471 | -15.28%
14 | Pherzwal | 1650 | 1400 | -250 | -15.15%
15 | Chandel | 840 | 713 | -127 | -15.12%
16 | Tengnoupal | 798 | 674 | -124 | -15.54%
| TOTAL | 38584 | 32693 | -5891 | -15.27%
2.5 No. of children ( Primary) (Source data : Table AT-5 of AWP&B 2019-20)
Sl. No. | Districts | No. of children as per PAB Approval for 2018-19 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Imphal West | 10498 | 9927 | -571 | -5.439%
2 | Imphal East | 11075 | 10473 | -602 | -5.436%
3 | Jiribam | 5076 | 4800 | -276 | -5.437%
4 | Thoubal | 10114 | 9564 | -550 | -5.438%
5 | Kakching | 3938 | 3724 | -214 | -5.434%
6 | Bishnupur | 7935 | 7504 | -431 | -5.432%
7 | Ukhrul | 8091 | 7651 | -440 | -5.438%
8 | Kamjong | 5004 | 4732 | -272 | -5.436%
9 | Senapati | 11892 | 11245 | -647 | -5.441%
10 | Kangpokpi | 13152 | 12437 | -715 | -5.436%
11 | Tamenglong | 6322 | 5978 | -344 | -5.441%
12 | Noney | 3205 | 3031 | -174 | -5.429%
13 | Churachandpur | 12991 | 12285 | -706 | -5.435%
14 | Pherzwal | 4095 | 3872 | -223 | -5.446%
15 | Chandel | 5246 | 4961 | -285 | -5.433%
16 | Tengnoupal | 2961 | 2800 | -161 | -5.437%
| TOTAL | 121595 | 114984 | -6611 | -5.437% |  |  |  | 155574
2.6 No. of children ( Upper Primary) (Source data : Table AT-5-A of AWP&B 2019-20)
Sl. No. | Districts | No. of children as per PAB Approval for 2018-19 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Imphal West | 4629 | 4580 | -49 | -1.059%
2 | Imphal East | 4720 | 4581 | -139 | -2.945%
3 | Jiribam | 1554 | 1508 | -46 | -2.96%
4 | Thoubal | 4007 | 3855 | -152 | -3.793%
5 | Kakching | 1716 | 1634 | -82 | -4.779%
6 | Bishnupur | 2827 | 2668 | -159 | -5.624%
7 | Ukhrul | 1973 | 1971 | -2 | -0.1014%
8 | Kamjong | 1058 | 1057 | -1 | -0.09452%
9 | Senapati | 1511 | 1391 | -120 | -7.942%
10 | Kangpokpi | 2399 | 2208 | -191 | -7.962%
11 | Tamenglong | 1317 | 1260 | -57 | -4.328%
12 | Noney | 659 | 631 | -28 | -4.249%
13 | Churachandpur | 2714 | 2585 | -129 | -4.753%
14 | Pherzwal | 1455 | 1386 | -69 | -4.742%
15 | Chandel | 741 | 709 | -32 | -4.318%
16 | Tengnoupal | 699 | 669 | -30 | -4.292%
| TOTAL | 33979 | 32693 | -1286 | -3.785%
2.7 Number of meal to be served and actual number of meal served during 2019-20 (Source data: Table AT-5 & 5A of AWP&B 2019-20)
Sr. No. | District | No of meals to be served during 1.4.18 to 31.03.19 | No of meal served during 1.4.18 to 31.03.19 | % Meals Served |  |  |  |  | Meals to be served |  |  | Meals served
1 | 2 | 3 | 4 | 5
1 | Imphal West | 3433829 | 2452050 | 71.41%
2 | Imphal East | 3585465 | 2744220 | 76.54%
3 | Jiribam | 1505010 | 1230518 | 81.76%
4 | Thoubal | 3205467 | 2572076 | 80.24%
5 | Kakching | 1283458 | 1037260 | 80.82%
6 | Bishnupur | 2442974 | 2219655 | 90.86%
7 | Ukhrul | 2284528 | 1947066 | 85.23%
8 | Kamjong | 1376074 | 1201762 | 87.33%
9 | Senapati | 3042481 | 3209662 | 105.5% |  |  |  |  | PRY | U PRY |  | Pry | U pry |  |  |  | Pry | Upry |  | Total
10 | Kangpokpi | 3530077 | 3726086 | 105.6% |  |  |  | Imphal West | 2383046 | 1050783 | 3433829 | 1499685 | 952365 | 2452050 |  |  | 2064203.7762 | 764569.3102 | 2828773.0864 |  | 0 | 0
11 | Tamenglong | 1734053 | 1770928 | 102.1% |  |  |  | Imphal East | 2514025 | 1071440 | 3585465 | 1773132 | 971088 | 2744220 |  |  | 3584514.6367 | 1016800.0888 | 4601314.7255 |  | 0 | 0
12 | Noney | 877128 | 898022 | 102.4% |  |  |  | Thoubal | 1152252 | 352758 | 1505010 | 910800 | 319718 | 1230518 |  |  | 2792549.7539 | 986465.3573 | 3779015.1112 |  | 0 | 0
13 | Churachandpur | 3565035 | 3397385 | 95.3% |  |  |  | Bishnupur | 2295878 | 909589 | 3205467 | 1747680 | 824396 | 2572076 |  |  | 1874460.7396 | 634012.6481 | 2508473.3877 |  | 0 | 0
14 | Pherzwal | 1259850 | 1067500 | 84.73% |  |  |  | Ukhrul | 893926 | 389532 | 1283458 | 684212 | 353048 | 1037260 |  |  | 3058301.373 | 621778.1984 | 3680079.5714 |  | 0 | 0
15 | Chandel | 1359049 | 1467523 | 108% |  |  |  | Senapati | 1801245 | 641729 | 2442974 | 1638031 | 581624 | 2219655 |  |  | 5214522.8654 | 600661.203 | 5815184.0684 |  | 0 | 0
16 | Tengnoupal | 830820 | 821141 | 98.84% |  |  |  | Tamenglong | 1836657 | 447871 | 2284528 | 1541143 | 405923 | 1947066 |  |  | 3094356.7263 | 285917.4141 | 3380274.1404 |  | 0 | 0
| TOTAL | 35315298 | 31762854 | 89.94% |  |  |  |  | 1135908 | 240166 | 1376074 | 984090 | 217672 | 1201762 | 87.33% |  | 26118832 | 5923820 | 32042652 |  | 0 | 0
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY) | [8 empty] | 2699484 | 342997 | 3042481 | 2898790 | 310872 | 3209662
[9 empty] | 2985504 | 544573 | 3530077 | 3232518 | 493568 | 3726086
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting (Source data: Table AT-6 & 6A of AWP&B 2019-20) | [8 empty] | 1435094 | 298959 | 1734053 | 1499970 | 270958 | 1770928
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff |  |  |  | 727535 | 149593 | 877128 | 762440 | 135582 | 898022
1 | 2 | 3 | 4 | 5(4-3) | 6 |  |  |  | 2948957 | 616078 | 3565035 | 2839010 | 558375 | 3397385
1 | Opening Stock as on 1.4.2018 | 836 | 836 | 0 | 0% |  |  |  | 929565 | 330285 | 1259850 | 768150 | 299350 | 1067500
2 | Allocation for 2018-19 | 3917.19 | 3917.2 | 0.01 | 0.0002553% |  |  |  | 1190842 | 168207 | 1359049 | 1315070 | 152453 | 1467523
3 | Lifting as on 31.03.2019 | 3081.2 | 3081.2 | 0 | 0% |  |  |  | 672147 | 158673 | 830820 | 677330 | 143811 | 821141
[9 empty] | 27602065 | 7713233 | 35315298 | 24772051 | 6990803 | 31762854
3.2) ANALYSIS ON OPENING STOCK AND UNSPENT STOCK OF FOODGRAINS
3.2.1) District-wise opening balance as on 1.4.2018 (Source data: Table AT-6 & 6A of AWP&B 2019-20)
(in MTs)
S.No. | Name of District | Allocation for 2018-19 | Opening Stock as on 1.4.2018 | % of OS on allocation 2018-19 |  |  |  | Allocation |  |  |  |  | O. B.
1 | 2 | 3 | 4 | 5 |  |  |  | Pry | U Pry |  |  | Pry | U Pry
1 | Imphal West | 395.9557 | 81.5177 | 20.59% |  |  |  | 238.3049 | 157.6508 | 395.9557 |  | 56.0237 | 25.494 | 81.5177
2 | Imphal East | 412.2884 | 85.12 | 20.65% |  |  |  | 251.4028 | 160.8856 | 412.2884 |  | 59.1029 | 26.017 | 85.12
3 | Jiribam | 168.1048 | 35.6398 | 21.2% |  |  |  | 115.2253 | 52.8794 | 168.1048 |  | 27.0886 | 8.5512 | 35.6398
4 | Thoubal | 366.0259 | 76.038 | 20.77% |  |  |  | 229.5881 | 136.4378 | 366.0259 |  | 53.9745 | 22.0636 | 76.038
5 | Kakching | 147.9244 | 30.4808 | 20.61% |  |  |  | 89.3927 | 58.5317 | 147.9244 |  | 21.0156 | 9.4653 | 30.4808
6 | Bishnupur | 276.3837 | 57.9122 | 20.95% |  |  |  | 180.1247 | 96.2589 | 276.3837 |  | 42.346 | 15.5662 | 57.9122
7 | Ukhrul | 250.7441 | 54.0258 | 21.55% |  |  |  | 183.6659 | 67.0782 | 250.7441 |  | 43.1785 | 10.8473 | 54.0258
8 | Kamjong | 149.5816 | 32.5245 | 21.74% |  |  |  | 113.5909 | 35.9907 | 149.5816 |  | 26.7044 | 5.8201 | 32.5245
9 | Senapati | 321.3981 | 71.7829 | 22.33% |  |  |  | 269.9487 | 51.4493 | 321.3981 |  | 63.463 | 8.3199 | 71.7829
10 | Kangpokpi | 380.2364 | 83.3966 | 21.93% |  |  |  | 298.5508 | 81.6856 | 380.2364 |  | 70.1871 | 13.2095 | 83.3966
11 | Tamenglong | 188.2851 | 40.9788 | 21.76% |  |  |  | 143.5096 | 44.7756 | 188.2851 |  | 33.738 | 7.2407 | 40.9788
12 | Noney | 95.1584 | 20.7269 | 21.78% |  |  |  | 72.7536 | 22.4048 | 95.1584 |  | 17.1038 | 3.6231 | 20.7269
13 | Churachandpur | 387.3074 | 84.2719 | 21.76% |  |  |  | 294.8961 | 92.4113 | 387.3074 |  | 69.3279 | 14.944 | 84.2719
14 | Pherzwal | 142.4311 | 29.854 | 20.96% |  |  |  | 92.9566 | 49.4744 | 142.4311 |  | 21.8534 | 8.0006 | 29.854
15 | Chandel | 144.2812 | 32.0705 | 22.23% |  |  |  | 119.0844 | 25.1969 | 144.2812 |  | 27.9959 | 4.0746 | 32.0705
16 | Tengnoupal | 91.0837 | 19.6616 | 21.59% |  |  |  | 67.2148 | 23.8689 | 91.0837 |  | 15.8017 | 3.8599 | 19.6616
| TOTAL | 3917.19 | 836.002 | 21.34% |  |  |  | 2760.21 | 1156.98 | 3917.19 |  | 648.905 | 187.097 | 836.002
3.3) District-wise unspent balance as on 31.03.2019 (Source data: Table AT-6 & 6A of AWP&B 2019-20)
(in MTs)
S.No. | Name of District | Allocation for 2018-19 | Unspent Balance as on 31.03.2019 | % of UB on allocation 2018-19
1 | 2 | 3 | 4 | 5 |  |  |  | Unspent Balance (Closing Balance)
1 | Imphal West | 395.9557 | 38.9501 | 9.837% |  |  |  | 24.3024 | 14.6477 | 38.9501
2 | Imphal East | 412.2884 | 40.5864 | 9.844% |  |  |  | 25.6381 | 14.9483 | 40.5864
3 | Jiribam | 168.1048 | 16.6639 | 9.913% |  |  |  | 11.7507 | 4.9132 | 16.6639
4 | Thoubal | 366.0259 | 36.0902 | 9.86% |  |  |  | 23.4135 | 12.6768 | 36.0902
5 | Kakching | 147.9244 | 14.5546 | 9.839% |  |  |  | 9.1163 | 5.4383 | 14.5546
6 | Bishnupur | 276.3837 | 27.3128 | 9.882% |  |  |  | 18.3692 | 8.9437 | 27.3128
7 | Ukhrul | 250.7441 | 24.9627 | 9.955% |  |  |  | 18.7303 | 6.2324 | 24.9627
8 | Kamjong | 149.5816 | 14.928 | 9.98% |  |  |  | 11.584 | 3.344 | 14.928
9 | Senapati | 321.3981 | 32.3097 | 10.05% |  |  |  | 27.5294 | 4.7803 | 32.3097
10 | Kangpokpi | 380.2364 | 38.0359 | 10% |  |  |  | 30.4463 | 7.5896 | 38.0359
11 | Tamenglong | 188.2851 | 18.7961 | 9.983% |  |  |  | 14.6351 | 4.161 | 18.7961
12 | Noney | 95.1584 | 9.5011 | 9.985% |  |  |  | 7.4194 | 2.0817 | 9.5011
13 | Churachandpur | 387.3074 | 38.6598 | 9.982% |  |  |  | 30.0736 | 8.5862 | 38.6598
14 | Pherzwal | 142.4311 | 14.0765 | 9.883% |  |  |  | 9.4797 | 4.5968 | 14.0765
15 | Chandel | 144.2812 | 14.4854 | 10.04% |  |  |  | 12.1443 | 2.3411 | 14.4854
16 | Tengnoupal | 91.0837 | 9.0723 | 9.96% |  |  |  | 6.8546 | 2.2177 | 9.0723
| TOTAL | 3917.19 | 388.9858 | 9.93% |  |  |  | 281.487 | 107.4988 | 388.9858
3.4) Foodgrains Allocation & Lifting
(in MTs)
Allocation | Unspent balance as on 31.3.18 | Lifting upto 31.03.19 | Total Availibility | % Availibility | Bench mark (75%)
3917.19 | 836.002 | 3081.2 | 3917.202 | 100% | 3917.19
Source: Table AT-6 & 6A of AWP&B 2019-20
3.5) District-wise Foodgrains availability as on 31.03.19 (Source data: Table AT-6 & 6A of AWP&B 2019-20)
(in MTs)
Sl. No. | District | Allocated | OB as on 1.4.2018 | Lifted from FCI | Total Availibility | % Availibility
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | Lifted from FCI
1 | Imphal West | 395.9557 | 81.5177 | 314.4399 | 395.9576 | 100% |  | 182.2807 | 132.1592 | 314.4399 |  | 56.0237 | 25.494 | 81.5177
2 | Imphal East | 412.2884 | 85.12 | 327.1703 | 412.2903 | 100% |  | 192.2994 | 134.8709 | 327.1703 |  | 59.1029 | 26.017 | 85.12
3 | Jiribam | 168.1048 | 35.6398 | 132.4655 | 168.1053 | 100% |  | 88.1365 | 44.329 | 132.4655 |  | 27.0886 | 8.5512 | 35.6398
4 | Thoubal | 366.0259 | 76.038 | 289.9894 | 366.0274 | 100% |  | 175.6132 | 114.3762 | 289.9894 |  | 53.9745 | 22.0636 | 76.038
5 | Kakching | 147.9244 | 30.4808 | 117.4443 | 147.9251 | 100% |  | 68.377 | 49.0673 | 117.4443 |  | 21.0156 | 9.4653 | 30.4808
6 | Bishnupur | 276.3837 | 57.9122 | 218.4726 | 276.3848 | 100% |  | 137.7784 | 80.6942 | 218.4726 |  | 42.346 | 15.5662 | 57.9122
7 | Ukhrul | 250.7441 | 54.0258 | 196.719 | 250.7448 | 100% |  | 140.4871 | 56.2319 | 196.719 |  | 43.1785 | 10.8473 | 54.0258
8 | Kamjong | 149.5816 | 32.5245 | 117.0575 | 149.582 | 100% |  | 86.8863 | 30.1711 | 117.0575 |  | 26.7044 | 5.8201 | 32.5245
9 | Senapati | 321.3981 | 71.7829 | 249.6154 | 321.3983 | 100% |  | 206.4853 | 43.1301 | 249.6154 |  | 63.463 | 8.3199 | 71.7829
10 | Kangpokpi | 380.2364 | 83.3966 | 296.8405 | 380.237 | 100% |  | 228.3632 | 68.4773 | 296.8405 |  | 70.1871 | 13.2095 | 83.3966
11 | Tamenglong | 188.2851 | 40.9788 | 147.3068 | 188.2855 | 100% |  | 109.7713 | 37.5355 | 147.3068 |  | 33.738 | 7.2407 | 40.9788
12 | Noney | 95.1584 | 20.7269 | 74.4316 | 95.1586 | 100% |  | 55.6496 | 18.782 | 74.4316 |  | 17.1038 | 3.6231 | 20.7269
13 | Churachandpur | 387.3074 | 84.2719 | 303.0363 | 387.3082 | 100% |  | 225.5676 | 77.4687 | 303.0363 |  | 69.3279 | 14.944 | 84.2719
14 | Pherzwal | 142.4311 | 29.854 | 112.5776 | 142.4316 | 100% |  | 71.103 | 41.4746 | 112.5776 |  | 21.8534 | 8.0006 | 29.854
15 | Chandel | 144.2812 | 32.0705 | 112.2109 | 144.2814 | 100% |  | 91.0883 | 21.1226 | 112.2109 |  | 27.9959 | 4.0746 | 32.0705
16 | Tengnoupal | 91.0837 | 19.6616 | 71.4224 | 91.084 | 100% |  | 51.413 | 20.0094 | 71.4224 |  | 15.8017 | 3.8599 | 19.6616
| TOTAL | 3917.19 | 836.002 | 3081.2 | 3917.202 | 100% |  | 2111.3 | 969.9 | 3081.2 |  | 648.905 | 187.097 | 836.002
3.6) Foodgrains Allocation, Lifting (availibility) & Utilisation
Allocation | T. Availibility | % T. Availibility | Utilisation | % Utilisation
3917.19 | 3917.202 | 100% | 3528.217 | 90.07%
3.7) District-wise Utilisation of foodgrains (Source data: Table AT-6 & 6A of AWP&B 2019-20)
Sl. No. | District | Allocated | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5 |  |  |  | Utilization
1 | Imphal West | 395.9557 | 357.0075 | 90.16% |  |  |  | 214.0021 | 143.0054 | 357.0075
2 | Imphal East | 412.2884 | 371.7039 | 90.16% |  |  |  | 225.7642 | 145.9396 | 371.7039
3 | Jiribam | 168.1048 | 151.4415 | 90.09% |  |  |  | 103.4744 | 47.967 | 151.4415
4 | Thoubal | 366.0259 | 329.9372 | 90.14% |  |  |  | 206.1742 | 123.763 | 329.9372
5 | Kakching | 147.9244 | 133.3705 | 90.16% |  |  |  | 80.2763 | 53.0942 | 133.3705
6 | Bishnupur | 276.3837 | 249.0719 | 90.12% |  |  |  | 161.7552 | 87.3167 | 249.0719
7 | Ukhrul | 250.7441 | 225.7821 | 90.04% |  |  |  | 164.9353 | 60.8468 | 225.7821
8 | Kamjong | 149.5816 | 134.6539 | 90.02% |  |  |  | 102.0067 | 32.6472 | 134.6539
9 | Senapati | 321.3981 | 289.0886 | 89.95% |  |  |  | 242.4188 | 46.6698 | 289.0886
10 | Kangpokpi | 380.2364 | 342.2011 | 90% |  |  |  | 268.1039 | 74.0972 | 342.2011
11 | Tamenglong | 188.2851 | 169.4902 | 90.02% |  |  |  | 128.8742 | 40.616 | 169.4902
12 | Noney | 95.1584 | 85.6575 | 90.02% |  |  |  | 65.334 | 20.3234 | 85.6575
13 | Churachandpur | 387.3074 | 348.6484 | 90.02% |  |  |  | 264.822 | 83.8265 | 348.6484
14 | Pherzwal | 142.4311 | 128.3551 | 90.12% |  |  |  | 83.4767 | 44.8784 | 128.3551
15 | Chandel | 144.2812 | 129.796 | 89.96% |  |  |  | 106.9399 | 22.8562 | 129.796
16 | Tengnoupal | 91.0837 | 82.0117 | 90.04% |  |  |  | 60.3601 | 21.6516 | 82.0117
| TOTAL | 3917.19 | 3528.217 | 90.07% |  |  |  | 2478.718 | 1049.499 | 3528.217
3.8) Cost of food grain- Allocation & Utilisation
Allocation | Bills submited by FCI | Payment made to FCI | % payment
117.53 | 92.44 | 92.44 | 100%
3.9) Payment of cost of foodgrain to FCI
(Rs. In Lakh)
Sl. No. | District | Allocation | Bills raised by FCI | Payment to FCI by State | Pending Bills | Bill paid
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Imphal West | 11.8801 | 9.344 | 9.344 | 0 | 100%
2 | Imphal East | 12.3702 | 9.7294 | 9.7294 | 0 | 100%
3 | Jiribam | 5.0438 | 3.967 | 3.967 | 0 | 100%
4 | Thoubal | 10.9821 | 8.6377 | 8.6377 | 0 | 100%
5 | Kakching | 4.4383 | 3.4908 | 3.4908 | 0 | 100%
6 | Bishnupur | 8.2925 | 6.5223 | 6.5223 | 0 | 100%
7 | Ukhrul | 7.5232 | 5.9172 | 5.9172 | 0 | 100%
8 | Kamjong | 4.488 | 3.5299 | 3.5299 | 0 | 100%
9 | Senapati | 9.6431 | 7.5845 | 7.5845 | 0 | 100%
10 | Kangpokpi | 11.4085 | 8.973 | 8.973 | 0 | 100%
11 | Tamenglong | 5.6492 | 4.4433 | 4.4433 | 0 | 100%
12 | Noney | 2.8551 | 2.2456 | 2.2456 | 0 | 100%
13 | Churachandpur | 11.6206 | 9.1399 | 9.1399 | 0 | 100%
14 | Pherzwal | 4.2735 | 3.3612 | 3.3612 | 0 | 100%
15 | Chandel | 4.329 | 3.4048 | 3.4048 | 0 | 100%
16 | Tengnoupal | 2.7328 | 2.1494 | 2.1494 | 0 | 100%
| TOTAL | 117.53 | 92.44 | 92.44 | 0 | 100%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 1.4.2018 (Source data: Table AT-7 & 7A of AWP&B 2019-20)
(Rs. In lakhs)
S.No. | Name of District | Allocation for 2018-19 | Opening Balance as on 1.4.2018 | % of OB on allocation 2018-19 |  |  |  | Allocation
1 | 2 | 3 | 4 | 5 |  |  |  | Pry | U Pry | Total |  | OB PRY | OB U PRY
1 | Imphal West | 175.182 | 41.5922 | 23.74% |  |  |  | 107.0762 | 68.1058 | 175.182 |  | 24.8103 | 16.7819 | 41.5922
2 | Imphal East | 182.4647 | 43.3002 | 23.73% |  |  |  | 112.9614 | 69.5032 | 182.4647 |  | 26.174 | 17.1262 | 43.3002
3 | Jiribam | 74.6177 | 17.6253 | 23.62% |  |  |  | 51.7736 | 22.8441 | 74.6177 |  | 11.9963 | 5.629 | 17.6253
4 | Thoubal | 162.1012 | 38.4265 | 23.71% |  |  |  | 103.1596 | 58.9417 | 162.1012 |  | 23.9028 | 14.5237 | 38.4265
5 | Kakching | 65.4523 | 15.5375 | 23.74% |  |  |  | 40.1663 | 25.2859 | 65.4523 |  | 9.3068 | 6.2307 | 15.5375
6 | Bishnupur | 122.5187 | 28.9998 | 23.67% |  |  |  | 80.9345 | 41.5842 | 122.5187 |  | 18.7531 | 10.2467 | 28.9998
7 | Ukhrul | 111.5037 | 26.2622 | 23.55% |  |  |  | 82.5256 | 28.9781 | 111.5037 |  | 19.1218 | 7.1404 | 26.2622
8 | Kamjong | 66.5873 | 15.6573 | 23.51% |  |  |  | 51.0392 | 15.5481 | 66.5873 |  | 11.8261 | 3.8312 | 15.6573
9 | Senapati | 143.5209 | 33.5816 | 23.4% |  |  |  | 121.2946 | 22.2263 | 143.5209 |  | 28.1048 | 5.4768 | 33.5816
10 | Kangpokpi | 169.4347 | 39.778 | 23.48% |  |  |  | 134.1462 | 35.2885 | 169.4347 |  | 31.0826 | 8.6954 | 39.778
11 | Tamenglong | 83.8256 | 19.7074 | 23.51% |  |  |  | 64.4824 | 19.3432 | 83.8256 |  | 14.941 | 4.7663 | 19.7074
12 | Noney | 42.3689 | 9.9595 | 23.51% |  |  |  | 32.69 | 9.679 | 42.3689 |  | 7.5745 | 2.385 | 9.9595
13 | Churachandpur | 172.4261 | 40.5393 | 23.51% |  |  |  | 132.504 | 39.9221 | 172.4261 |  | 30.7021 | 9.8371 | 40.5393
14 | Pherzwal | 63.1408 | 14.9444 | 23.67% |  |  |  | 41.7677 | 21.3732 | 63.1408 |  | 9.6779 | 5.2665 | 14.9444
15 | Chandel | 64.3927 | 15.0803 | 23.42% |  |  |  | 53.5075 | 10.8852 | 64.3927 |  | 12.3981 | 2.6822 | 15.0803
16 | Tengnoupal | 40.5127 | 9.5387 | 23.54% |  |  |  | 30.2013 | 10.3115 | 40.5127 |  | 6.9978 | 2.5408 | 9.5387
| TOTAL | 1740.05 | 410.53 | 23.59% |  |  |  | 1240.23 | 499.82 | 1740.05 |  | 287.37 | 123.16 | 410.53
4.1.2) District-wise unspent balance as on 31.03.2019 Source data: Table AT-7 & 7A of AWP&B 2019-20)
(Rs. In lakhs)
S.No. | Name of District | Allocation for 2018-19 | Unspent Balance as on 31.03.2019 | % of UB on allocation 2018-19 |  |  |  | Unspent Balance
1 | 2 | 3 | 4 | 5 |  |  |  | PRY | U PRY | Total
1 | Imphal West | 175.182 | 27.071 | 15.45% |  |  |  | 16.2777 | 10.7932 | 27.071
2 | Imphal East | 182.4647 | 28.1871 | 15.45% |  |  |  | 17.1724 | 11.0147 | 28.1871
3 | Jiribam | 74.6177 | 11.4909 | 15.4% |  |  |  | 7.8706 | 3.6203 | 11.4909
4 | Thoubal | 162.1012 | 25.0232 | 15.44% |  |  |  | 15.6823 | 9.3409 | 25.0232
5 | Kakching | 65.4523 | 10.1133 | 15.45% |  |  |  | 6.1061 | 4.0072 | 10.1133
6 | Bishnupur | 122.5187 | 18.8938 | 15.42% |  |  |  | 12.3037 | 6.5901 | 18.8938
7 | Ukhrul | 111.5037 | 17.1379 | 15.37% |  |  |  | 12.5456 | 4.5924 | 17.1379
8 | Kamjong | 66.5873 | 10.223 | 15.35% |  |  |  | 7.759 | 2.464 | 10.223 | [7 empty] | #REF!
9 | Senapati | 143.5209 | 21.9616 | 15.3% |  |  |  | 18.4392 | 3.5224 | 21.9616 | [7 empty] | #REF!
10 | Kangpokpi | 169.4347 | 25.9853 | 15.34% |  |  |  | 20.3929 | 5.5924 | 25.9853 | [7 empty] | #REF!
11 | Tamenglong | 83.8256 | 12.8681 | 15.35% |  |  |  | 9.8026 | 3.0655 | 12.8681 | [7 empty] | #REF!
12 | Noney | 42.3689 | 6.5034 | 15.35% |  |  |  | 4.9695 | 1.5339 | 6.5034 | [7 empty] | #REF!
13 | Churachandpur | 172.4261 | 26.47 | 15.35% |  |  |  | 20.1433 | 6.3267 | 26.47 | [7 empty] | #REF!
14 | Pherzwal | 63.1408 | 9.7367 | 15.42% |  |  |  | 6.3495 | 3.3872 | 9.7367 | [7 empty] | #REF!
15 | Chandel | 64.3927 | 9.8593 | 15.31% |  |  |  | 8.1342 | 1.725 | 9.8593 | [7 empty] | #REF!
16 | Tengnoupal | 40.5127 | 6.2253 | 15.37% |  |  |  | 4.5912 | 1.6341 | 6.2253 | [7 empty] | #REF!
| TOTAL | 1740.05 | 267.75 | 15.39% |  |  |  | 188.54 | 79.21 | 267.75 | [7 empty] | #REF!
4.2) Cooking cost allocation and disbursed to Dists
Allocation | Availibility | Bench mark
100% | 110.4% | 85%
47718.17 | 52695.2695 | 40560.4445
Allocation | OB as on 1.4.18 | Disbursed to Dist | Total Availibility | % Availibility | Bench mark (100%)
1740.05 | 410.53 | 1389.91 | 1800.44 | 103.5% | 1740.05
4.3) District-wise Cooking Cost availability (Source data: Table AT-7 & 7A of AWP&B 2019-20)
(Rs. In lakhs)
S.No. | Name of District | Allocation for 2018-19 | Opening Balance as on 1.4.2018 | Cooking assistance received | Total Availibility of cooking cost | % Availibility of cooking cost |  | Cooking Assisstance (Cooking Cost Received)
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | Pry | U Pry | Total
1 | Imphal West | 175.182 | 41.5922 | 140.5256 | 182.1177 | 104% |  | 84.502 | 56.0236 | 140.5256
2 | Imphal East | 182.4647 | 43.3002 | 146.3196 | 189.6197 | 103.9% |  | 89.1465 | 57.1731 | 146.3196
3 | Jiribam | 74.6177 | 17.6253 | 59.65 | 77.2752 | 103.6% |  | 40.8585 | 18.7915 | 59.65
4 | Thoubal | 162.1012 | 38.4265 | 129.8963 | 168.3228 | 103.8% |  | 81.4111 | 48.4852 | 129.8963
5 | Kakching | 65.4523 | 15.5375 | 52.4984 | 68.0359 | 103.9% |  | 31.6983 | 20.8001 | 52.4984
6 | Bishnupur | 122.5187 | 28.9998 | 98.0786 | 127.0784 | 103.7% |  | 63.8715 | 34.207 | 98.0786
7 | Ukhrul | 111.5037 | 26.2622 | 88.9645 | 115.2267 | 103.3% |  | 65.1272 | 23.8372 | 88.9645
8 | Kamjong | 66.5873 | 15.6573 | 53.0687 | 68.7261 | 103.2% |  | 40.2789 | 12.7898 | 53.0687
9 | Senapati | 143.5209 | 33.5816 | 114.0061 | 147.5876 | 102.8% |  | 95.7228 | 18.2833 | 114.0061
10 | Kangpokpi | 169.4347 | 39.778 | 134.8932 | 174.6712 | 103.1% |  | 105.865 | 29.0282 | 134.8932
11 | Tamenglong | 83.8256 | 19.7074 | 66.7996 | 86.507 | 103.2% |  | 50.888 | 15.9117 | 66.7996
12 | Noney | 42.3689 | 9.9595 | 33.76 | 43.7195 | 103.2% |  | 25.7981 | 7.9619 | 33.76
13 | Churachandpur | 172.4261 | 40.5393 | 137.4088 | 177.948 | 103.2% |  | 104.569 | 32.8397 | 137.4088
14 | Pherzwal | 63.1408 | 14.9444 | 50.5435 | 65.4879 | 103.7% |  | 32.9621 | 17.5815 | 50.5435
15 | Chandel | 64.3927 | 15.0803 | 51.1809 | 66.2612 | 102.9% |  | 42.2269 | 8.9541 | 51.1809
16 | Tengnoupal | 40.5127 | 9.5387 | 32.3163 | 41.855 | 103.3% |  | 23.8341 | 8.4822 | 32.3163
| TOTAL | 1740.05 | 410.53 | 1389.91 | 1800.44 | 103.5% |  | 978.76 | 411.15 | 1389.91
4.4) Cooking Cost Utilisation
District-wise Utilisation of Cooking cost (Source data: Table AT-7 & 7A of AWP&B 2019-20)
Allocation | Disbursed | % Disbursed | Utilisation | % Utilisation
1740.05 | 1389.91 | 79.88% | 1532.69 | 88.08%
(Rs. In lakhs)
S.No. | Name of District | Allocation for 2018-19 | Utilisation of Cooking assistance | % Utilisation |  |  |  | Utilization
1 | 2 | 3 | 4 | 5 |  |  |  | Pry | U Pry | Total
1 | Imphal West | 175.182 | 155.0468 | 88.51% |  |  |  | 93.0346 | 62.0122 | 155.0468
2 | Imphal East | 182.4647 | 161.4326 | 88.47% |  |  |  | 98.148 | 63.2846 | 161.4326
3 | Jiribam | 74.6177 | 65.7844 | 88.16% |  |  |  | 44.9841 | 20.8002 | 65.7844
4 | Thoubal | 162.1012 | 143.2995 | 88.4% |  |  |  | 89.6315 | 53.668 | 143.2995
5 | Kakching | 65.4523 | 57.9226 | 88.5% |  |  |  | 34.899 | 23.0235 | 57.9226
6 | Bishnupur | 122.5187 | 108.1846 | 88.3% |  |  |  | 70.321 | 37.8636 | 108.1846
7 | Ukhrul | 111.5037 | 98.0888 | 87.97% |  |  |  | 71.7034 | 26.3853 | 98.0888
8 | Kamjong | 66.5873 | 58.5031 | 87.86% |  |  |  | 44.3461 | 14.157 | 58.5031
9 | Senapati | 143.5209 | 125.6261 | 87.53% |  |  |  | 105.3884 | 20.2377 | 125.6261
10 | Kangpokpi | 169.4347 | 148.6858 | 87.75% |  |  |  | 116.5547 | 32.1312 | 148.6858
11 | Tamenglong | 83.8256 | 73.6389 | 87.85% |  |  |  | 56.0263 | 17.6125 | 73.6389
12 | Noney | 42.3689 | 37.2161 | 87.84% |  |  |  | 28.4031 | 8.813 | 37.2161
13 | Churachandpur | 172.4261 | 151.478 | 87.85% |  |  |  | 115.1279 | 36.3501 | 151.478
14 | Pherzwal | 63.1408 | 55.7513 | 88.3% |  |  |  | 36.2904 | 19.4609 | 55.7513
15 | Chandel | 64.3927 | 56.4019 | 87.59% |  |  |  | 46.4907 | 9.9112 | 56.4019
16 | Tengnoupal | 40.5127 | 35.6296 | 87.95% |  |  |  | 26.2407 | 9.3889 | 35.6296
| Total | 1740.05 | 1532.69 | 88.08% |  |  |  | 1077.59 | 455.1 | 1532.69
5. Reconciliation of Utilisation and Performance during 2018-19 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost (Source data: para 3.7 and 4.4 above)
S. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | Imphal West | 90.16% | 88.51% | -1.6574
2 | Imphal East | 90.16% | 88.47% | -1.6829
3 | Jiribam | 90.09% | 88.16% | -1.9257
4 | Thoubal | 90.14% | 88.4% | -1.7391
5 | Kakching | 90.16% | 88.5% | -1.6653
6 | Bishnupur | 90.12% | 88.3% | -1.8177
7 | Ukhrul | 90.04% | 87.97% | -2.0757
8 | Kamjong | 90.02% | 87.86% | -2.1612
9 | Senapati | 89.95% | 87.53% | -2.4157
10 | Kangpokpi | 90% | 87.75% | -2.2429
11 | Tamenglong | 90.02% | 87.85% | -2.1701
12 | Noney | 90.02% | 87.84% | -2.1776
13 | Churachandpur | 90.02% | 87.85% | -2.1676
14 | Pherzwal | 90.12% | 88.3% | -1.8207
15 | Chandel | 89.96% | 87.59% | -2.3698
16 | Tengnoupal | 90.04% | 87.95% | -2.0931
| TOTAL | 90.07% | 88.08% | -1.987
5.2 Reconciliation of Food grains utilisation during 2018-19 (Source data: para 2.7 and 3.7 above)
Expected
S. No. | District | No. of Meals served during 01.4.18 to 31.03.19 | Expected consumption of food grains | Actual consumption of food grains | % consumption |  |  | Pry |  | U Pry |  | Meal | FG
1 | 2 | 3 | 4 | 5 | 6 |  |  | Meal | FG Expect | Meal | FG Expect | Pry+U.Pry | Pry+U.Pry
1 | Imphal West | 3433829 | 395.9221 | 357.0075 | 90.17% |  |  | 2383046 | 238.3046 | 1050783 | 157.6174 | 3433829 | 395.9221
2 | Imphal East | 3585465 | 412.1185 | 371.7039 | 90.19% |  |  | 2514025 | 251.4025 | 1071440 | 160.716 | 3585465 | 412.1185
3 | Jiribam | 1505010 | 168.1389 | 151.4415 | 90.07% |  |  | 1152252 | 115.2252 | 352758 | 52.9137 | 1505010 | 168.1389
4 | Thoubal | 3205467 | 366.0262 | 329.9372 | 90.14% |  |  | 2295878 | 229.5878 | 909589 | 136.4383 | 3205467 | 366.0262
5 | Kakching | 1283458 | 147.8224 | 133.3705 | 90.22% |  |  | 893926 | 89.3926 | 389532 | 58.4298 | 1283458 | 147.8224
6 | Bishnupur | 2442974 | 276.3838 | 249.0719 | 90.12% |  |  | 1801245 | 180.1245 | 641729 | 96.2593 | 2442974 | 276.3838
7 | Ukhrul | 2284528 | 250.8464 | 225.7821 | 90.01% |  |  | 1836657 | 183.6657 | 447871 | 67.1806 | 2284528 | 250.8464
8 | Kamjong | 1376074 | 149.6157 | 134.6539 | 90% |  |  | 1135908 | 113.5908 | 240166 | 36.0249 | 1376074 | 149.6157
9 | Senapati | 3042481 | 321.3979 | 289.0886 | 89.95% |  |  | 2699484 | 269.9484 | 342997 | 51.4495 | 3042481 | 321.3979
10 | Kangpokpi | 3530077 | 380.2364 | 342.2011 | 90% |  |  | 2985504 | 298.5504 | 544573 | 81.6859 | 3530077 | 380.2364
11 | Tamenglong | 1734053 | 188.3533 | 169.4902 | 89.99% |  |  | 1435094 | 143.5094 | 298959 | 44.8438 | 1734053 | 188.3533
12 | Noney | 877128 | 95.1925 | 85.6575 | 89.98% |  |  | 727535 | 72.7535 | 149593 | 22.4389 | 877128 | 95.1925
13 | Churachandpur | 3565035 | 387.3074 | 348.6484 | 90.02% |  |  | 2948957 | 294.8957 | 616078 | 92.4117 | 3565035 | 387.3074
14 | Pherzwal | 1259850 | 142.4993 | 128.3551 | 90.07% |  |  | 929565 | 92.9565 | 330285 | 49.5427 | 1259850 | 142.4993
15 | Chandel | 1359049 | 144.3152 | 129.796 | 89.94% |  |  | 1190842 | 119.0842 | 168207 | 25.231 | 1359049 | 144.3152
16 | Tengnoupal | 830820 | 91.0157 | 82.0117 | 90.11% |  |  | 672147 | 67.2147 | 158673 | 23.8009 | 830820 | 91.0157
| TOTAL | 35315298 | 3917.1915 | 3528.217 | 90.07% |  |  | 27602065 | 1472.5036 | 7713233 | 427.4296 | 35315298 | 3917.1915
5.3 Reconciliation of Cooking Cost utilisation during 2017-18 (Source data: para 2.5 and 4.5 above)
|  |  |  | (Rs. in Lakhs) | [8 empty] | Expected Utilisation of Cooking Cost Upr Pry | Expected Utilisation of Cooking Cost (In Lakhs)
S. No. | District | No. of Meals served during 01.4.18 to 31.03.19 | Expected expenditure of cooking cost | Actual expenditure of cooking cost | % consumption |  |  | Name of District | Pry / Average No. of children availed MDM [Col. 8/Col. 9] | Expected Utilisation of Cooking Cost / Pry | Average No. of children availed Upr Pry MDM [Col. 8/Col. 9] | Expected Utilisation of Cooking Cost / U. Pry | Pry. + U.Pry. | /100000
1 | 2 | 3 | 4 | 5 | 6 |  |  | Imphal West | 9927 | 9802416.15 | 4580 | 6768186.6 | 16570602.75 | 165.706
1 | Imphal West | 3433829 | 165.706 | 155.0468 | 93.57% |  |  |  | 10473 | 10341563.85 | 4581 | 6769664.37 | 17111228.22 | 171.1123
2 | Imphal East | 3585465 | 171.1123 | 161.4326 | 94.34% |  |  |  | 4800 | 4739760 | 1508 | 2228477.16 | 6968237.16 | 69.6824
3 | Jiribam | 1505010 | 69.6824 | 65.7844 | 94.41% |  |  |  | 9564 | 9443971.8 | 3855 | 5696803.35 | 15140775.15 | 151.4078
4 | Thoubal | 3205467 | 151.4078 | 143.2995 | 94.64% |  |  |  | 3724 | 3677263.8 | 1634 | 2414676.18 | 6091939.98 | 60.9194
5 | Kakching | 1283458 | 60.9194 | 57.9226 | 95.08% |  |  |  | 7504 | 7409824.8 | 2668 | 3942690.36 | 11352515.16 | 113.5252
6 | Bishnupur | 2442974 | 113.5252 | 108.1846 | 95.3% |  |  |  | 7651 | 7554979.95 | 1971 | 2912684.67 | 10467664.62 | 104.6766
7 | Ukhrul | 2284528 | 104.6766 | 98.0888 | 93.71% |  |  |  | 4732 | 4672613.4 | 1057 | 1562002.89 | 6234616.29 | 62.3462
8 | Kamjong | 1376074 | 62.3462 | 58.5031 | 93.84% |  |  | Imphal East | 11245 | 11103875.25 | 1391 | 2055578.07 | 13159453.32 | 131.5945
9 | Senapati | 3042481 | 131.5945 | 125.6261 | 95.46% |  |  | Thoubal | 12437 | 12280915.65 | 2208 | 3262916.16 | 15543831.81 | 155.4383
10 | Kangpokpi | 3530077 | 155.4383 | 148.6858 | 95.66% |  |  | Bishnupur | 5978 | 5902976.1 | 1260 | 1861990.2 | 7764966.3 | 77.6497
11 | Tamenglong | 1734053 | 77.6497 | 73.6389 | 94.83% |  |  | Ukhrul | 3031 | 2992960.95 | 631 | 932472.87 | 3925433.82 | 39.2543
12 | Noney | 877128 | 39.2543 | 37.2161 | 94.81% |  |  | Senapati | 12285 | 12130823.25 | 2585 | 3820035.45 | 15950858.7 | 159.5086
13 | Churachandpur | 3565035 | 159.5086 | 151.478 | 94.97% |  |  | Tamenglong | 3872 | 3823406.4 | 1386 | 2048189.22 | 5871595.62 | 58.716
14 | Pherzwal | 1259850 | 58.716 | 55.7513 | 94.95% |  |  | Ccpur | 4961 | 4898739.45 | 709 | 1047738.93 | 5946478.38 | 59.4648
15 | Chandel | 1359049 | 59.4648 | 56.4019 | 94.85% |  |  | Chandel | 2800 | 2764860 | 669 | 988628.13 | 3753488.13 | 37.5349
16 | Tengnoupal | 830820 | 37.5349 | 35.6296 | 94.92% |  |  |  | 114984 | 113540950.8 | 32693 | 48312734.61 | 161853685.41 | 1618.5369
| TOTAL | 35315298 | 1618.5369 | 1532.69 | 94.7%
6. ANALYSIS of HONORIUM To COOK-CUM-HELPERS
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
S.No. | Name of District | Allocation for 2018-19 | Opening Balance as on 1.4.2018 | Amount received | Total availability | % Availibilty |  |  | Allocation |  |  |  | OB |  |  | Releases
1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  | Pry | U Pry | Total |  | Pry | U Pry | Total | Pry | U Pry | Total
1 | Imphal West | 84.8 | 28.9885 | 74.4999 | 103.4884 | 122%
2 | Imphal East | 69.3 | 23.6899 | 60.8826 | 84.5725 | 122%
3 | Jiribam | 33 | 11.2809 | 28.9917 | 40.2726 | 122%
4 | Thoubal | 42 | 14.3575 | 36.8985 | 51.256 | 122%
5 | Kakching | 32 | 10.9391 | 28.1132 | 39.0522 | 122%
6 | Bishnupur | 59.3 | 20.2715 | 52.0972 | 72.3687 | 122%
7 | Ukhrul | 51.3 | 17.5367 | 45.0689 | 62.6056 | 122%
8 | Kamjong | 35 | 11.9646 | 30.7488 | 42.7134 | 122% |  |  | 84.8 |  | 84.8 |  | #REF! |  | #REF! | #REF! |  | #REF!
9 | Senapati | 64.6 | 22.0832 | 56.7534 | 78.8367 | 122% |  |  | 102.3 |  | 102.3 |  | #REF! |  | #REF! | #REF! |  | #REF!
10 | Kangpokpi | 75 | 25.6384 | 65.8902 | 91.5286 | 122% |  |  | 74 |  | 74 |  | #REF! |  | #REF! | #REF! |  | #REF!
11 | Tamenglong | 37.5 | 12.8192 | 32.9451 | 45.7643 | 122% |  |  | 59.3 |  | 59.3 |  | #REF! |  | #REF! | #REF! |  | #REF!
12 | Noney | 23 | 7.8625 | 20.2063 | 28.0688 | 122% |  |  | 86.3 |  | 86.3 |  | #REF! |  | #REF! | #REF! |  | #REF!
13 | Churachandpur | 66.2 | 22.6302 | 58.1591 | 80.7893 | 122% |  |  | 139.6 |  | 139.6 |  | #REF! |  | #REF! | #REF! |  | #REF!
14 | Pherzwal | 35 | 11.9646 | 30.7488 | 42.7134 | 122% |  |  | 60.5 |  | 60.5 |  | #REF! |  | #REF! | #REF! |  | #REF!
15 | Chandel | 25.7 | 8.7854 | 22.5784 | 31.3638 | 122% |  |  | 101.2 |  | 101.2 |  | #REF! |  | #REF! | #REF! |  | #REF!
16 | Tengnoupal | 15 | 5.1277 | 13.178 | 18.3057 | 122% |  |  | 40.7 |  | 40.7 |  | #REF! |  | #REF! | #REF! |  | #REF!
| Total | 748.7 | 255.94 | 657.76 | 913.7 | 122% |  |  | 748.7 |  | 748.7 |  | #REF! |  | #REF! | #REF! |  | #REF!
6.2) District-wise Utilisation of grant for Honorarium, cooks-cum-Helpers | [8 empty] | 192
Refer table AT_8 and AT-8A,AWP&B, 2019-20 | [7 empty] | 109.31 | 12.1456 | 121.4556 | 109.31 | 12.1456
S.No. | Name of District | Allocation for 2018-19 | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation |  |  |  | 2429.04 | 241.49 | 2670.53
1 | 2 | 3 | 4 | 5 | 6
1 | Imphal West | 84.8 | 103.4884 | 71.1 | 83.84%
2 | Imphal East | 69.3 | 84.5725 | 58.1 | 83.84%
3 | Jiribam | 33 | 40.2726 | 27.7 | 83.94%
4 | Thoubal | 42 | 51.256 | 35.2 | 83.81%
5 | Kakching | 32 | 39.0522 | 26.8 | 83.75%
6 | Bishnupur | 59.3 | 72.3687 | 49.7 | 83.81%
7 | Ukhrul | 51.3 | 62.6056 | 43 | 83.82%
8 | Kamjong | 35 | 42.7134 | 29.3 | 83.71%
9 | Senapati | 64.6 | 78.8367 | 54.2 | 83.9%
10 | Kangpokpi | 75 | 91.5286 | 62.9 | 83.87%
11 | Tamenglong | 37.5 | 45.7643 | 31.4 | 83.73%
12 | Noney | 23 | 28.0688 | 19.3 | 83.91%
13 | Churachandpur | 66.2 | 80.7893 | 55.5 | 83.84%
14 | Pherzwal | 35 | 42.7134 | 29.3 | 83.71%
15 | Chandel | 25.7 | 31.3638 | 21.5 | 83.66%
16 | Tengnoupal | 15 | 18.3057 | 12.7 | 84.67%
| Total | 748.7 | 913.7 | 627.7 | 83.84%
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
Refer table AT_8 and AT-8A,AWP&B, 2019-20
S.No. | Name of District | Allocation for 2018-19 | Total Availability | Unspent balance as on 31.03.2019 | % of UB as on Allocation 2018-19
1 | 2 | 3 | 4 | 5 | 6 |  |  |  | Unspent Balance as on 31.12.2012 |  |  | 588.96
1 | Imphal West | 84.8 | 103.4884 | 32.3884 | 38.19%
2 | Imphal East | 69.3 | 84.5725 | 26.4725 | 38.2%
3 | Jiribam | 33 | 40.2726 | 12.5726 | 38.1%
4 | Thoubal | 42 | 51.256 | 16.056 | 38.23%
5 | Kakching | 32 | 39.0522 | 12.2522 | 38.29%
6 | Bishnupur | 59.3 | 72.3687 | 22.6687 | 38.23%
7 | Ukhrul | 51.3 | 62.6056 | 19.6056 | 38.22%
8 | Kamjong | 35 | 42.7134 | 13.4134 | 38.32% |  |  |  | #REF! | 0 | #REF!
9 | Senapati | 64.6 | 78.8367 | 24.6367 | 38.14% |  |  |  | #REF! |  | #REF!
10 | Kangpokpi | 75 | 91.5286 | 28.6286 | 38.17% |  |  |  | #REF! |  | #REF!
11 | Tamenglong | 37.5 | 45.7643 | 14.3643 | 38.3% |  |  |  | #REF! |  | #REF!
12 | Noney | 23 | 28.0688 | 8.7688 | 38.13% |  |  |  | #REF! |  | #REF!
13 | Churachandpur | 66.2 | 80.7893 | 25.2893 | 38.2% |  |  |  | #REF! |  | #REF!
14 | Pherzwal | 35 | 42.7134 | 13.4134 | 38.32% |  |  |  | #REF! |  | #REF!
15 | Chandel | 25.7 | 31.3638 | 9.8638 | 38.38% |  |  |  | #REF! |  | #REF!
16 | Tengnoupal | 15 | 18.3057 | 5.6057 | 37.37% |  |  |  | #REF! |  | #REF!
| Total | 748.7 | 913.7 | 286 | 38.2% |  |  |  | #REF! | 0 | #REF!
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
7.1) Releasing details
Releases for MME by GoI (2018-19)
Stage | Installment | Dated | Amount (Rs. In lakh)
Pry+U.Pry | Adhoc Released | 01.05.2018 | 10.88
| Balance of First Installment | 12.09.2018 | 13.91
| 2nd Installment | 21.01.2019 | 17.88
Total Release |  |  | 42.67
7.2) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. | Details | As per GOI records | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2018-19 | 42.67 | 42.12 | -0.55 | -1.289%
2 | Opening Balance as on 1.4.2018 | 0 | 0 | 0 | 0%
3 | Released during 2018-19 | 42.67 | 42.7 | 0.03 | 0.07031%
4 | Total Availibility | 42.67 | 42.7 | 0.03 | 0.07031% |  |  |  |  | 25.51
7.3) Utilisation of MME during 2018-19 (Source data: Table AT-10 of AWP&B 2019-20)
|  |  | (Rs. In lakhs) | (As on 31.03.18)
Sl. No. | Activity | Allocated for 2018-19 | Total Availibility | Expenditure | Exp as % of allocation
1 | 2 | 3 | 4 | 5 | 6
1 | School Level Expenses | 21.06 | 21.335 | 21.06 | 100%
2 | Management, Supervision, Training & Internal Monitoring, External Monitoring & Evaluation | 21.06 | 21.335 | 21.06 | 100%
Total |  | 42.12 | 42.67 | 42.12 | 100%
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
8.1) Releasing details
Releases for TA by GoI (2018-19)
Schools | Installment | Dated | Amount (Rs. In lakh)
Pry+U. Pry | Adhoc Released | 01.05.2018 | 24.97
| 1st Installment | 12.09.2018 | 18.84
| 2nd Installment | 21.01.2019 | 29.22
Total Release |  |  | 73.03
8.2) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Details | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2018-19 | 73.03 | 92.84 | 19.81 | 27.13%
2 | Opening Balance as on 1.4.2018 | -15.55 | -15.55 | 0 | 0%
3 | Released during 2018-19 | 73.03 | 73.03 | 0 | 0%
4 | Total Availibility | 57.48 | 57.48 | 0 | 0%
8.3) Utilisation of TA during 2018-19 (Source data: Table AT-9 of AWP&B 2019-20)
(Rs. In lakhs)
Allocated for 2018-19 | Total availibility of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7 | 8= (2-5)
73.03 | 57.48 | 3081.2 | 73.0244 | 73.04 | -0.01556 | 100% | -15.56
9. INFRASTRUCTURE DEVELOPMENT DURING 2017-18 (Primary + Upper primary) Source: Table AT-11 of AWP&B 2019-20
9.1) Kitchen-cum-store
9.1.1) Releasing details
Releases for Kitchen-cum-stores by GoI as on 31.03.2019
Schools | Installment | Units | Amount (in lakh)
Primary + Upper Primary | 2006-07 | 1174 | 704.4
| 2007-08 | 0 | 0
| 2008-09 | 0 | 0
| 2009-10 | 0 | 0
| 2010-11 | 1792 | 2927.37
| 2011-12 | 0 | 0
| 2012-13 | 0 | 0
| 2013-14 | 0 | 0
| 2014-15* | 0 | 0
| 2015-16 | 0 | 0
| 2016-17 | 0 | 0
| 2017-18 | 0 | 0
| 2018-19 | 0 | 0
| Grand Total | 2966 | 3631.77 |  |  |  |  | 2980.12 | 2956
9.1.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation*
2006-07 to 2018-19 | Phy | Fin | Phy | Fin | Phy | Fin
| 2966 | 3631.77 | 2966 | 3631.77 | 0 | 0
*The amount sanctioned for construction of 1174 units being the 1st phase is Rs. 704.40 lakh. In the 2nd phase, out of the total sanctioned 1889 units in the year 2010-11, GoI adjusted 97 units and refunded an amount of Rs. 651.65 lakh from the sanctioned amount of Rs. 3579.02 lakh Therefore the total sanctioned unit becomes 2966.
9.1.3) Achievement ( under MDM Funds) (Source data: Table AT-11 of AWP&B 2019-20)
Sactioned by GoI during 2006-07 to 2018-19 |  | Achievement (C+IP) upto 31.12.18 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh)* | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 |  |  | 1174 | 1875.34
2966 | 3631.77 | 2966 | 3631.77 | 100% | 100% |  |  | 1792 | 1756.42
Kitchen Devices
9.2.1) Releasing details (Including Replacement)
Releases for Kitchen devices by GoI as on 31.12.2018
Schools | Installment | Units (New) | Amount (in lakh) | Replacement | Amount (in lakh) |  |  |  |  | 1408.8
Primary & UPY | 2006-07 | 1457 | 72.85 | 0 | 0
| 2007-08 | 0 | 0 | 0 | 0
| 2008-09 | 0 | 0 | 0 | 0
| 2009-10 | 1650 | 82.5 | 0 | 0
| 2010-11 | 0 | 0 | 0 | 0
| 2011-12 | 0 | 0 | 0 | 0
| 2012-13 | 0 | 0 | 0 | 0
| 2013-14 | 0 | 0 | 0 | 0
| 2014-15 | 0 | 0 | 0 | 0
| 2015-16 | 532 | 0 | 1457 | 72.85
| 2016-17* | 0 | 0 | 0 | 0
| 2017-18** | 0 | 0
| 2018-19 | 0 | 0
| Total | 3639 | 155.35 | 1457 | 72.85 |  |  | 228.2 | 5096 | 254.8
* 183 (new) sanctioned in FY 2016-17 and 1650(replacement) sanctioned in FY 2017-18 however, funds not released to State due to want of physical and financial progress report of 1989 KD sanctioned earlier
9.2.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
2006-07 to 2018-19 | Phy | Fin | Phy | Fin | Phy | Fin
| 5096 | 228.2 | 5096 | 228.2 | 0% | 0%
9.2.3) Achievement ( under MDM Funds) (Source data: Table AT-12 of AWP&B 2018-19)
Sactioned during 2006-07 to 2018-19 |  | Achievement (P+IP) upto 31.03.19 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
| 2 | 3 | 4 | 5 | 6
5096 | 228.2 | 5096 | 228.2 | 100% | 100%
Benchmark (85%)
100%
68%