## Sikkim
Government of India | [8 empty] | 1
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2019-20
State : Sikkim
Part-D: ANALYSIS SHEET
REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2018-19 (1.4.18 to 31.03.19)
I. PAB- MDM Approval VS Performance
1.1 No. of children
S.no | Stage | MDM PAB Approval for 2018-19 | Average number of children availed MDM during 1.4.18 to 31.03.19 (AT-5&5A) | Difference | Difference in %
1 | 2 | 3 | 4 | 5=(4-3) | 6
1 | Primary | 31347.5364 | 29573 | -1774.5364 | -5.661%
2 | Up Primary | 26675.7773 | 24217 | -2458.7773 | -9.217%
| Total | 58023.3136 | 53790 | -4233.3136 | -7.296%
1.2 No. of Working Days Approved for FY 2018-19
S.no | Stage | No of working days approved for FY 2018-19
1 | Primary | 224
2 | Upper Primary | 224
1.2.1) No. of School working days approved for 12 Months(April- March 2019)
S.no | Stage | No of Working days approved for 12 months | No. of working days served MDM | Difference (Less/Excess)
1 | Primary | 224 | 224 | 0 |  |  |  |  | 1
2 | Upper Primary | 224 | 224 | 0
1.3) No. of Meals (Primary & Upper Primary)
i) Base period 01.04.18 to 31.03.19
S. No | Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Difference | Diff in %
1 | PY | 7021848.1455 | 6624435 | -397413.1455 | -5.66%
2 | UP PY | 5975374.1091 | 5424577 | -550797.1091 | -9.218%
3 | Total | 12997222.2545 | 12049012 | -948210.2545 | -7.295%
ii) Base period 01.04.18 to 31.03.19
S. No | Stage | No. of Meals as per PAB approval (01.04.18 to 31.03.19) | No. of Meals served by State during the period 01.04.18 to 31.03.19 | Bench Mark as per State's claim
1 | PY | 7021848.1455 | 6624435 | 94.34%
2 | U PY | 5975374.1091 | 5424577 | 90.78%
3 | Total | 12997222.2545 | 12049012 | 92.7%
2. COVERAGE UNDER MDM
2.1 Institutions- (Primary) (Source: Table AT-3 of AWP&B 2019-20)
Sl. No. | Districts | No. of Existing Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | East | 141 | 141 | 0 | 0%
2 | West | 145 | 145 | 0 | 0%
3 | North | 62 | 62 | 0 | 0%
4 | South | 150 | 150 | 0 | 0%
| TOTAL | 498 | 498 | 0 | 0%
2.2 Institutions- (Upper Primary) (Source :Table AT-3A & 3B of AWP&B 2019-20)
Sl. No. | Districts | No. of Existing Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | East | 130 | 130 | 0 | 0%
2 | West | 98 | 98 | 0 | 0%
3 | North | 33 | 33 | 0 | 0%
4 | South | 109 | 109 | 0 | 0%
| TOTAL | 370 | 370 | 0 | 0%
2.3 PAB Approval VS. Coverage of children ( Primary) Source : Table AT-5 of AWP&B 2019-20)
Sl. No. | Districts | No. of children as per PAB Approval for 2018-19 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | East | 12961.2909 | 11604.9062 | -1356.3847 | -10.46%
2 | West | 7539.4 | 7257.7946 | -281.6054 | -3.735%
3 | North | 2533.0045 | 2442.0089 | -90.9956 | -3.592%
4 | South | 8313.8409 | 8268.6607 | -45.1802 | -0.5434%
| TOTAL | 31347.5364 | 29573.3705 | -1774.1658 | -5.66% |  |  | 0.9434 | 58023.3136 | 53790.2321
2.4 PAB Approval VS Coverage of children ( Upper Primary) (Source : Table AT-5-A of AWP&B 2019-20
Sl. No. | Districts | No. of children as per PAB Approval for 2018-19 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | East | 10961.9409 | 9979.0982 | -982.8427 | -8.966%
2 | West | 7083.4091 | 6218.7545 | -864.6546 | -12.21%
3 | North | 1765.9818 | 1593.3348 | -172.647 | -9.776%
4 | South | 6864.4455 | 6425.6741 | -438.7713 | -6.392%
| TOTAL | 26675.7773 | 24216.8616 | -2458.9157 | -9.218%
2.5 Enrolment Vs Coverage of children ( Primary) (Source : Table AT-4 of AWP&B 2019-20)
Sl. No. | Districts | Enrollment | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | East | 13822 | 11604.9062 | -2217.0938 | -16.04%
2 | West | 8143 | 7257.7946 | -885.2054 | -10.87%
3 | North | 2576 | 2442.0089 | -133.9911 | -5.202%
4 | South | 8892 | 8268.6607 | -623.3393 | -7.01%
| TOTAL | 33433 | 29573.3705 | -3859.6295 | -11.54% |  |  | 60691 | 60691 | 53790.2321 | 88.63%
2.6 Enrolment Vs. Coverage of children (U.Primary) (Source : Table AT-4A of AWP&B 2019-20)
Sl. No. | Districts | Enrollment | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | East | 11503 | 9979.0982 | -1523.9018 | -13.25%
2 | West | 6904 | 6218.7545 | -685.2455 | -9.925%
3 | North | 1858 | 1593.3348 | -264.6652 | -14.24%
4 | South | 6993 | 6425.6741 | -567.3259 | -8.113%
| TOTAL | 27258 | 24216.8616 | -3041.1384 | -11.16%
2.7 Number of meal to be served and actual number of meal served during 2018-19
|  |  | (Source: Table AT-5 & 5A of AWP&B 2019-20) |  |  |  |  | Meals to be served |  |  | Meals served
Sr. No. | District | No of meals to be served during 1.4.18 to 31.03.19 | No of meal served during 1.4.18 to 31.03.19 | % Meals Served |  |  |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 |  |  |  | 2903329.1636 | 2455474.7636 | 5358803.9273 | 2599499 | 2235318 | 4834817
1 | East | 5358803.9273 | 4834817 | 90.22% |  |  |  | 1688825.6 | 1586683.6364 | 3275509.2364 | 1625746 | 1393001 | 3018747
2 | West | 3275509.2364 | 3018747 | 92.16% |  |  |  | 567393.0182 | 395579.9273 | 962972.9455 | 547010 | 356907 | 903917
3 | North | 962972.9455 | 903917 | 93.87% |  |  |  | 1862300.3636 | 1537635.7818 | 3399936.1455 | 1852180 | 1439351 | 3291531
4 | South | 3399936.1455 | 3291531 | 96.81% |  |  |  | 7021848.1455 | 5975374.1091 | 12997222.2545 | 6624435 | 5424577 | 12049012
| TOTAL | 12997222.2545 | 12049012 | 92.7%
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. | Details | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 1.4.2018 | 0 | 0 | 0 | 0%
2 | Allocation for 2018-19 | 1598.54 | 1598.54 | 0 | 0%
3 | Lifting as on 31.03.2019 | 1598.54 | 1598.54 | 0 | 0%
3.2) ANALYSIS ON OPENING STOCK AND UNSPENT STOCK OF FOODGRAINS
3.2.1) District-wise opening balance as on 1.4.2018 (Source: Table AT-6 & 6A of AWP&B 2019-20)
|  |  |  | (in MTs) |  |  |  | Allocation |  |  | Opening Balance
S.No. | Name of District | Allocation for 2018-19 | Opening balance as on 01.04.2018 | % of OB on allocation 2018-19 |  |  |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 |  |  |  | 290.38 | 368.32 | 658.7 | 0 | 0 | 0
1 | East | 658.7 | 0 | 0% |  |  |  | 168.87 | 238.02 | 406.89 | 0 | 0 | 0
2 | West | 406.89 | 0 | 0% |  |  |  | 56.74 | 59.33 | 116.07 | 0 | 0 | 0
3 | North | 116.07 | 0 | 0% |  |  |  | 186.24 | 230.64 | 416.88 | 0 | 0 | 0
4 | South | 416.88 | 0 | 0% |  |  |  | 702.23 | 896.31 | 1598.54 | 0 | 0 | 0
| TOTAL | 1598.54 | 0 | 0%
3.2.2) District-wise Closing balance as on 31.03.2018 (Source: Table AT-6 & 6A of AWP&B 2019-20)
|  |  |  | (in MTs) |  |  |  | Lifted From FCI
S.No. | Name of District | Allocation for 2018-19 | Closing Balance as on 31.03.2019 | % of Closing Balance on allocation 2018-19 |  |  |  | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 |  |  |  | 290.38 | 368.32 | 658.7
1 | East | 658.7 | 0 | 0% |  |  |  | 168.87 | 238.02 | 406.89
2 | West | 406.89 | 0 | 0% |  |  |  | 56.74 | 59.33 | 116.07
3 | North | 116.07 | 0 | 0% |  |  |  | 186.24 | 230.64 | 416.88
4 | South | 416.88 | 0 | 0% |  |  |  | 702.23 | 896.31 | 1598.54
| TOTAL | 1598.54 | 0 | 0%
(in MTs)
Allocation | Unspent balance as on 01.04.18 | Lifting upto 31.03.19 | Total Availability | % Availability
1598.54 | 0 | 1598.54 | 1598.54 | 100%
Source: Table AT-6 & 6A of AWP&B 2019-20
3.4) District-wise Foodgrains availability as on 31.03.19 (Source : Table AT-6 & 6A of AWP&B 2019-20)
[6 empty] | (in MTs) |  | Utilisation
Sl. No. | District | Allocation | OB as on 01.04.2018 | Lifted from FCI | Total Availability | % Availability |  | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 290.38 | 368.32 | 658.7
1 | East | 658.7 | 0 | 658.7 | 658.7 | 100% |  | 168.87 | 238.02 | 406.89
2 | West | 406.89 | 0 | 406.89 | 406.89 | 100% |  | 56.74 | 59.33 | 116.07
3 | North | 116.07 | 0 | 116.07 | 116.07 | 100% |  | 186.24 | 230.64 | 416.88
4 | South | 416.88 | 0 | 416.88 | 416.88 | 100% |  | 702.23 | 896.31 | 1598.54
| TOTAL | 1598.54 | 0 | 1598.54 | 1598.54 | 100%
3.5) Foodgrains Allocation, Lifting (Availability) & Utilisation
Allocation | Total Availability | % Total Availability | Utilisation | % Utilisation
1598.54 | 1598.54 | 100% | 1598.54 | 100%
3.6) District-wise Utilisation of foodgrains (Source: Table AT-6 & 6A of AWP&B 2019-20)
Sl. No. | District | Allocation | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5
1 | East | 658.7 | 658.7 | 100%
2 | West | 406.89 | 406.89 | 100%
3 | North | 116.07 | 116.07 | 100%
4 | South | 416.88 | 416.88 | 100%
| TOTAL | 1598.54 | 1598.54 | 100%
3.7) Cost of Foodgrains: Allocation, Releases (Availability) & Utilisation
Allocation | Total Availability | % Availability | Bills submited by FCI | Payment made to FCI | % payment
47.9562 | 47.9562 | 100% | 47.9562 | 47.9562 | 100%
3.8) Payment of cost of foodgrain to FCI
Sl. No. | District | Allocation | Bills raised by FCI | Payment to FCI by State | % of Bills paid
1 | 2 | 3 | 4 | 5 | 6
1 | East | 19.761 | 19.761 | 19.761 | 100%
2 | West | 12.2067 | 12.2067 | 12.2067 | 100%
3 | North | 3.4821 | 3.4821 | 3.4821 | 100%
4 | South | 12.5064 | 12.5064 | 12.5064 | 100%
| TOTAL | 47.9562 | 47.9562 | 47.9562 | 100%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
Verification of Cooking Cost Allocation
| Centre (85,81,264x220xRs.1.5) |  |  | 283.1817
| State Share (85,81,264*220*Rs. 1.0) |  |  | 188.7878
| Total |  |  | 471.9695
| Actual Allocation shown in State Plan |  |  | 477.18
| Diff. (Excess/Deficit) |  |  | 5.2105
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 01.04.2018 (Source : Table AT-7 & 7A of AWP&B 2019-20)
| *(Refer col.8 of table AT-7 and AT-7A, AWP&B 2019-20 |  |  | (Rs. In lakhs) |  |  |  | Allocation |  |  | Opening Balance
S.No. | Name of District | Allocation for 2018-19 | Opening Balance as on 01.04.2018 | % of OB on allocation 2018-19 |  |  |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 |  |  |  | 124.42 | 162.7 | 287.12 | 70.15 | 0 | 70.15
1 | East | 287.12 | 70.15 | 24.43% |  |  |  | 73.32 | 96.85 | 170.17 | 0 | 0 | 0
2 | West | 170.17 | 0 | 0% |  |  |  | 23.18 | 27.11 | 50.29 | 0 | 0 | 0
3 | North | 50.29 | 0 | 0% |  |  |  | 80.06 | 100.71 | 180.77 | 0 | 0 | 0
4 | South | 180.77 | 0 | 0% |  |  |  | 300.98 | 387.37 | 688.35 | 70.15 | 0 | 70.15
| TOTAL | 688.35 | 70.15 | 10.19%
4.2.2) District-wise closing balance as on 31.03.2019 (Source : Table AT-7 & 7A of AWP&B 2019-20)
|  |  |  | (Rs. In lakhs) |  |  |  | Closing Balance / Unspent |  |  | Cooking Cost Received
S.No. | Name of District | Allocation for 2018-19 | Closing Balance as on 31.03.2019 | % of UB on allocation 2018-19 |  |  |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 |  |  |  | 40.753 | 0.293 | 41.046 | 73.66 | 162.7 | 236.36
1 | East | 287.12 | 41.046 | 14.3% |  |  |  | 12.5895 | 0.1825 | 12.772 | 73.32 | 96.85 | 170.17
2 | West | 170.17 | 12.772 | 7.505% |  |  |  | 3.9813 | 0.0455 | 4.0268 | 23.18 | 27.11 | 50.29
3 | North | 50.29 | 4.0268 | 8.007% |  |  |  | 13.7462 | 0.179 | 13.9252 | 80.06 | 100.71 | 180.77
4 | South | 180.77 | 13.9252 | 7.703% |  |  |  | 71.07 | 0.7 | 71.77 | 250.22 | 387.37 | 637.59
| TOTAL | 688.35 | 71.77 | 10.43%
4.3) Cooking cost allocation and disbursed to Districts
Allocation | Availability | Bench mark
100% | 110.4% | 85%
47718.17 | 52695.2695 | 40560.4445
Allocation | OB as on 01.04.18 | Disbursed to Dist | Total Availability | % Availability
688.35 | 70.15 | 637.59 | 707.74 | 102.8%
4.4) District-wise Cooking Cost availability (Source : Table AT-7 & 7A of AWP&B 2019-20)
[6 empty] | (Rs. In lakhs) |  | Expenditure
S.No. | Name of District | Allocation for 2018-19 | Opening Balance as on 01.04.2018 | Cooking assistance received | Total Availability of cooking cost | % Availability of cooking cost |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 103.057 | 162.407 | 265.464 |  |  | 0
1 | East | 287.12 | 70.15 | 236.36 | 306.51 | 106.8% |  | 60.7305 | 96.6675 | 157.398 |  |  | 0
2 | West | 170.17 | 0 | 170.17 | 170.17 | 100% |  | 19.1987 | 27.0645 | 46.2632 |  |  | 0
3 | North | 50.29 | 0 | 50.29 | 50.29 | 100% |  | 66.3138 | 100.531 | 166.8448 |  |  | 0
4 | South | 180.77 | 0 | 180.77 | 180.77 | 100% |  | 249.3 | 386.67 | 635.97 | 0 | 0 | 0
| TOTAL | 688.35 | 70.15 | 637.59 | 707.74 | 102.8%
4.5) Cooking Cost Utilisation
Allocation | Availability | % Availability | Utilisation | % Utilisation
688.35 | 707.74 | 102.8% | 635.97 | 92.39%
47718.17 | 52695.2695 | 21852.2148 | 35788.6275
4.6) District-wise Utilisation of Cooking cost
| (Refer col. 14 of Table AT-7 & 7A of AWP&B 2019-20) |  |  | (Rs. In lakhs)
S.No. | Name of District | Allocation for 2018-19 | Utilisation of Cooking assistance | % Utilisation
1 | 2 | 3 | 4 | 5
1 | East | 287.12 | 265.464 | 92.46%
2 | West | 170.17 | 157.398 | 92.49%
3 | North | 50.29 | 46.2632 | 91.99%
4 | South | 180.77 | 166.8448 | 92.3%
| TOTAL | 688.35 | 635.97 | 92.39%
5. Reconciliation of Utilisation and Performance during 2018-19 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | East | 100% | 92.46% | -7.5425
2 | West | 100% | 92.49% | -7.5054
3 | North | 100% | 91.99% | -8.0071
4 | South | 100% | 92.3% | -7.7033
| TOTAL | 100% | 92.39% | -7.6095
5.2 Reconciliation of Food grains utilisation during 2018-19 (Source data: para 2.5 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 01.4.18 to 31.03.19 | Expected consumption of food grains | Actual consumption of food grains | % consumption |  |  |  | Name of District | NO. OF MEALS PRY | NO. OF MEAL UPPR PRY | TOTAL NO. OF MEALS AS PER Performance | Formulae for Pry | Formulae for Upr Pry | Expected Consumption of foodgrains
1 | 2 | 3 | 4 | 5 | 6 |  |  |  | East | 2599499 | 2235318 | 4834817 | 259.9499 | 335.2977 | 595.2476
1 | East | 4834817 | 595.2476 | 658.7 | 110.7% |  |  |  | West | 1625746 | 1393001 | 3018747 | 162.5746 | 208.9502 | 371.5248
2 | West | 3018747 | 371.5248 | 406.89 | 109.5% |  |  |  | North | 547010 | 356907 | 903917 | 54.701 | 53.5361 | 108.2371
3 | North | 903917 | 108.2371 | 116.07 | 107.2% |  |  |  | South | 1852180 | 1439351 | 3291531 | 185.218 | 215.9026 | 401.1206
4 | South | 3291531 | 401.1206 | 416.88 | 103.9% |  |  |  | Total | 6624435 | 5424577 | 12049012 | 662.4435 | 813.6866 | 1476.1301
| TOTAL | 12049012 | 1476.1301 | 1598.54 | 108.3%
5.3 Reconciliation of Cooking Cost utilisation during 2018-19 (Source data: para 2.5 and 3.7 above)
Sr. No. | District | No. of Meals served during 01.4.18 to 31.03.19 | Expected Utilisation of Cooking Cost (Rs. In Lakhs) | Actual utilisation of Cooking cost (Rs. In Lakhs) | % Utilisation |  |  |  | Name of District | Pry / Average No. of children availed MDM [Col. 8/Col. 9] | Expected Utilisation of Cooking Cost / Pry | Average No. of children availed Upr Pry MDM [Col. 8/Col. 9] | Expected Utilisation of Cooking Cost Upr Pry | Expected Utilisation of Cooking Cost (In Lakhs) |  | Name of District | Actual utilisation of Cooking cost (Rs. In Lakhs) Pry | Actual utilisation of Cooking cost (Rs. In Lakhs) Upry Pry | Actual utilisation of Cooking cost (Rs. In Lakhs) Pry + Upr Pry
1 | East | 4834817 |  | 265.464 | #DIV/0! |  |  |  | East |  | 0 |  | 0 | 0 |  | West | 129.12 | 148.84 | 277.96
2 | West | 3018747 |  | 157.398 | #DIV/0! |  |  |  | West |  | 0 |  | 0 | 0 |  | Sepahijala | 73.46 | 97.69 | 171.15
3 | North | 903917 |  | 46.2632 | #DIV/0! |  |  |  | North |  | 0 |  | 0 | 0 |  | Khowai | 23.53 | 24.12 | 47.65
4 | South | 3291531 |  | 166.8448 | #DIV/0! |  |  |  | South |  | 0 |  | 0 | 0 |  | Gomati | 80.9 | 88.23 | 169.13
Total |  | 12049012 | 0 | 635.97 | #DIV/0! |  |  |  | Total | 0 | 0 | 0 | 0 | 0 |  | Total | 307.01 | 358.88 | 665.89
6. ANALYSIS OF HONORARIUM TO COOK-CUM-HELPERS
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers | [7 empty] | Allocation |  |  | Opening Balance
S.No. | Name of District | Allocation for 2018-19 | Opening Balance as on 1.4.2018 | Amount released | Total availability | % Availibilty |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | East | 72.3 | 4.5 | 67.8 | 72.3 | 100% |  | 49.4 | 22.9 | 72.3 | 4.5 | 0 | 4.5
2 | West | 43.7 | 0 | 43.7 | 43.7 | 100% |  | 23.1 | 20.6 | 43.7 | 0 | 0 | 0
3 | North | 16 | 0 | 16 | 16 | 100% |  | 7.7 | 8.3 | 16 | 0 | 0 | 0
4 | South | 57.1 | 0 | 57.1 | 57.1 | 100% |  | 39.2 | 17.9 | 57.1 | 0 | 0 | 0
| Total | 189.1 | 4.5 | 184.6 | 189.1 | 100% |  | 119.4 | 69.7 | 189.1 | 4.5 | 0 | 4.5
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers
Refer table AT-8 and AT-8A ,AWP&B, 2019-20 | [7 empty] | Releases |  |  | Expenditure
S.No. | Name of District | Allocation for 2018-19 | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation |  |  | Pry | U. Pry. | Total | Pry | U. Pry. | Total
1 | East | 72.3 | 72.3 | 72.3 | 100% |  |  | 44.9 | 22.9 | 67.8 | 49.4 | 22.9 | 72.3
2 | West | 43.7 | 43.7 | 42.7 | 97.71% |  |  | 23.1 | 20.6 | 43.7 | 22.1 | 20.6 | 42.7
3 | North | 16 | 16 | 16 | 100% |  |  | 7.7 | 8.3 | 16 | 7.7 | 8.3 | 16
4 | South | 57.1 | 57.1 | 57.1 | 100% |  |  | 39.2 | 17.9 | 57.1 | 39.2 | 17.9 | 57.1
| Total | 189.1 | 189.1 | 188.1 | 99.47% |  |  | 114.9 | 69.7 | 184.6 | 118.4 | 69.7 | 188.1
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
Refer table AT_8 and AT-8A,AWP&B, 2019-20 | [7 empty] | closing balamce
S.No. | Name of District | Allocation for 2018-19 | Total Availability | Closing balance as on 31.03.2019 | % of Closing Balance as on Allocation 2018-19 |  |  | Pry | U. Pry. | Total
1 | East | 72.3 | 72.3 | 0 | 0% |  |  | 0 | 0 | 0
2 | West | 43.7 | 43.7 | 1 | 2.288% |  |  | 1 | 0 | 1
3 | North | 16 | 16 | 0 | 0% |  |  | 0 | 0 | 0
4 | South | 57.1 | 57.1 | 0 | 0% |  |  | 0 | 0 | 0
| Total | 189.1 | 189.1 | 1 | 0.5288% |  |  | 1 | 0 | 1
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
Verification of Cooking Cost Allocation
| Centre (85,81,264x220xRs.1.5) |  |  | 283.1817
| State Share (85,81,264*220*Rs. 1.0) |  |  | 188.7878
| Total |  |  | 471.9695
| Actual Allocation shown in State Plan |  |  | 477.18
| Diff. (Excess/Deficit) |  |  | 5.2105
7.1) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2018-19 | 14.87 | 14.87 | 0 | 0%
2 | Opening Balance as on 1.4.2018 | 0 | 14.87 | 14.87 | 0%
3 | Releasing during 2018-19 | 14.87 | 14.87 | 0 | 0%
4 | Total Availability | 14.87 | 29.74 | 14.87 | 100%
7.2) Utilisation of MME during 2018-19 (Source data: Table AT-9 of AWP&B 2019-20)
|  |  | (Rs. In lakhs) | (As on 31.03.19)
Sl. No. | Activity | Allocated for 2017-18 | Total Availability | Expenditure | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | School Level Expenses | 7.44 | 7.44 | 2.5 | 100% | 0
2 | Management, Supervision, Training & Internal Monitoring | 7.43 | 7.43 | 12.37
Total |  | 14.87 | 14.87 | 14.87 | 100% | 0
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
Verification of Cooking Cost Allocation
| Centre (85,81,264x220xRs.1.5) |  |  | 283.1817
| State Share (85,81,264*220*Rs. 1.0) |  |  | 188.7878
| Total |  |  | 471.9695
| Actual Allocation shown in State Plan |  |  | 477.18
| Diff. (Excess/Deficit) |  |  | 5.2105
8.1) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Releases during 2018-19 | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2018-19 | 29.09 | 29.09 | 0 | 0%
2 | Opening Balance as on 1.4.2018 | 0 | 0 | 0 | 0%
3 | Releasing during 2018-2019 | 29.09 | 29.09 | 0 | 0%
4 | Total Availability | 29.09 | 29.09 | 0 | 0%
8.3) Utilisation of TA during 2018-19 (Source data: Table AT-8 of AWP&B 2019-20
|  |  | (Rs. In lakhs) |  |  | (As on 31.03.19)
Allocated for 2018-19 | Total Availability of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7 | 8= (2-5)
29.09 | 29.09 | 1598.54 | 29.0934 | 29.09 | 0.003428 | 100% | 0
Source: Table AT-11 of AWP&B 2019-20
9. INFRASTRUCTURE DEVELOPMENT DURING 2015-16 (Primary + Upper primary)
9.1 KITCHEN-CUM -STORES
9.1.1) Releasing details
Releases for Kitchen -cum-stores by GoI as on 31.03.19
Schools | Installment |  | Units | Amount (in lakh)
Primary + Upper Primary | 2006-07 |  | 800 | 480
| 2007-08 |  | 0 | 0
| 2008-09 |  | 59 | 35.4
| 2009-10 |  | 0 | 0
| 2010-11 |  | 0 | 0
| 2011-12 |  | 0 | 0
| 2013-14 |  | 77 | 168.94
| 2014-15 |  | 0 | 0
2015-16
| 2016-17 |  | 0 | 0
2017-18
| 2018-19 |  | 12 | 26.388
| Grand Total |  | 948 | 710.728
9.1.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-07 to 2018-19 | 948 | 710.718 | 948 | 710.718 | 0% | 0%
9.1.3) Achievement ( under MDM Funds) (Source data: Table AT-10 of AWP&B 2019-20)
Sactioned by GoI during 2006-07 to 2018-19 |  | Achievement (C+IP) upto 31.03.19 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
948 | 710.718 | 948 | 710.71 | 100% | 100%
9.2 KITCHEN DEVICES
9.2.1) Releasing details
Releases for Kitchen devices by GoI as on 31.03.2018
Schools | Installment |  | Units | Replacement | Amount (in lakh)
Primary + Upper Primary | 2006-07 |  | 446 |  | 22.3
| 2007-08 |  | 336 |  | 16.8
| 2009-10 |  | 0 |  | 0
| 2010-11 |  | 0 |  | 0
| 2011-12 |  | 97 |  | 4.85
| 2012-13 |  |  | 443 | 22.15
| 2013-14 |  |  | 336 | 16.8
2014-15
2015-16
| 2016-17 |  | 0 | 0
2017-18
| 2018-19* |  |  | 540 | 27
| Grand Total |  | 879 | 1319 | 109.9 |  |  | 2198 | 43.95 | 65.95
* 97 KD sanctioned, funds yet to be released to State
9.2.2) Reconciliation of amount sanctioned
Year | GoI records |  | State Plan |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-16-17 | 2198 | 109.9 | 2198 | 109.9 | 0% | 0%
9.2.3) Achievement ( under MDM Funds) (Source data: Table AT-11 of AWP&B 2019-20)
Sactioned during 2006-07 to 2018-19 |  | Achievement (C+IP) upto 31.03.19 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
2198 | 109.9 | 2198 | 109.9 | 100% | 100%
Benchmark (85%)
68%