## Chhattisgarh
Government of India
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2020-21
State : Chhattisgarh
Part-D: ANALYSIS SHEET
Section-A : REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2019-20
1. Calculation of Bench mark for utilisation.
1.1) No. of children
Stage | MDM PAB Approval for 2019-20 | Average number of children availed MDM during 2019-20 | Diff | Diff in %
Primary | 1700000 | 1587950 | -112050 | -6.591%
Up Primary | 1100000 | 925641 | -174359 | -15.85%
NCLP | 0 | 0 | 0 | 0%
Total | 2800000 | 2513591 | -286409 | -10.23%
1.2) No. of School working days
PY | 240 | 222 | -18 | -7.5%
UP.PY | 240 | 228 | -12 | -5%
NCLP | 0 | 0 | 0 | 0%
1.3) Number of meals served vis-à-vis PAB approval during 2019-20
Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Diff. | Diff in %
PY | 408000000 | 352574741 | -55425259 | -13.58%
UP PY | 264000000 | 211842317 | -52157683 | -19.76%
NCLP | 0 | 0 | 0 | 0%
Total | 672000000 | 564417058 | -107582942 | -16.01%
2. COVERAGE
2.1 Institutions- (Primary) (Source data : Table AT-3A of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Surajpur | 826 | 826 | 0 | 0%
2 | Balrampur | 1192 | 1192 | 0 | 0%
3 | Sarguja | 1393 | 1393 | 0 | 0%
4 | Bilaspur | 1545 | 1545 | 0 | 0%
5 | Raigarh | 745 | 745 | 0 | 0%
6 | Rajnandgaon | 693 | 693 | 0 | 0%
7 | Durg | 1714 | 1714 | 0 | 0%
8 | Raipur | 647 | 647 | 0 | 0%
9 | Bastar | 884 | 884 | 0 | 0%
10 | Narayanpur | 612 | 612 | 0 | 0%
11 | Sukma | 982 | 982 | 0 | 0%
12 | Kondagaon | 1553 | 1553 | 0 | 0%
13 | Balod | 1747 | 1747 | 0 | 0%
14 | Bemetera | 1597 | 1597 | 0 | 0%
15 | Gariyaband | 986 | 986 | 0 | 0%
16 | Balodabazar | 1229 | 1229 | 0 | 0%
17 | Koriya | 1494 | 1494 | 0 | 0%
18 | Janjgir-Champa | 967 | 967 | 0 | 0%
19 | Korba | 1307 | 1307 | 0 | 0%
20 | Jashpur | 666 | 666 | 0 | 0%
21 | Kawardha | 422 | 422 | 0 | 0%
22 | Mahasamund | 1986 | 1986 | 0 | 0%
23 | Dhamtari | 797 | 797 | 0 | 0%
24 | Kanker | 1860 | 1860 | 0 | 0%
25 | Dantewada | 1353 | 1353 | 0 | 0%
26 | Bijapur | 788 | 788 | 0 | 0%
27 | Mungeli | 1412 | 1412 | 0 | 0%
| TOTAL | 31397 | 31397 | 0 | 0%
2.2 Institutions- (Primary with Upper Primary) (Source data : Table AT-3B of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Surajpur | 413 | 413 | 0 | 0
2 | Balrampur | 638 | 638 | 0 | 0
3 | Sarguja | 571 | 571 | 0 | 0
4 | Bilaspur | 649 | 649 | 0 | 0
5 | Raigarh | 386 | 386 | 0 | 0
6 | Rajnandgaon | 204 | 204 | 0 | 0
7 | Durg | 782 | 782 | 0 | 0
8 | Raipur | 237 | 237 | 0 | 0
9 | Bastar | 452 | 452 | 0 | 0
10 | Narayanpur | 361 | 361 | 0 | 0
11 | Sukma | 450 | 450 | 0 | 0
12 | Kondagaon | 791 | 791 | 0 | 0
13 | Balod | 521 | 521 | 0 | 0
14 | Bemetera | 615 | 615 | 0 | 0
15 | Gariyaband | 496 | 496 | 0 | 0
16 | Balodabazar | 604 | 604 | 0 | 0
17 | Koriya | 525 | 525 | 0 | 0
18 | Janjgir-Champa | 419 | 419 | 0 | 0
19 | Korba | 502 | 502 | 0 | 0
20 | Jashpur | 275 | 275 | 0 | 0
21 | Kawardha | 146 | 146 | 0 | 0
22 | Mahasamund | 919 | 919 | 0 | 0
23 | Dhamtari | 482 | 482 | 0 | 0
24 | Kanker | 795 | 795 | 0 | 0
25 | Dantewada | 576 | 576 | 0 | 0
26 | Bijapur | 216 | 216 | 0 | 0
27 | Mungeli | 564 | 564 | 0 | 0
| TOTAL | 13589 | 13589 | 0 | 0
2.2A Institutions- (Upper Primary) (Source data : Table AT-3C of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Surajpur | 0 | 0 | 0 | 0%
2 | Balrampur | 0 | 0 | 0 | 0%
3 | Sarguja | 0 | 0 | 0 | 0%
4 | Bilaspur | 0 | 0 | 0 | 0%
5 | Raigarh | 0 | 0 | 0 | 0%
6 | Rajnandgaon | 0 | 0 | 0 | 0%
7 | Durg | 0 | 0 | 0 | 0%
8 | Raipur | 0 | 0 | 0 | 0%
9 | Bastar | 0 | 0 | 0 | 0%
10 | Narayanpur | 0 | 0 | 0 | 0%
11 | Sukma | 0 | 0 | 0 | 0%
12 | Kondagaon | 0 | 0 | 0 | 0%
13 | Balod | 0 | 0 | 0 | 0%
14 | Bemetera | 0 | 0 | 0 | 0%
15 | Gariyaband | 0 | 0 | 0 | 0%
16 | Balodabazar | 0 | 0 | 0 | 0%
17 | Koriya | 0 | 0 | 0 | 0%
18 | Janjgir-Champa | 0 | 0 | 0 | 0%
19 | Korba | 0 | 0 | 0 | 0%
20 | Jashpur | 0 | 0 | 0 | 0%
21 | Kawardha | 0 | 0 | 0 | 0%
22 | Mahasamund | 0 | 0 | 0 | 0%
23 | Dhamtari | 0 | 0 | 0 | 0%
24 | Kanker | 0 | 0 | 0 | 0%
25 | Dantewada | 0 | 0 | 0 | 0%
26 | Bijapur | 0 | 0 | 0 | 0%
27 | Mungeli | 0 | 0 | 0 | 0%
| TOTAL | 0 | 0 | 0 | 0%
2.3 Coverage Chidlren vs. Enrolment ( Primary) (Source data : Table AT-4 & 5 of AWP&B 2020-21)
Sl. No. | Districts | Enrolment as on 30.9.2019 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Surajpur | 48824 | 47416 | -1408 | -2.884%
2 | Balrampur | 113686 | 93776 | -19910 | -17.51%
3 | Sarguja | 72733 | 61949 | -10784 | -14.83%
4 | Bilaspur | 69485 | 58625 | -10860 | -15.63%
5 | Raigarh | 71214 | 60746 | -10468 | -14.7%
6 | Rajnandgaon | 29859 | 29428 | -431 | -1.443%
7 | Durg | 147084 | 120101 | -26983 | -18.35%
8 | Raipur | 25976 | 23435 | -2541 | -9.782%
9 | Bastar | 46101 | 43462 | -2639 | -5.724%
10 | Narayanpur | 63850 | 54580 | -9270 | -14.52%
11 | Sukma | 49939 | 46240 | -3699 | -7.407%
12 | Kondagaon | 102891 | 88137 | -14754 | -14.34%
13 | Balod | 66460 | 63073 | -3387 | -5.096%
14 | Bemetera | 52361 | 51154 | -1207 | -2.305%
15 | Gariyaband | 75629 | 67462 | -8167 | -10.8%
16 | Balodabazar | 53454 | 48421 | -5033 | -9.416%
17 | Koriya | 74981 | 66276 | -8705 | -11.61%
18 | Janjgir-Champa | 42131 | 35817 | -6314 | -14.99%
19 | Korba | 76997 | 67502 | -9495 | -12.33%
20 | Jashpur | 66454 | 56439 | -10015 | -15.07%
21 | Kawardha | 15281 | 13916 | -1365 | -8.933%
22 | Mahasamund | 85322 | 73672 | -11650 | -13.65%
23 | Dhamtari | 98863 | 86829 | -12034 | -12.17%
24 | Kanker | 110059 | 100914 | -9145 | -8.309%
25 | Dantewada | 57841 | 49206 | -8635 | -14.93%
26 | Bijapur | 29719 | 26157 | -3562 | -11.99%
27 | Mungeli | 61743 | 53217 | -8526 | -13.81%
| TOTAL | 1808937 | 1587950 | -220987 | -12.22%
2.4 Coverage Chidlren vs. Enrolment ( Up Pry) (Source : Table AT- 4A & 5-A of AWP&B 2020-21)
Sl. No. | Districts | Enrolment as on 30.9.2019 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Surajpur | 32634 | 30054 | -2580 | -7.906%
2 | Balrampur | 71039 | 58013 | -13026 | -18.34%
3 | Sarguja | 39498 | 32086 | -7412 | -18.77%
4 | Bilaspur | 35955 | 28984 | -6971 | -19.39%
5 | Raigarh | 46645 | 37903 | -8742 | -18.74%
6 | Rajnandgaon | 10901 | 10853 | -48 | -0.4403%
7 | Durg | 90381 | 72512 | -17869 | -19.77%
8 | Raipur | 10743 | 10096 | -647 | -6.023%
9 | Bastar | 31358 | 28848 | -2510 | -8.004%
10 | Narayanpur | 45546 | 36305 | -9241 | -20.29%
11 | Sukma | 29837 | 24324 | -5513 | -18.48%
12 | Kondagaon | 66470 | 54196 | -12274 | -18.47%
13 | Balod | 37638 | 33714 | -3924 | -10.43%
14 | Bemetera | 32951 | 29236 | -3715 | -11.27%
15 | Gariyaband | 45010 | 37154 | -7856 | -17.45%
16 | Balodabazar | 30598 | 26708 | -3890 | -12.71%
17 | Koriya | 46059 | 38965 | -7094 | -15.4%
18 | Janjgir-Champa | 26219 | 21333 | -4886 | -18.64%
19 | Korba | 51820 | 43516 | -8304 | -16.02%
20 | Jashpur | 37185 | 30811 | -6374 | -17.14%
21 | Kawardha | 7120 | 6122 | -998 | -14.02%
22 | Mahasamund | 55882 | 45634 | -10248 | -18.34%
23 | Dhamtari | 70393 | 58787 | -11606 | -16.49%
24 | Kanker | 70749 | 61721 | -9028 | -12.76%
25 | Dantewada | 33991 | 29252 | -4739 | -13.94%
26 | Bijapur | 8462 | 7655 | -807 | -9.537%
27 | Mungeli | 35895 | 30859 | -5036 | -14.03%
| TOTAL | 1100979 | 925641 | -175338 | -15.93%
2.5 No. of children ( Primary) (Source data : Table AT-5 of AWP&B 2020-21)
Sl. No. | Districts | No. of children as per PAB Approval for 2019-20 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Surajpur | 49042 | 47416 | -1626 | -3.316%
2 | Balrampur | 103342 | 93776 | -9566 | -9.257%
3 | Sarguja | 67368 | 61949 | -5419 | -8.044%
4 | Bilaspur | 63361 | 58625 | -4736 | -7.475%
5 | Raigarh | 67947 | 60746 | -7201 | -10.6%
6 | Rajnandgaon | 27484 | 29428 | 1944 | 7.073%
7 | Durg | 135600 | 120101 | -15499 | -11.43%
8 | Raipur | 25263 | 23435 | -1828 | -7.236%
9 | Bastar | 47209 | 43462 | -3747 | -7.937%
10 | Narayanpur | 58156 | 54580 | -3576 | -6.149%
11 | Sukma | 45778 | 46240 | 462 | 1.009%
12 | Kondagaon | 101215 | 88137 | -13078 | -12.92%
13 | Balod | 60999 | 63073 | 2074 | 3.4%
14 | Bemetera | 51700 | 51154 | -546 | -1.056%
15 | Gariyaband | 72620 | 67462 | -5158 | -7.103%
16 | Balodabazar | 48943 | 48421 | -522 | -1.067%
17 | Koriya | 69557 | 66276 | -3281 | -4.717%
18 | Janjgir-Champa | 38993 | 35817 | -3176 | -8.145%
19 | Korba | 74017 | 67502 | -6515 | -8.802%
20 | Jashpur | 62905 | 56439 | -6466 | -10.28%
21 | Kawardha | 14868 | 13916 | -952 | -6.403%
22 | Mahasamund | 78355 | 73672 | -4683 | -5.977%
23 | Dhamtari | 94332 | 86829 | -7503 | -7.954%
24 | Kanker | 103796 | 100914 | -2882 | -2.777%
25 | Dantewada | 54657 | 49206 | -5451 | -9.973%
26 | Bijapur | 24668 | 26157 | 1489 | 6.036%
27 | Mungeli | 57825 | 53217 | -4608 | -7.969%
| TOTAL | 1700000 | 1587950 | -112050 | -6.591%
2.6 No. of children ( Upper Primary) (Source data : Table AT-5-A of AWP&B 2020-21)
Sl. No. | Districts | No. of children as per PAB Approval for 2019-20 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Surajpur | 33105 | 30054 | -3051 | -9.216%
2 | Balrampur | 70521 | 58013 | -12508 | -17.74%
3 | Sarguja | 38566 | 32086 | -6480 | -16.8%
4 | Bilaspur | 35441 | 28984 | -6457 | -18.22%
5 | Raigarh | 45032 | 37903 | -7129 | -15.83%
6 | Rajnandgaon | 10458 | 10853 | 395 | 3.777%
7 | Durg | 92301 | 72512 | -19789 | -21.44%
8 | Raipur | 10110 | 10096 | -14 | -0.1385%
9 | Bastar | 33009 | 28848 | -4161 | -12.61%
10 | Narayanpur | 43481 | 36305 | -7176 | -16.5%
11 | Sukma | 28352 | 24324 | -4028 | -14.21%
12 | Kondagaon | 73380 | 54196 | -19184 | -26.14%
13 | Balod | 35780 | 33714 | -2066 | -5.774%
14 | Bemetera | 35646 | 29236 | -6410 | -17.98%
15 | Gariyaband | 45524 | 37154 | -8370 | -18.39%
16 | Balodabazar | 29142 | 26708 | -2434 | -8.352%
17 | Koriya | 46227 | 38965 | -7262 | -15.71%
18 | Janjgir-Champa | 27477 | 21333 | -6144 | -22.36%
19 | Korba | 53336 | 43516 | -9820 | -18.41%
20 | Jashpur | 36436 | 30811 | -5625 | -15.44%
21 | Kawardha | 6451 | 6122 | -329 | -5.1%
22 | Mahasamund | 55346 | 45634 | -9712 | -17.55%
23 | Dhamtari | 68598 | 58787 | -9811 | -14.3%
24 | Kanker | 69043 | 61721 | -7322 | -10.6%
25 | Dantewada | 33695 | 29252 | -4443 | -13.19%
26 | Bijapur | 7860 | 7655 | -205 | -2.608%
27 | Mungeli | 35683 | 30859 | -4824 | -13.52%
| TOTAL | 1100000 | 925641 | -174359 | -15.85%
2.7 Number of meal to be served and actual number of meal served during 2019-20 (Source data: Table AT-5 & 5A of AWP&B 2020-21)
Sr. No. | District | No of meals to be served during 2019-20 | No of meal served during 2019-20 | % Meals Served
1 | 2 | 3 | 4 | 5
1 | Surajpur | 19715280 | 17593786 | 89.24%
2 | Balrampur | 41727120 | 34196908 | 81.95%
3 | Sarguja | 25424160 | 20848277 | 82%
4 | Bilaspur | 23712480 | 19856962 | 83.74%
5 | Raigarh | 27114960 | 22226021 | 81.97%
6 | Rajnandgaon | 9106080 | 7972836 | 87.56%
7 | Durg | 54696240 | 43002508 | 78.62%
8 | Raipur | 8489520 | 7521032 | 88.59%
9 | Bastar | 19252320 | 16529816 | 85.86%
10 | Narayanpur | 24392880 | 20666951 | 84.73%
11 | Sukma | 17791200 | 16095654 | 90.47%
12 | Kondagaon | 41902800 | 31692686 | 75.63%
13 | Balod | 23226960 | 21209538 | 91.31%
14 | Bemetera | 20963040 | 18453113 | 88.03%
15 | Gariyaband | 28354560 | 23201403 | 81.83%
16 | Balodabazar | 18740400 | 17064346 | 91.06%
17 | Koriya | 27788160 | 23924643 | 86.1%
18 | Janjgir-Champa | 15952800 | 12622533 | 79.12%
19 | Korba | 30564720 | 25505696 | 83.45%
20 | Jashpur | 23841840 | 19467222 | 81.65%
21 | Kawardha | 5116560 | 4517398 | 88.29%
22 | Mahasamund | 32088240 | 26521041 | 82.65%
23 | Dhamtari | 39103200 | 33116366 | 84.69%
24 | Kanker | 41481360 | 37024800 | 89.26%
25 | Dantewada | 21204480 | 17573050 | 82.87%
26 | Bijapur | 7806720 | 7467946 | 95.66%
27 | Mungeli | 22441920 | 18544526 | 82.63%
| TOTAL | 672000000 | 564417058 | 83.99%
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 1.4.2019 | 4945.6 | 4945.6 | 0 | 0%
2 | Allocation for 2019-20 | 80400.03 | 80400.03 | 0 | 0%
3.2) District-wise opening balance as on 1.4.2019 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
S.No. | Name of District | Allocation | Opening Stock as on 01.04.2019 | % of OS on allocation
1 | 2 | 3 | 4 | 5
1 | Surajpur | 2368.788 | 144.6617 | 6.107%
2 | Balrampur | 5018.968 | 305.9358 | 6.096%
3 | Sarguja | 3005.212 | 188.6985 | 6.279%
4 | Bilaspur | 2796.544 | 176.2715 | 6.303%
5 | Raigarh | 3251.878 | 199.2195 | 6.126%
6 | Rajnandgaon | 1036.106 | 69.3353 | 6.692%
7 | Durg | 6577.24 | 401.0997 | 6.098%
8 | Raipur | 970.272 | 64.4482 | 6.642%
9 | Bastar | 2321.336 | 140.9092 | 6.07%
10 | Narayanpur | 2961.064 | 177.6735 | 6%
11 | Sukma | 2119.342 | 131.339 | 6.197%
12 | Kondagaon | 5070.84 | 305.8939 | 6.032%
13 | Balod | 2752.056 | 172.1065 | 6.254%
14 | Bemetera | 2524.06 | 153.5801 | 6.085%
15 | Gariyaband | 3381.74 | 209.1391 | 6.184%
16 | Balodabazar | 2223.742 | 138.7166 | 6.238%
17 | Koriya | 3333.538 | 204.1225 | 6.123%
18 | Janjgir-Champa | 1925.002 | 116.6972 | 6.062%
19 | Korba | 3696.508 | 223.2223 | 6.039%
20 | Jashpur | 2821.42 | 176.8128 | 6.267%
21 | Kawardha | 589.072 | 38.6618 | 6.563%
22 | Mahasamund | 3872.98 | 234.6816 | 6.059%
23 | Dhamtari | 4733.498 | 285.389 | 6.029%
24 | Kanker | 4976.654 | 304.6905 | 6.122%
25 | Dantewada | 2524.788 | 156.5877 | 6.202%
26 | Bijapur | 874.992 | 60.0155 | 6.859%
27 | Mungeli | 2672.39 | 165.6912 | 6.2%
| TOTAL | 80400.03 | 4945.6 | 6.151%
3.3) District-wise unspent balance as on 31.03.2020 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
S.No. | Name of District | Allocation | Unspent Balance as on 31.03.2020 | % of UB on allocation
1 | 2 | 3 | 4 | 5
1 | Surajpur | 2368.788 | 104.6486 | 4.418%
2 | Balrampur | 5018.968 | 229.2971 | 4.569%
3 | Sarguja | 3005.212 | 145.6835 | 4.848%
4 | Bilaspur | 2796.544 | 136.1732 | 4.869%
5 | Raigarh | 3251.878 | 149.2239 | 4.589%
6 | Rajnandgaon | 1036.106 | 54.7257 | 5.282%
7 | Durg | 6577.24 | 305.757 | 4.649%
8 | Raipur | 970.272 | 50.3247 | 5.187%
9 | Bastar | 2321.336 | 102.8417 | 4.43%
10 | Narayanpur | 2961.064 | 129.8566 | 4.385%
11 | Sukma | 2119.342 | 97.6237 | 4.606%
12 | Kondagaon | 5070.84 | 234.9013 | 4.632%
13 | Balod | 2752.056 | 127.3217 | 4.626%
14 | Bemetera | 2524.06 | 113.5999 | 4.501%
15 | Gariyaband | 3381.74 | 159.8895 | 4.728%
16 | Balodabazar | 2223.742 | 102.4024 | 4.605%
17 | Koriya | 3333.538 | 151.4045 | 4.542%
18 | Janjgir-Champa | 1925.002 | 88.9392 | 4.62%
19 | Korba | 3696.508 | 164.9017 | 4.461%
20 | Jashpur | 2821.42 | 135.5709 | 4.805%
21 | Kawardha | 589.072 | 29.9646 | 5.087%
22 | Mahasamund | 3872.98 | 175.1967 | 4.524%
23 | Dhamtari | 4733.498 | 208.1691 | 4.398%
24 | Kanker | 4976.654 | 221.9856 | 4.461%
25 | Dantewada | 2524.788 | 117.7343 | 4.663%
26 | Bijapur | 874.992 | 48.492 | 5.542%
27 | Mungeli | 2672.39 | 125.217 | 4.686%
| TOTAL | 80400.03 | 3711.8459 | 4.617%
3.4) Foodgrains Allocation & Lifting
(in MTs)
Allocation | Opening balance as on 01.4.19 | Lifting upto 31.03.2020 | Total Availibility | % Availibility
80400.03 | 4945.6 | 65800.06 | 70745.66 | 87.99%
Source: Table AT-6 & 6A of AWP&B 2020-21
3.5) District-wise Foodgrains availability as on 31.03.2020 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
Sl. No. | District | Allocation | OB as on 01.04.2019 | Lifted from FCI | Total Availibility | % Availibility
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Surajpur | 2368.788 | 144.6617 | 2067.99 | 2212.6517 | 93.41%
2 | Balrampur | 5018.968 | 305.9358 | 4007.3 | 4313.2358 | 85.94%
3 | Sarguja | 3005.212 | 188.6985 | 2402.78 | 2591.4785 | 86.23%
4 | Bilaspur | 2796.544 | 176.2715 | 2278.92 | 2455.1915 | 87.79%
5 | Raigarh | 3251.878 | 199.2195 | 2606.59 | 2805.8095 | 86.28%
6 | Rajnandgaon | 1036.106 | 69.3353 | 898.81 | 968.1453 | 93.44%
7 | Durg | 6577.24 | 401.0997 | 5027.92 | 5429.0197 | 82.54%
8 | Raipur | 970.272 | 64.4482 | 851.56 | 916.0082 | 94.41%
9 | Bastar | 2321.336 | 140.9092 | 1948.11 | 2089.0192 | 89.99%
10 | Narayanpur | 2961.064 | 177.6735 | 2438.2 | 2615.8735 | 88.34%
11 | Sukma | 2119.342 | 131.339 | 1860.44 | 1991.779 | 93.98%
12 | Kondagaon | 5070.84 | 305.8939 | 3713.4 | 4019.2939 | 79.26%
13 | Balod | 2752.056 | 172.1065 | 2455.45 | 2627.5565 | 95.48%
14 | Bemetera | 2524.06 | 153.5801 | 2147.39 | 2300.9701 | 91.16%
15 | Gariyaband | 3381.74 | 209.1391 | 2688.88 | 2898.0191 | 85.7%
16 | Balodabazar | 2223.742 | 138.7166 | 1978.6 | 2117.3166 | 95.21%
17 | Koriya | 3333.538 | 204.1225 | 2793.68 | 2997.8025 | 89.93%
18 | Janjgir-Champa | 1925.002 | 116.6972 | 1473.43 | 1590.1272 | 82.6%
19 | Korba | 3696.508 | 223.2223 | 3001.39 | 3224.6123 | 87.23%
20 | Jashpur | 2821.42 | 176.8128 | 2255.19 | 2432.0028 | 86.2%
21 | Kawardha | 589.072 | 38.6618 | 513.75 | 552.4118 | 93.78%
22 | Mahasamund | 3872.98 | 234.6816 | 3108.28 | 3342.9616 | 86.31%
23 | Dhamtari | 4733.498 | 285.389 | 3913.41 | 4198.799 | 88.7%
24 | Kanker | 4976.654 | 304.6905 | 4335.74 | 4640.4305 | 93.24%
25 | Dantewada | 2524.788 | 156.5877 | 2053.38 | 2209.9677 | 87.53%
26 | Bijapur | 874.992 | 60.0155 | 818.33 | 878.3455 | 100.4%
27 | Mungeli | 2672.39 | 165.6912 | 2161.14 | 2326.8312 | 87.07%
| TOTAL | 80400.03 | 4945.6 | 65800.06 | 70745.66 | 87.99%
3.6) Foodgrains Allocation, Lifting (availibility) & Utilisation
Allocation | T. Availibility | % T. Availibility | Utilisation | % Utilisation
80400.03 | 70745.66 | 87.99% | 67033.8141 | 83.38%
3.7) District-wise Utilisation of foodgrains (Source data: Table AT-6 & 6A of AWP&B 2020-21)
Sl. No. | District | Allocation | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5
1 | Surajpur | 2368.788 | 2108.0031 | 88.99%
2 | Balrampur | 5018.968 | 4083.9387 | 81.37%
3 | Sarguja | 3005.212 | 2445.795 | 81.39%
4 | Bilaspur | 2796.544 | 2319.0183 | 82.92%
5 | Raigarh | 3251.878 | 2656.5856 | 81.69%
6 | Rajnandgaon | 1036.106 | 913.4196 | 88.16%
7 | Durg | 6577.24 | 5123.2627 | 77.89%
8 | Raipur | 970.272 | 865.6835 | 89.22%
9 | Bastar | 2321.336 | 1986.1775 | 85.56%
10 | Narayanpur | 2961.064 | 2486.0169 | 83.96%
11 | Sukma | 2119.342 | 1894.1553 | 89.37%
12 | Kondagaon | 5070.84 | 3784.3926 | 74.63%
13 | Balod | 2752.056 | 2500.2348 | 90.85%
14 | Bemetera | 2524.06 | 2187.3702 | 86.66%
15 | Gariyaband | 3381.74 | 2738.1296 | 80.97%
16 | Balodabazar | 2223.742 | 2014.9142 | 90.61%
17 | Koriya | 3333.538 | 2846.398 | 85.39%
18 | Janjgir-Champa | 1925.002 | 1501.188 | 77.98%
19 | Korba | 3696.508 | 3059.7106 | 82.77%
20 | Jashpur | 2821.42 | 2296.4319 | 81.39%
21 | Kawardha | 589.072 | 522.4472 | 88.69%
22 | Mahasamund | 3872.98 | 3167.7649 | 81.79%
23 | Dhamtari | 4733.498 | 3990.6299 | 84.31%
24 | Kanker | 4976.654 | 4418.4449 | 88.78%
25 | Dantewada | 2524.788 | 2092.2334 | 82.87%
26 | Bijapur | 874.992 | 829.8535 | 94.84%
27 | Mungeli | 2672.39 | 2201.6142 | 82.38%
| TOTAL | 80400.03 | 67033.8141 | 83.38%
3.8) Cost of Foodgrains, Payment to FCI
Allocation | Bills submited by FCI | Payment made to FCI | % payment
2263.6329 | 1973.99 | 1973.99 | 100%
3.9) Payment of cost of foodgrain to FCI
Sl. No. | District | Allocation | Bills raised by FCI | Payment to FCI | Pending Bills | % Bill paid
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Surajpur | 66.7238 | 62.04 | 62.04 | 0 | 100%
2 | Balrampur | 141.391 | 120.22 | 120.22 | 0 | 100%
3 | Sarguja | 84.4954 | 72.08 | 72.08 | 0 | 100%
4 | Bilaspur | 78.6082 | 68.37 | 68.37 | 0 | 100%
5 | Raigarh | 91.5798 | 78.2 | 78.2 | 0 | 100%
6 | Rajnandgaon | 29.0031 | 26.96 | 26.96 | 0 | 100%
7 | Durg | 185.2842 | 150.84 | 150.84 | 0 | 100%
8 | Raipur | 27.1747 | 25.55 | 25.55 | 0 | 100%
9 | Bastar | 65.4128 | 58.44 | 58.44 | 0 | 100%
10 | Narayanpur | 83.5017 | 73.15 | 73.15 | 0 | 100%
11 | Sukma | 59.6401 | 55.81 | 55.81 | 0 | 100%
12 | Kondagaon | 142.9484 | 111.4 | 111.4 | 0 | 100%
13 | Balod | 77.3985 | 73.66 | 73.66 | 0 | 100%
14 | Bemetera | 71.1144 | 64.42 | 64.42 | 0 | 100%
15 | Gariyaband | 95.178 | 80.67 | 80.67 | 0 | 100%
16 | Balodabazar | 62.5508 | 59.36 | 59.36 | 0 | 100%
17 | Koriya | 93.8825 | 83.81 | 83.81 | 0 | 100%
18 | Janjgir-Champa | 54.2491 | 44.2 | 44.2 | 0 | 100%
19 | Korba | 104.1986 | 90.04 | 90.04 | 0 | 100%
20 | Jashpur | 79.3382 | 67.66 | 67.66 | 0 | 100%
21 | Kawardha | 16.5123 | 15.41 | 15.41 | 0 | 100%
22 | Mahasamund | 109.149 | 93.25 | 93.25 | 0 | 100%
23 | Dhamtari | 133.4433 | 117.4 | 117.4 | 0 | 100%
24 | Kanker | 140.1589 | 130.07 | 130.07 | 0 | 100%
25 | Dantewada | 71.046 | 61.6 | 61.6 | 0 | 100%
26 | Bijapur | 24.4493 | 24.55 | 24.55 | 0 | 100%
27 | Mungeli | 75.201 | 64.83 | 64.83 | 0 | 100%
| TOTAL | 2263.6329 | 1973.99 | 1973.99 | 0 | 100%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 01.04.2019 (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2019 | % of OB on allocation
1 | 2 | 3 | 4 | 5
1 | Surajpur | 1109.86 | 306.8 | 27.64%
2 | Balrampur | 2350.98 | 650.02 | 27.65%
3 | Sarguja | 1413.32 | 389.19 | 27.54%
4 | Bilaspur | 1315.88 | 362.16 | 27.52%
5 | Raigarh | 1524.26 | 421.16 | 27.63%
6 | Rajnandgaon | 491.64 | 134.17 | 27.29%
7 | Durg | 3081.07 | 851.84 | 27.65%
8 | Raipur | 459.89 | 125.64 | 27.32%
9 | Bastar | 1086.75 | 300.65 | 27.67%
10 | Narayanpur | 1384.14 | 383.51 | 27.71%
11 | Sukma | 994.93 | 274.47 | 27.59%
12 | Kondagaon | 2371.99 | 656.76 | 27.69%
13 | Balod | 1293.54 | 356.41 | 27.55%
14 | Bemetera | 1182.05 | 326.89 | 27.65%
15 | Gariyaband | 1587.13 | 437.97 | 27.6%
16 | Balodabazar | 1044.87 | 287.99 | 27.56%
17 | Koriya | 1562.43 | 431.72 | 27.63%
18 | Janjgir-Champa | 901.05 | 249.32 | 27.67%
19 | Korba | 1729.37 | 478.76 | 27.68%
20 | Jashpur | 1326.53 | 365.39 | 27.54%
21 | Kawardha | 278.73 | 76.28 | 27.37%
22 | Mahasamund | 1812.75 | 501.6 | 27.67%
23 | Dhamtari | 2214.05 | 613.07 | 27.69%
24 | Kanker | 2332.5 | 644.53 | 27.63%
25 | Dantewada | 1185.4 | 326.98 | 27.58%
26 | Bijapur | 416.67 | 113.29 | 27.19%
27 | Mungeli | 1254.67 | 346.08 | 27.58%
| TOTAL | 37706.45 | 10412.65 | 27.62%
4.1.2) District-wise unspent balance as on 31.03.2020 Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Unspent Balance as on 31.03.2020 | % of UB on allocation
1 | 2 | 3 | 4 | 5
1 | Surajpur | 1109.86 | 129.52 | 11.67%
2 | Balrampur | 2350.98 | 425.69 | 18.11%
3 | Sarguja | 1413.32 | 255.01 | 18.04%
4 | Bilaspur | 1315.88 | 223.07 | 16.95%
5 | Raigarh | 1524.26 | 268.48 | 17.61%
6 | Rajnandgaon | 491.64 | 58.03 | 11.8%
7 | Durg | 3081.07 | 648.13 | 21.04%
8 | Raipur | 459.89 | 50.42 | 10.96%
9 | Bastar | 1086.75 | 157.52 | 14.49%
10 | Narayanpur | 1384.14 | 223.53 | 16.15%
11 | Sukma | 994.93 | 119.23 | 11.98%
12 | Kondagaon | 2371.99 | 568.16 | 23.95%
13 | Balod | 1293.54 | 134.13 | 10.37%
14 | Bemetera | 1182.05 | 169.68 | 14.35%
15 | Gariyaband | 1587.13 | 295.08 | 18.59%
16 | Balodabazar | 1044.87 | 110.15 | 10.54%
17 | Koriya | 1562.43 | 233.19 | 14.92%
18 | Janjgir-Champa | 901.05 | 191.77 | 21.28%
19 | Korba | 1729.37 | 294.78 | 17.05%
20 | Jashpur | 1326.53 | 235.92 | 17.78%
21 | Kawardha | 278.73 | 32.13 | 11.53%
22 | Mahasamund | 1812.75 | 325.78 | 17.97%
23 | Dhamtari | 2214.05 | 345.07 | 15.59%
24 | Kanker | 2332.5 | 279.86 | 12%
25 | Dantewada | 1185.4 | 194.94 | 16.45%
26 | Bijapur | 416.67 | 32.84 | 7.882%
27 | Mungeli | 1254.67 | 213.4 | 17.01%
| TOTAL | 37706.45 | 6215.51 | 16.48%
4.2) Cooking cost allocation and disbursed to Districts
(Rs. In lakh)
Allocation | OB as on 01.4.2019 | Disbursed to Dist | Total Availability | % Availibility
37706.45 | 10412.65 | 27293.59 | 37706.24 | 100%
4.3) District-wise Cooking Cost availability (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2019 | Cooking assistance received | Total Availibility of cooking cost | % Availibility of cooking cost
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Surajpur | 1109.86 | 306.8 | 811.01 | 1117.81 | 100.7%
2 | Balrampur | 2350.98 | 650.02 | 1691.76 | 2341.78 | 99.61%
3 | Sarguja | 1413.32 | 389.19 | 1018.06 | 1407.25 | 99.57%
4 | Bilaspur | 1315.88 | 362.16 | 954.57 | 1316.73 | 100.1%
5 | Raigarh | 1524.26 | 421.16 | 1093.48 | 1514.64 | 99.37%
6 | Rajnandgaon | 491.64 | 134.17 | 356.57 | 490.74 | 99.82%
7 | Durg | 3081.07 | 851.84 | 2201.36 | 3053.2 | 99.1%
8 | Raipur | 459.89 | 125.64 | 334.43 | 460.07 | 100%
9 | Bastar | 1086.75 | 300.65 | 787.43 | 1088.08 | 100.1%
10 | Narayanpur | 1384.14 | 383.51 | 1004.49 | 1388 | 100.3%
11 | Sukma | 994.93 | 274.47 | 736.48 | 1010.95 | 101.6%
12 | Kondagaon | 2371.99 | 656.76 | 1687.01 | 2343.77 | 98.81%
13 | Balod | 1293.54 | 356.41 | 954.28 | 1310.69 | 101.3%
14 | Bemetera | 1182.05 | 326.89 | 870.81 | 1197.7 | 101.3%
15 | Gariyaband | 1587.13 | 437.97 | 1145.29 | 1583.26 | 99.76%
16 | Balodabazar | 1044.87 | 287.99 | 769.99 | 1057.98 | 101.3%
17 | Koriya | 1562.43 | 431.72 | 1138.09 | 1569.81 | 100.5%
18 | Janjgir-Champa | 901.05 | 249.32 | 647.45 | 896.77 | 99.52%
19 | Korba | 1729.37 | 478.76 | 1250.12 | 1728.88 | 99.97%
20 | Jashpur | 1326.53 | 365.39 | 951.02 | 1316.41 | 99.24%
21 | Kawardha | 278.73 | 76.28 | 202.8 | 279.08 | 100.1%
22 | Mahasamund | 1812.75 | 501.6 | 1310.39 | 1811.99 | 99.96%
23 | Dhamtari | 2214.05 | 613.07 | 1600.5 | 2213.57 | 99.98%
24 | Kanker | 2332.5 | 644.53 | 1708.73 | 2353.26 | 100.9%
25 | Dantewada | 1185.4 | 326.98 | 850.27 | 1177.25 | 99.31%
26 | Bijapur | 416.67 | 113.29 | 315.54 | 428.83 | 102.9%
27 | Mungeli | 1254.67 | 346.08 | 901.66 | 1247.74 | 99.45%
| TOTAL | 37706.45 | 10412.65 | 27293.59 | 37706.24 | 100%
4.4) Cooking Cost Utilisation |  |  |  | (Rs. In lakh)
Allocation | Total available | % available | Utilisation | % Utilisation
37706.45 | 37706.24 | 100% | 31490.73 | 83.52%
4.5) District-wise Utilisation of Cooking cost (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Utilisation of Cooking assistance | % Utilisation
1 | 2 | 3 | 4 | 5
1 | Surajpur | 1109.86 | 988.29 | 89.05%
2 | Balrampur | 2350.98 | 1916.09 | 81.5%
3 | Sarguja | 1413.32 | 1152.24 | 81.53%
4 | Bilaspur | 1315.88 | 1093.66 | 83.11%
5 | Raigarh | 1524.26 | 1246.16 | 81.76%
6 | Rajnandgaon | 491.64 | 432.71 | 88.01%
7 | Durg | 3081.07 | 2405.07 | 78.06%
8 | Raipur | 459.89 | 409.65 | 89.08%
9 | Bastar | 1086.75 | 930.56 | 85.63%
10 | Narayanpur | 1384.14 | 1164.47 | 84.13%
11 | Sukma | 994.93 | 891.72 | 89.63%
12 | Kondagaon | 2371.99 | 1775.61 | 74.86%
13 | Balod | 1293.54 | 1176.56 | 90.96%
14 | Bemetera | 1182.05 | 1028.02 | 86.97%
15 | Gariyaband | 1587.13 | 1288.18 | 81.16%
16 | Balodabazar | 1044.87 | 947.83 | 90.71%
17 | Koriya | 1562.43 | 1336.62 | 85.55%
18 | Janjgir-Champa | 901.05 | 705 | 78.24%
19 | Korba | 1729.37 | 1434.1 | 82.93%
20 | Jashpur | 1326.53 | 1080.49 | 81.45%
21 | Kawardha | 278.73 | 246.95 | 88.6%
22 | Mahasamund | 1812.75 | 1486.21 | 81.99%
23 | Dhamtari | 2214.05 | 1868.5 | 84.39%
24 | Kanker | 2332.5 | 2073.4 | 88.89%
25 | Dantewada | 1185.4 | 982.31 | 82.87%
26 | Bijapur | 416.67 | 395.99 | 95.04%
27 | Mungeli | 1254.67 | 1034.34 | 82.44%
| TOTAL | 37706.45 | 31490.73 | 83.52%
5. Reconciliation of Utilisation and Performance during 2019-20 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost (Source data: para 3.7 and 4.5 above)
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | Surajpur | 88.99% | 89.05% | 0.05558%
2 | Balrampur | 81.37% | 81.5% | 0.1317%
3 | Sarguja | 81.39% | 81.53% | 0.1421%
4 | Bilaspur | 82.92% | 83.11% | 0.188%
5 | Raigarh | 81.69% | 81.76% | 0.06119%
6 | Rajnandgaon | 88.16% | 88.01% | -0.1453%
7 | Durg | 77.89% | 78.06% | 0.1658%
8 | Raipur | 89.22% | 89.08% | -0.1451%
9 | Bastar | 85.56% | 85.63% | 0.06596%
10 | Narayanpur | 83.96% | 84.13% | 0.1726%
11 | Sukma | 89.37% | 89.63% | 0.2517%
12 | Kondagaon | 74.63% | 74.86% | 0.2269%
13 | Balod | 90.85% | 90.96% | 0.1069%
14 | Bemetera | 86.66% | 86.97% | 0.3085%
15 | Gariyaband | 80.97% | 81.16% | 0.196%
16 | Balodabazar | 90.61% | 90.71% | 0.1035%
17 | Koriya | 85.39% | 85.55% | 0.1608%
18 | Janjgir-Champa | 77.98% | 78.24% | 0.2583%
19 | Korba | 82.77% | 82.93% | 0.1532%
20 | Jashpur | 81.39% | 81.45% | 0.05959%
21 | Kawardha | 88.69% | 88.6% | -0.09159%
22 | Mahasamund | 81.79% | 81.99% | 0.1951%
23 | Dhamtari | 84.31% | 84.39% | 0.08671%
24 | Kanker | 88.78% | 88.89% | 0.1083%
25 | Dantewada | 82.87% | 82.87% | -0.0002998%
26 | Bijapur | 94.84% | 95.04% | 0.1956%
27 | Mungeli | 82.38% | 82.44% | 0.05549%
| TOTAL | 83.38% | 83.52% | 0.1401%
5.2 Reconciliation of Food grains utilisation during 2019-20 (Source data: para 2.7 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 2019-20 | Expected consumption of food grains | Actual consumption of food grains | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | Surajpur | 17593786 | 2108.0031 | 2108.0031 | 100%
2 | Balrampur | 34196908 | 4083.9387 | 4083.9387 | 100%
3 | Sarguja | 20848277 | 2445.795 | 2445.795 | 100%
4 | Bilaspur | 19856962 | 2319.0183 | 2319.0183 | 100%
5 | Raigarh | 22226021 | 2656.5856 | 2656.5856 | 100%
6 | Rajnandgaon | 7972836 | 913.4196 | 913.4196 | 100%
7 | Durg | 43002508 | 5123.2627 | 5123.2627 | 100%
8 | Raipur | 7521032 | 865.6835 | 865.6835 | 100%
9 | Bastar | 16529816 | 1986.1775 | 1986.1775 | 100%
10 | Narayanpur | 20666951 | 2486.0169 | 2486.0169 | 100%
11 | Sukma | 16095654 | 1894.1553 | 1894.1553 | 100%
12 | Kondagaon | 31692686 | 3784.3926 | 3784.3926 | 100%
13 | Balod | 21209538 | 2500.2348 | 2500.2348 | 100%
14 | Bemetera | 18453113 | 2187.3702 | 2187.3702 | 100%
15 | Gariyaband | 23201403 | 2738.1296 | 2738.1296 | 100%
16 | Balodabazar | 17064346 | 2014.9142 | 2014.9142 | 100%
17 | Koriya | 23924643 | 2846.398 | 2846.398 | 100%
18 | Janjgir-Champa | 12622533 | 1501.188 | 1501.188 | 100%
19 | Korba | 25505696 | 3059.7106 | 3059.7106 | 100%
20 | Jashpur | 19467222 | 2296.4319 | 2296.4319 | 100%
21 | Kawardha | 4517398 | 522.4472 | 522.4472 | 100%
22 | Mahasamund | 26521041 | 3167.7649 | 3167.7649 | 100%
23 | Dhamtari | 33116366 | 3990.6299 | 3990.6299 | 100%
24 | Kanker | 37024800 | 4418.4449 | 4418.4449 | 100%
25 | Dantewada | 17573050 | 2092.2334 | 2092.2334 | 100%
26 | Bijapur | 7467946 | 829.8535 | 829.8535 | 100%
27 | Mungeli | 18544526 | 2201.6142 | 2201.6142 | 100%
| TOTAL | 564417058 | 67033.8141 | 67033.8141 | 100%
5.3 Reconciliation of Cooking Cost utilisation during 2019-20 (Source data: para 2.5 and 4.7 above)
(Rs. in Lakh)
Sr. No. | District | No. of Meals served during 2019-20 | Expected expenditure of cooking cost | Actual expenditure of cooking cost | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | Surajpur | 17593786 | 988.29 | 988.29 | 100%
2 | Balrampur | 34196908 | 1916.09 | 1916.09 | 100%
3 | Sarguja | 20848277 | 1152.24 | 1152.24 | 100%
4 | Bilaspur | 19856962 | 1093.66 | 1093.66 | 100%
5 | Raigarh | 22226021 | 1246.16 | 1246.16 | 100%
6 | Rajnandgaon | 7972836 | 432.71 | 432.71 | 100%
7 | Durg | 43002508 | 2405.07 | 2405.07 | 100%
8 | Raipur | 7521032 | 409.65 | 409.65 | 100%
9 | Bastar | 16529816 | 930.56 | 930.56 | 100%
10 | Narayanpur | 20666951 | 1164.47 | 1164.47 | 100%
11 | Sukma | 16095654 | 891.72 | 891.72 | 100%
12 | Kondagaon | 31692686 | 1775.61 | 1775.61 | 100%
13 | Balod | 21209538 | 1176.56 | 1176.56 | 100%
14 | Bemetera | 18453113 | 1028.02 | 1028.02 | 100%
15 | Gariyaband | 23201403 | 1288.18 | 1288.18 | 100%
16 | Balodabazar | 17064346 | 947.83 | 947.83 | 100%
17 | Koriya | 23924643 | 1336.62 | 1336.62 | 100%
18 | Janjgir-Champa | 12622533 | 705 | 705 | 100%
19 | Korba | 25505696 | 1434.1 | 1434.1 | 100%
20 | Jashpur | 19467222 | 1080.49 | 1080.49 | 100%
21 | Kawardha | 4517398 | 246.95 | 246.95 | 100%
22 | Mahasamund | 26521041 | 1486.21 | 1486.21 | 100%
23 | Dhamtari | 33116366 | 1868.5 | 1868.5 | 100%
24 | Kanker | 37024800 | 2073.4 | 2073.4 | 100%
25 | Dantewada | 17573050 | 982.31 | 982.31 | 100%
26 | Bijapur | 7467946 | 395.99 | 395.99 | 100%
27 | Mungeli | 18544526 | 1034.34 | 1034.34 | 100%
| TOTAL | 564417058 | 31490.73 | 31490.73 | 100%
6. ANALYSIS of HONORIUM, To COOK-CUM-HELPERS
6.1) District-wise number of cook-cum-Helpers approved by PAB and engaged by State
(Refer table AT_8 and AT-8A, AWP&B, 2020-21)
S.No. | Name of District | PAB Approval | Engaged by State | Not engaged
1 | 2 | 3 | 4 | 5 = (4 - 3)
1 | Surajpur | 2744 | 2452 | -292
2 | Balrampur | 4667 | 4329 | -338
3 | Sarguja | 3886 | 3701 | -185
4 | Bilaspur | 4302 | 3841 | -461
5 | Raigarh | 2964 | 2708 | -256
6 | Rajnandgaon | 1309 | 1274 | -35
7 | Durg | 6614 | 5738 | -876
8 | Raipur | 1398 | 1358 | -40
9 | Bastar | 2808 | 2491 | -317
10 | Narayanpur | 2560 | 2397 | -163
11 | Sukma | 2806 | 2656 | -150
12 | Kondagaon | 5375 | 4832 | -543
13 | Balod | 3955 | 3823 | -132
14 | Bemetera | 3837 | 3573 | -264
15 | Gariyaband | 3534 | 3178 | -356
16 | Balodabazar | 3303 | 3238 | -65
17 | Koriya | 4309 | 3831 | -478
18 | Janjgir-Champa | 2371 | 2481 | 110
19 | Korba | 3940 | 3668 | -272
20 | Jashpur | 2570 | 2322 | -248
21 | Kawardha | 930 | 851 | -79
22 | Mahasamund | 5805 | 5113 | -692
23 | Dhamtari | 3739 | 3429 | -310
24 | Kanker | 5438 | 5272 | -166
25 | Dantewada | 3465 | 3385 | -80
26 | Bijapur | 2107 | 1475 | -632
27 | Mungeli | 2684 | 3533 | 849
| TOTAL | 93420 | 86949 | -6471 |  |  |  | 0.93073
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
(Refer table AT_8 and AT-8A, AWP&B, 2020-21)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2019 | Amount released | Total availability | % Availibilty
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Surajpur | 329.28 | 20.8 | 295.28 | 316.08 | 95.99%
2 | Balrampur | 560.04 | 36.7 | 521.32 | 558.02 | 99.64%
3 | Sarguja | 466.32 | 31.4 | 445.84 | 477.24 | 102.3%
4 | Bilaspur | 516.24 | 32.6 | 462.72 | 495.32 | 95.95%
5 | Raigarh | 355.68 | 22.96 | 326.1 | 349.06 | 98.14%
6 | Rajnandgaon | 157.08 | 10.8 | 153.52 | 164.32 | 104.6%
7 | Durg | 793.68 | 48.68 | 691.08 | 739.76 | 93.21%
8 | Raipur | 167.76 | 11.52 | 163.64 | 175.16 | 104.4%
9 | Bastar | 336.96 | 21.14 | 299.96 | 321.1 | 95.29%
10 | Narayanpur | 307.2 | 20.32 | 288.6 | 308.92 | 100.6%
11 | Sukma | 336.72 | 22.52 | 319.9 | 342.42 | 101.7%
12 | Kondagaon | 645 | 40.98 | 581.9 | 622.88 | 96.57%
13 | Balod | 474.6 | 32.44 | 460.64 | 493.08 | 103.9%
14 | Bemetera | 460.44 | 30.32 | 430.4 | 460.72 | 100.1%
15 | Gariyaband | 424.08 | 26.96 | 382.74 | 409.7 | 96.61%
16 | Balodabazar | 396.36 | 27.46 | 389.98 | 417.44 | 105.3%
17 | Koriya | 517.08 | 32.52 | 461.54 | 494.06 | 95.55%
18 | Janjgir-Champa | 284.52 | 21.06 | 298.84 | 319.9 | 112.4%
19 | Korba | 472.8 | 31.12 | 441.84 | 472.96 | 100%
20 | Jashpur | 308.4 | 19.7 | 279.7 | 299.4 | 97.08%
21 | Kawardha | 111.6 | 7.22 | 102.54 | 109.76 | 98.35%
22 | Mahasamund | 696.6 | 43.38 | 615.8 | 659.18 | 94.63%
23 | Dhamtari | 448.68 | 29.08 | 412.84 | 441.92 | 98.49%
24 | Kanker | 652.56 | 44.72 | 634.98 | 679.7 | 104.2%
25 | Dantewada | 415.8 | 28.7 | 407.74 | 436.44 | 105%
26 | Bijapur | 252.84 | 12.52 | 177.82 | 190.34 | 75.28%
27 | Mungeli | 322.08 | 29.98 | 425.6 | 455.58 | 141.4%
| TOTAL | 11210.4 | 737.6 | 10472.86 | 11210.46 | 100%
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2020-21)
S.No. | Name of District | Allocation | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation
1 | 2 | 3 | 4 | 5 | 6
1 | Surajpur | 329.28 | 316.08 | 294.24 | 89.36%
2 | Balrampur | 560.04 | 558.02 | 519.48 | 92.76%
3 | Sarguja | 466.32 | 477.24 | 444.12 | 95.24%
4 | Bilaspur | 516.24 | 495.32 | 460.92 | 89.28%
5 | Raigarh | 355.68 | 349.06 | 324.96 | 91.36%
6 | Rajnandgaon | 157.08 | 164.32 | 152.88 | 97.33%
7 | Durg | 793.68 | 739.76 | 688.56 | 86.76%
8 | Raipur | 167.76 | 175.16 | 162.96 | 97.14%
9 | Bastar | 336.96 | 321.1 | 298.92 | 88.71%
10 | Narayanpur | 307.2 | 308.92 | 287.64 | 93.63%
11 | Sukma | 336.72 | 342.42 | 318.72 | 94.65%
12 | Kondagaon | 645 | 622.88 | 579.84 | 89.9%
13 | Balod | 474.6 | 493.08 | 458.76 | 96.66%
14 | Bemetera | 460.44 | 460.72 | 428.76 | 93.12%
15 | Gariyaband | 424.08 | 409.7 | 381.36 | 89.93%
16 | Balodabazar | 396.36 | 417.44 | 388.56 | 98.03%
17 | Koriya | 517.08 | 494.06 | 459.72 | 88.91%
18 | Janjgir-Champa | 284.52 | 319.9 | 297.72 | 104.6%
19 | Korba | 472.8 | 472.96 | 440.16 | 93.1%
20 | Jashpur | 308.4 | 299.4 | 278.64 | 90.35%
21 | Kawardha | 111.6 | 109.76 | 102.12 | 91.51%
22 | Mahasamund | 696.6 | 659.18 | 613.56 | 88.08%
23 | Dhamtari | 448.68 | 441.92 | 411.48 | 91.71%
24 | Kanker | 652.56 | 679.7 | 632.64 | 96.95%
25 | Dantewada | 415.8 | 436.44 | 406.2 | 97.69%
26 | Bijapur | 252.84 | 190.34 | 177 | 70%
27 | Mungeli | 322.08 | 455.58 | 423.96 | 131.6%
| TOTAL | 11210.4 | 11210.46 | 10433.88 | 93.07%
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A, AWP&B - 2020-21)
S.No. | Name of District | Allocation | Total Availability | Unspent balance as on 31.03.2020 | % of UB as on Allocation
1 | 2 | 3 | 4 | 5 | 6
1 | Surajpur | 329.28 | 316.08 | 21.84 | 6.633%
2 | Balrampur | 560.04 | 558.02 | 38.54 | 6.882%
3 | Sarguja | 466.32 | 477.24 | 33.12 | 7.102%
4 | Bilaspur | 516.24 | 495.32 | 34.4 | 6.664%
5 | Raigarh | 355.68 | 349.06 | 24.1 | 6.776%
6 | Rajnandgaon | 157.08 | 164.32 | 11.44 | 7.283%
7 | Durg | 793.68 | 739.76 | 51.2 | 6.451%
8 | Raipur | 167.76 | 175.16 | 12.2 | 7.272%
9 | Bastar | 336.96 | 321.1 | 22.18 | 6.582%
10 | Narayanpur | 307.2 | 308.92 | 21.28 | 6.927%
11 | Sukma | 336.72 | 342.42 | 23.7 | 7.038%
12 | Kondagaon | 645 | 622.88 | 43.04 | 6.673%
13 | Balod | 474.6 | 493.08 | 34.32 | 7.231%
14 | Bemetera | 460.44 | 460.72 | 31.96 | 6.941%
15 | Gariyaband | 424.08 | 409.7 | 28.34 | 6.683%
16 | Balodabazar | 396.36 | 417.44 | 28.88 | 7.286%
17 | Koriya | 517.08 | 494.06 | 34.34 | 6.641%
18 | Janjgir-Champa | 284.52 | 319.9 | 22.18 | 7.796%
19 | Korba | 472.8 | 472.96 | 32.8 | 6.937%
20 | Jashpur | 308.4 | 299.4 | 20.76 | 6.732%
21 | Kawardha | 111.6 | 109.76 | 7.64 | 6.846%
22 | Mahasamund | 696.6 | 659.18 | 45.62 | 6.549%
23 | Dhamtari | 448.68 | 441.92 | 30.44 | 6.784%
24 | Kanker | 652.56 | 679.7 | 47.06 | 7.212%
25 | Dantewada | 415.8 | 436.44 | 30.24 | 7.273%
26 | Bijapur | 252.84 | 190.34 | 13.34 | 5.276%
27 | Mungeli | 322.08 | 455.58 | 31.62 | 9.817%
| TOTAL | 11210.4 | 11210.46 | 776.58 | 6.927%
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
7.1) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2019-20 | 822.84 | 822.84 | 0 | 0%
2 | Opening Balance as on 01.04.2019 | 1.09 | 1.09 | 0 | 0%
3 | Released during 2019-20. | 821.75 | 821.75 | 0 | 0%
4 | Total Availibility | 822.84 | 822.84 | 0 | 0%
7.2) Utilisation of MME during 2019-20 (Source data: Table AT-10 of AWP&B 2020-21)
|  |  |  | (Rs. In lakh) | (As on 31.03.2020)
Sl. No. | Activity | Allocated | Total Availibility | Expenditure | Exp as % of allocation
1 | 2 | 3 | 4 | 5 | 6
1 | School Level Expenses | 411.42 | 400.84 | 389.98 | 94.79%
2 | Management, Supervision, Training & Internal Monitoring, External Monitoring & Evaluation | 411.42 | 422 | 417.04 | 101.4%
Total |  | 822.84 | 822.84 | 807.02 | 98.08%
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
8.1) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Activity | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2019-20 | 992.22 | 992.22 | 0 | 0%
2 | Opening Balance as on 01.04.2019 | 110.9 | 110.9 | 0 | 0%
3 | Released during 2019-20 | 881.32 | 881.32 | 0 | 0%
4 | Total Availibility | 992.22 | 992.22 | 0 | 0%
8.2) Utilisation of TA during 2019-20 (Source data: Table AT-9 of AWP&B 2020-21)
(Rs. In lakh)
Allocated for 2019-20 | Total availability of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7 | 8= (2-5)
992.22 | 992.22 | 65800.06 | 865.2708 | 865.27 | 0.000789 | 87.21% | 126.95
9. INFRASTRUCTURE DEVELOPMENT DURING 2019-20 (Primary + Upper primary)
Kitchen-cum-Stores
9.1) Releasing details
9.1.1) Releasing details
Releases for Kitchen sheds by GoI as on 31.3.2020
Schools | Installment | Dated | Units | Amount (Rs in lakh)
Primary + Upper-Primary | 2006-07 |  | 5570 | 3342.28
| 2007-08 |  | 6016 | 3609.6
| 2008-09 |  | 26727 | 16036.2
| 2011-12 |  | 8953 | 9351.87
| Grand Total |  | 47266 | 32339.95
9.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-13 | 47266 | 32339.95 | 47266 | 32339.95 | 0% | 0%
9.3) Achievement ( under MDM Funds) (Source data: Table AT-10 of AWP&B 2020-21)
Sanctioned by GoI during 2006-07 to 2019-20 |  | Constructed + In progress upto 31.03.2020 |  | Achievement as % of allocation
Physical | Financial (Rs in Lakh) | Physical | Financial (Rs in Lakh) | Physical | Financial (Rs in Lakh)
1 | 2 | 3 | 4 | 5 | 6
47266 | 32339.95 | 47266 | 32339.95 | 100% | 100%
10. Kitchen Devices
10.1 Releases for Kitchen devices by GoI as on 31.3.2020
Schools | Year | Units | Amount (Rs in lakh)
Primary & UPY | 2006-07 | 22420 | 1121
| 2007-08 | 6016 | 300.8
| 2008-09 | 30774 | 1538.7
| 2012-13 (rep.) | 16800 | 840
| 2014-15 (rep.) | 30774 | 1538.7
| 2018-19 (rep.) | 28436 | 1421.8
| Total | 135220 | 6761
10.1) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-18 | 59210 | 2960.5 | 59210 | 2960.5 | 0% | 0%
2012-13 to 2019-20 (Replacement) | 76010 | 3800.5 | 76010 | 3800.5 | 0% | 0%
10.2) Achievement ( under MDM Funds) (Source data: Table AT-11 of AWP&B 2020-21)
| Sanctioned during 2006-07 to 2019-20 |  | Achievement (Procured+IP) |  | Achievement as % of allocation
| Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7
2006-10 | 59210 | 2960.5 | 59210 | 2960.5 | 100% | 100%
2012-13 -2018-19(Replacement) | 76010 | 3800.5 | 76010 | 3800.5 | 100% | 100%
Benchmark (85%)
100%
68%