## Goa
Government of India
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2020-20
State : Goa
Part-D: ANALYSIS SHEET
Section-A : REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2019-20 (1.4.19 to 31.12.19)
1. Calculation of Bench mark for utilisation.
1.1) No. of children
Stage | MDM PAB Approval for 2019-20 | Average number of children availed MDM during 1.4.19 to 31.12.19 (AT-5&5A) | Diff | Diff in %
1 | 2 | 3 | 4=(3-2) | 5=(4/2)*100
Primary | 87000 | 85386 | -1614 | -1.855%
Up Primary | 58000 | 54477 | -3523 | -6.074%
NCLP | 0 | 0 | 0 | 0%
Total | 145000 | 139863 | -5137 | -3.543%
1.2) No. of School working days
PY | 152 | 152 | 0 | 0%
UP.PY | 152 | 152 | 0 | 0%
NCLP | 0 | 0 | 0 | 0%
i) Base period 01.04.18 to 31.12.19
Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Diff. | Diff in %
PY | 13224000 | 12978672 | -245328 | -1.855%
UP PY | 8816000 | 8280504 | -535496 | -6.074% |  | 12978672
NCLP | 0 | 0 | 0 | 0% |  | 8280504
Total | 22040000 | 21259176 | -780824 | -3.543%
ii) Base period 01.04.19 to 31.03.20 (As per PAB aaproval = 220 days for Py & U Py )
Stage | No. of Meals as per PAB approval (01.04.19 to 31.3.20) | No. of Meals claimed to have served by the State |  | Bench Mark as per State's claim
PY | 19140000 | 12978672 |  | 67.81%
U PY | 12760000 | 8280504 |  | 64.89%
NCLP | 0 | 0 |  | 0%
Total | 31900000 | 21259176 |  | 66.64%
2. COVERAGE
2.1 Institutions- (Primary) (Source data : Table AT-3A of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | North | 616 | 616 | 0 | 0%
2 | South | 413 | 413 | 0 | 0%
| TOTAL | 1029 | 1029 | 0 | 0%
2.2 Institutions- (Primary with Upper Primary) (Source data : Table AT-3B of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | North | 0 | 0 | 0 | 0
2 | South | 0 | 0 | 0 | 0
| TOTAL | 0 | 0 | 0 | 0
2.2A Institutions- (Upper Primary) (Source data : Table AT-3C of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | North | 258 | 258 | 0 | 0
2 | South | 181 | 181 | 0 | 0%
| TOTAL | 439 | 439 | 0 | 0%
2.3 Coverage Chidlren vs. Enrolment ( Primary) (Source data : Table AT-4 & 5 of AWP&B 2020-21)
Sl. No. | Districts | Enrolment as on 30.9.2019 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | North | 54648 | 50070 | -4578 | -8.377%
2 | South | 41342 | 35316 | -6026 | -14.58%
| TOTAL | 95990 | 85386 | -10604 | -11.05%
2.4 Coverage Chidlren vs. Enrolment ( Upper Primary) (Source data : Table AT- 4A & 5-A of AWP&B 2020-21)
Sl. No. | Districts | Enrolment as on 30.9.2019 | Avg. number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | North | 37622 | 32267 | -5355 | -14.23%
2 | South | 27883 | 22210 | -5673 | -20.35%
| TOTAL | 65505 | 54477 | -11028 | -16.84%
2.5 No. of children ( Primary) (Source data : Table AT-5 of AWP&B 2020-21)
Sl. No. | Districts | No. of children as per PAB Approval for 2019-20 | Avg. number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | North | 51074 | 50070 | -1004 | -1.966%
2 | South | 35926 | 35316 | -610 | -1.698%
| TOTAL | 87000 | 85386 | -1614 | -1.855%
2.6 No. of children ( Upper Primary) (Source data : Table AT-5-A of AWP&B 2020-21)
Sl. No. | Districts | No. of children as per PAB Approval for 2019-20 | Avg. number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | North | 34354 | 32267 | -2087 | -6.075%
2 | South | 23646 | 22210 | -1436 | -6.073%
| TOTAL | 58000 | 54477 | -3523 | -6.074%
2.7 No. of meal to be served and actual number of meal served during 2019-20 (Source data: Table AT-5 & 5A of AWP&B 2020-21)
Sr. No. | District | No of meals to be served during 1.4.19 to 31.12.2019 | No of meal served during 1.4.19 to 31.12.19 | % Meals Served
1 | 2 | 3 | 4 | 5
1 | North | 13224000 | 12978672 | 98.14%
2 | South | 8816000 | 8280504 | 93.93%
| TOTAL | 22040000 | 21259176 | 96.46%
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 1.4.2019 | 108.91 | 108.91 | 0 | 0%
2 | Allocation for 2019-20 | 3828 | 3828 | 0 | 0%
3 | Lifting as on 31.12.2019 | 2763.99 | 2763.99 | 0 | 0%
3.2) District-wise opening balance as on 1.4.2019 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
S.No. | Name of District | Allocation for 2019-20 | Opening Stock as on 1.4.2019 | % of OS on allocation 2019-20
1 | 2 | 3 | 4 | 5
1 | North | 2150.12 | 61.35 | 2.853%
2 | South | 1677.88 | 47.56 | 2.835%
| TOTAL | 3828 | 108.91 | 2.845%
3.3) District-wise unspent balance as on 31.12.2019 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
S.No. | Name of District | Allocation for 2019-20 | Unspent Balance as on 31.12.2019 | % of UB on allocation 2019-20
1 | 2 | 3 | 4 | 5
1 | North | 2150.12 | 253.14 | 11.77%
2 | South | 1677.88 | 79.8 | 4.756%
| TOTAL | 3828 | 332.94 | 8.697%
3.4) Foodgrains Allocation & Lifting
(in MTs)
Allocation | Unspent balance as on 31.03.19 | Lifting upto 31.03.19 | Total Availibility | % Availibility | Bench mark (85%)
3828 | 108.91 | 2763.99 | 2872.9 | 75.05% | 3253.8
Source: Table AT-6 & 6A of AWP&B 2020-21
3.5) District-wise Foodgrains availability as on 31.12.19 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
Sl. No. | District | Allocation | OB as on 1.4.2019 | Lifted from FCI | Total Availibility | % Availibility
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | North | 2150.12 | 61.35 | 1688.56 | 1749.91 | 81.39%
2 | South | 1677.88 | 47.56 | 1075.43 | 1122.99 | 66.93%
| TOTAL | 3828 | 108.91 | 2763.99 | 2872.9 | 75.05%
3.6) Foodgrains Allocation, Lifting (availibility) & Utilisation
Allocation | T. Availibility | % T. Availibility | Utilisation | % Utilisation
3828 | 2872.9 | 75.05% | 2539.96 | 66.35%
3.7) District-wise Utilisation of foodgrains (Source data: Table AT-6 & 6A of AWP&B 2020-21)
Sl. No. | District | Allocation | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5
1 | North | 2150.12 | 1496.77 | 69.61%
2 | South | 1677.88 | 1043.19 | 62.17%
| TOTAL | 3828 | 2539.96 | 66.35%
3.8) Cost of Foodgrains, Payment to FCI
Allocation | Bills submited by FCI | Payment made to FCI | % payment
74.38 | 55.26 | 36.16 | 65.44%
3.9) Payment of cost of foodgrain to FCI
Sl. No. | District | Allocation | Bills raised by FCI | Payment to FCI | Pending Bills | % Bill paid
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | North | 46.01 | 34.18 | 22.37 | 11.81 | 65.45%
2 | South | 28.37 | 21.08 | 13.79 | 7.29 | 65.42%
| TOTAL | 74.38 | 55.26 | 36.16 | 19.1 | 65.44%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 1.4.2019 (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2019-20 | Opening Balance as on 1.4.2019 | % of OB on allocation 2019-20
1 | 2 | 3 | 4 | 5
1 | North | 1167.66 | 15.45 | 1.323%
2 | South | 914.77 | 12.93 | 1.413%
| TOTAL | 2082.43 | 28.38 | 1.363%
4.1.2) District-wise unspent balance as on 31.12.2019 Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2019-20 | Unspent Balance as on 31.12.2019 | % of UB on allocation 2019-20
1 | 2 | 3 | 4 | 5
1 | North | 1167.66 | -58.06 | -4.972%
2 | South | 914.77 | -10.33 | -1.129%
| TOTAL | 2082.43 | -68.39 | -3.284%
4.2) Cooking cost allocation and disbursed to Dists
Allocation | OB as on 1.4.19 | Disbursed to Dist | Total Availibility | % Availibility | Bench mark (75%)
2082.43 | 28.38 | 1297.38 | 1325.76 | 63.66% | 1561.8225
4.3) District-wise Cooking Cost availability (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2019-20 | Opening Balance as on 1.4.2019 | Cooking assistance received | Total Availibility of cooking cost | % Availibility of cooking cost
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | North | 1167.66 | 15.45 | 747.56 | 763.01 | 65.35%
2 | South | 914.77 | 12.93 | 549.82 | 562.75 | 61.52%
| TOTAL | 2082.43 | 28.38 | 1297.38 | 1325.76 | 63.66%
4.4) Cooking Cost Utilisation
Allocation | Total available | % available | Utilisation | % Utilisation
2082.43 | 1325.76 | 63.66% | 1394.15 | 66.95%
4.5) District-wise Utilisation of Cooking cost (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation for 2019-20 | Utilisation of Cooking assistance | % Utilisation
1 | 2 | 3 | 4 | 5
1 | North | 1167.66 | 821.07 | 70.32%
2 | South | 914.77 | 573.08 | 62.65%
| TOTAL | 2082.43 | 1394.15 | 66.95%
5. Reconciliation of Utilisation and Performance during 2019-20 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost (Source data: para 3.7 and 4.5 above)
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | North | 69.61% | 70.32% | 0.7042%
2 | South | 62.17% | 62.65% | 0.4743%
| TOTAL | 66.35% | 66.95% | 0.5961%
5.2 Reconciliation of Food grains utilisation during 2019-20 (Source data: para 2.7 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 01.4.19 to 31.12.19 | Expected consumption of food grains | Actual consumption of food grains | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | North | 12978672 | 1496.7516 | 1496.77 | 100%
2 | South | 8280504 | 1043.1912 | 1043.19 | 100%
| TOTAL | 21259176 | 2539.9428 | 2539.96 | 100%
5.3 Reconciliation of Cooking Cost utilisation during 2019-20 (Source data: para 2.5 and 4.7 above)
(Rs. in Lakh)
Sr. No. | District | No. of Meals served during 01.4.19 to 31.12.19 | Expected expenditure of cooking cost | Actual expenditure of cooking cost | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | North | 12978672 | 814.9944 | 821.07 | 100.7%
2 | South | 8280504 | 568.7841 | 573.08 | 100.8%
| TOTAL | 21259176 | 1383.7785 | 1394.15 | 100.7%
6. ANALYSIS of HONORIUM, To COOK-CUM-HELPERS
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2020-21)
S.No. | Name of District | PAB Approval for 2019-20 | Engaged by State | Not engaged
1 | 2 | 3 | 4 | 5 = (4 - 3)
1 | North | 1598 | 1598 | 0
2 | South | 1131 | 1131 | 0
| TOTAL | 2729 | 2729 | 0
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2020-21)
S.No. | Name of District | Allocation for 2019-20 | Opening Balance as on 1.4.2019 | Amount released | Total availability | % Availibilty
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | North | 159.8 | 21.69 | 94.7 | 116.39 | 72.83%
2 | South | 113.1 | 13.94 | 68.95 | 82.89 | 73.29%
| TOTAL | 272.9 | 35.63 | 163.65 | 199.28 | 73.02%
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers
Refer table AT_8 and AT-8A,AWP&B, 2020-21
S.No. | Name of District | Allocation for 2019-20 | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation
1 | 2 | 3 | 4 | 5 | 6
1 | North | 159.8 | 116.39 | 116.39 | 72.83%
2 | South | 113.1 | 82.89 | 82.89 | 73.29%
| TOTAL | 272.9 | 199.28 | 199.28 | 73.02%
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A, AWP&B, 2020-21)
S.No. | Name of District | Allocation for 2019-20 | Total Availability | Unspent balance as on 31.03.2019 | % of UB as on Allocation 2019-20
1 | 2 | 3 | 4 | 5 | 6
1 | North | 159.8 | 116.39 | 0 | 0%
2 | South | 113.1 | 82.89 | 0 | 0%
| TOTAL | 272.9 | 199.28 | 0 | 0%
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME) | [5 empty] | 0
7.1) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2019-20 | 35.72 | 35.72 | 0 | 0%
2 | Opening Balance as on 1.4.2019 | 18.67 | 18.67 | 0 | 0%
3 | Released during 2019-20 | 5.79 | 5.79 | 0 | 0%
4 | Total Availibility | 24.46 | 24.46 | 0 | 0%
7.2) Utilisation of MME during 2019-20 (Source data: Table AT-10 of AWP&B 2020-21)
|  |  | (Rs. In lakh) | (As on 31.12.19)
Sl. No. | Activity | Allocated for 2019-20 | Total Availibility | Expenditure | Exp as % of allocation
1 | 2 | 3 | 4 | 5 | 6
1 | School Level Expenses | 17.86 | 3.54 | 3.54 | 19.82%
2 | Management, Supervision, Training & Internal Monitoring, External Monitoring & Evaluation | 17.86 | 20.92 | 21.65 | 121.2%
Total |  | 35.72 | 24.46 | 25.19 | 70.52%
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
8.1) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Activity | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2019-20 | 55.79 | 55.79 | 0 | 0%
2 | Opening Balance as on 1.4.2019 | 0 | 0 | 0 | 0%
3 | Released during 2019-20 | 33.47 | 33.47 | 0 | 0%
4 | Total Availibility | 33.47 | 33.47 | 0 | 0%
8.2) Utilisation of TA during 2019-20 (Source data: Table AT-9 of AWP&B 2020-21)
(Rs. In lakh)
Allocated for 2019-20 | Total availibility of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7 | 8= (2-5)
55.79 | 33.47 | 2763.99 | 20.7299 | 20.32 | 0.40992 | 36.42% | 13.15
9. INFRASTRUCTURE DEVELOPMENT DURING 2019-20 (Primary + Upper primary)
Kitchen-cum-Stores
9.1) Releasing details
Releases for Kitchen sheds by GoI as on 31.03.2018
Schools | Installment | Dated | Units | Amount (in lakh)
Primary + Upper Primary |  |  | 0 | 0
|  |  | 0 | 0
| Grand Total |  | 0 | 0
9.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-19 | 0 | 0 | 0 | 0 | 0% | 0%
9.3) Achievement ( under MDM Funds) (Source data: Table AT-11 of AWP&B 2020-21)
Sanctioned by GoI during 2006-07 to 2019-20 |  | Cosntructed upto 31.12.19 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
0 | 0 | 0 | 0 | 0% | 0%
10. Kitchen Devices
10.1) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-19 | 0 | 0 | 0 | 0 | 0% | 0%
2014-15 (Replacement) | 1521 | 76.05 | 1521 | 76.05 | 0% | 0%
10.2) Achievement ( under MDM Funds) (Source data: Table AT-12 of AWP&B 2020-21)
Sactioned during 2006-07 to 2019-20 |  | Achievement (C+IP) upto 31.12.2019 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
0 | 0 | 0 | 0 | 0% | 0%
1521 (Replacement) | 76.05 | 0 | 0 | 0 | 0
Benchmark (85%)
100%
68%

## Sheet3
GOA State Data for AWPB 2020-21 (Data From Apr-19 to Dec-19)
Component | Allocatlion | MIS | AWP&B | MIS | AWP&B
Schools | 1468 | 1454 | 1468 | 99.05% | 100%
Enrolment | 160742 | 160742 | 161495 | 100% | 100.5%
CCH | 2729 | 2483 | 2729 | 90.99% | 100%
Working days | 152 | 152 | 152 | 100% | 100%
Meal served | 22040000 | 18227566 | 21259176 | 82.7% | 96.46%
Cooking Cost Exp. (in Lakhs) | 2082.43 | 566.72 | 1394.15 | 27.21% | 66.95%
Food Grains (in MT) | 3828 | 1021.64 | 2539.96 | 26.69% | 66.35%
CCH Hon. (in Lakhs) | 272.9 | 205.07 | 199.28 | 75.14% | 73.02%
Component | MIS | AWP&B
Schools | 99.05% | 100%
Enrolment | 100% | 100%
CCH | 90.99% | 100%
Working days | 100% | 100%
Meal served | 82.7% | 96.46%
Cooking Cost Exp. (in Lakhs) | 27.21% | 66.95%
Food Grains (in MT) | 26.69% | 66.35%
CCH Hon. (in Lakhs) | 75.14% | 73.02%

## Sheet1
Institution | 10
Children | 9.6
Working Days | 9.7
Foodgrain Util. | 9.2
Payment to FCI | 10
Cooking Cost | 9.3
Payment to CCH | 8.3
MME | 9.9
Kitchen Shed | 4.5
Kitchen Devices | 10
TA | 9.9
Monthly D.E | 10
Annual D.E | 10
School Health | 9.8
Drinking Water | 9.9
Toilet Facility | 9.9
Fund flow | 10
|  | Name of States | PAB Approval | Coverage | %age
|  | Goa | 1479 | 1473 | 99.59%
|  | Gujarat | 34307 | 34307 | 100%
|  | Kerala | 12327 | 12341 | 100.1%
|  | Goa | 99.59%
|  | Gujarat | 100%
|  | Kerala | 100.1%

## Sheet2
Component | PAB-Approval (Target) | Achievement | % Achievement
Institutions | 1479 | 1473 | 92%
Children | 145500 | 141464 | 88%
Working Days | 220 | 221 | 99%
Food Grain Utilisation (in MTs) | 3844.52 | 3735.61 | 87%
Cooking Cost (Rs. in Lacs) | 2103.8 | 2050.33 | 85%
CCH Engaged | 2777 | 2729 | 97%
CCH Honorarieum (Rs. in Lacs) | 277.7 | 242.07 | 94%
TA (Rs. in Lacs) | 28.84 | 28.84 | 87%
MME (Rs. in Lacs) | 60 | 41.33 | 100%
Kitchen cum Store (KS) | 0 | 0 | 100%
Kitchen Devices (KD) | 1521 | 0 | 100%
No. of Children's Health Check-up | 161693 | 161693 | 64%
Annual Data Entry | 1473 | 1458 | 13%
Monthly Data Entry | 1473 | 1458 | 0%
Component | PAB-Approval (Target) | Achievement | % Achievement
Institutions | 1479 | 1473 | 99.59%
Children | 145500 | 141464 | 97.23%
Working Days | 220 | 221 | 100.5%
Food Grain Utilisation (in MTs) | 3844.52 | 3735.61 | 97.17%
Cooking Cost (Rs. in Lacs) | 2103.8 | 2050.33 | 97.46%
CCH Engaged | 2777 | 2729 | 98.27%
CCH Honorarieum (Rs. in Lacs) | 277.7 | 242.07 | 87.17%
TA (Rs. in Lacs) | 28.84 | 28.84 | 100%
MME (Rs. in Lacs) | 60 | 41.33 | 68.88%
Kitchen cum Store (KS) | 0 | 0 | #DIV/0!
Kitchen Devices (KD) | 1521 | 0 | 0%
No. of Children's Health Check-up | 161693 | 161693 | 100%
Annual Data Entry | 1473 | 1458 | 98.98%
Monthly Data Entry | 1473 | 1458 | 98.98%
Component | PAB-Approval (Target) | Achievement | % Achievement
Institutions (School) | 12341 | 12341 | 100%
Children | 2654807 | 2578727 | 97.13%
Working Days | 210 | 200 | 95.24%
Food Grain Utilisation (in MTs) | 67013.58 | 61140.12 | 91.24%
Cooking Cost (Rs. in Lacs) | 45568.2 | 41131.12 | 90.26%
CCH Engaged | 17673 | 14389 | 81.42%
CCH Honorarieum (Rs. in Lacs) | 14495.91 | 12345.27 | 85.16%
TA (Rs. in Lacs) | 462.03 | 462.04 | 100%
MME (Rs. in Lacs) | 375.29 | 356.23 | 94.92%
Kitchen cum Store (KS) | 5481 | 2450 | 44.7%
Kitchen Devices (KD) | 13831 | 13831 | 100%
No. of Children's Health Check-up | 2728751 | 2673996 | 97.99%
Annual Data Entry | 12341 | 12330 | 99.91%
Monthly Data Entry | 12341 | 11813 | 95.72%
Component | PAB-Approval (Target) | Achievement | % Achievement
Institutions (School) | 34307 | 34307 | 100%
Children | 4397240 | 4299029 | 97.77%
Working Days | 248 | 243 | 97.98%
Food Grain Utilisation (in MTs) | 130433.95 | 123851.05 | 94.95%
Cooking Cost (Rs. in Lacs) | 55522.11 | 50693.08 | 91.3%
CCH Engaged | 96329 | 96329 | 100%
CCH Honorarieum (Rs. in Lacs) | 9632.9 | 8853.64 | 91.91%
TA (Rs. in Lacs) | 951.54 | 889.81 | 93.51%
MME (Rs. in Lacs) | 790.62 | 319.33 | 40.39%
Kitchen cum Store | 25077 | 24308 | 96.93%
Kitchen Devices | 33540 | 33540 | 100%
No. of Children's Health Check-up | 5488319 | 5056002 | 92.12%
Annual Data Entry | 34307 | 34307 | 100%
Monthly Data Entry | 34307 | 31868 | 92.89%
32934.72