## Telangana
Government of India
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2020-21
State : Telangana
Part-D: ANALYSIS SHEET
Section-A : REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2019-20 (1.4.2019 to 31.12.2019)
1. Calculation of Bench mark for utilisation.
1.1) No. of children
Stage | MDM PAB Approval for 2019-20 | Average number of children availed MDM during 2019-20 | Diff | Diff in %
Primary | 1075656 | 997990 | -77666 | -7.22%
Up Pry | 654000 | 572084 | -81916 | -12.53%
NCLP | 1765 | 1270 | -495 | 0%
Total | 1731421 | 1571344 | -160077 | -9.245%
1.2) No. of School working days
PY | 158 | 158 | 0 | 0%
UP.PY | 158 | 158 | 0 | 0%
NCLP | 214 | 214 | 0 | 0%
1.3) Number of meals served vis-à-vis PAB approval during 2019-20
Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Diff. | Diff in %
PY | 169953648 | 157635020 | -12318628 | -7.248%
UP PY | 103332000 | 90389272 | -12942728 | -12.53%
NCLP | 377710 | 271780 | -105930 | 0%
Total | 273663358 | 248296072 | -25367286 | -9.27%
2. COVERAGE
2.1 Institutions- (Primary) (Source data : Table AT-3A of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | ADILABAD | 936 | 929 | 7 | 0.7479%
2 | BHADRADRI | 1036 | 1029 | 7 | 0.6757%
3 | HYDERABAD | 611 | 575 | 36 | 5.892%
4 | JAGITIAL | 516 | 487 | 29 | 5.62%
5 | JANAGOAN | 362 | 319 | 43 | 11.88%
6 | JAYASHANKAR | 320 | 298 | 22 | 6.875%
7 | JOGULAMBA | 289 | 287 | 2 | 0.692%
8 | KAMAREDDY | 701 | 681 | 20 | 2.853%
9 | KARIMNAGAR | 425 | 398 | 27 | 6.353%
10 | KHAMMAM | 841 | 826 | 15 | 1.784%
11 | KOMRAM BHEEM | 863 | 840 | 23 | 2.665%
12 | MAHABUBABAD | 765 | 668 | 97 | 12.68%
13 | MAHABUBNAGAR | 647 | 613 | 34 | 5.255%
14 | MANCHERIAL | 566 | 551 | 15 | 2.65%
15 | MEDAK | 627 | 609 | 18 | 2.871%
16 | MEDCHAL | 375 | 371 | 4 | 1.067%
17 | MULUGU | 346 | 322 | 24 | 6.936%
18 | NAGARKURNOOL | 604 | 566 | 38 | 6.291%
19 | NALGONDA | 1162 | 1035 | 127 | 10.93%
20 | NARAYANPET | 345 | 324 | 21 | 6.087%
21 | NIRMAL | 570 | 555 | 15 | 2.632%
22 | NIZAMABAD | 797 | 791 | 6 | 0.7528%
23 | PEDDAPALLI | 360 | 330 | 30 | 8.333%
24 | RAJANNA | 341 | 321 | 20 | 5.865%
25 | RANGA REDDY | 902 | 868 | 34 | 3.769%
26 | SANGAREDDY | 872 | 858 | 14 | 1.606%
27 | SIDDIPET | 638 | 607 | 31 | 4.859%
28 | SURYAPET | 701 | 672 | 29 | 4.137%
29 | VIKARABAD | 756 | 732 | 24 | 3.175%
30 | WANAPARTHY | 361 | 346 | 15 | 4.155%
31 | WARANGAL (R) | 459 | 386 | 73 | 15.9%
32 | WARANGAL (U) | 343 | 324 | 19 | 5.539%
33 | YADADRI | 476 | 448 | 28 | 5.882%
| TOTAL | 19913 | 18966 | 947 | 4.756%
2.2 Institutions- (Primary with Upper Primary) (Source data : Table AT-3B of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | ADILABAD | 116 | 116 | 0 | 0
2 | BHADRADRI | 168 | 168 | 0 | 0
3 | HYDERABAD | 51 | 34 | -17 | 0
4 | JAGITIAL | 85 | 85 | 0 | 0
5 | JANAGOAN | 70 | 70 | 0 | 0
6 | JAYASHANKAR | 44 | 44 | 0 | 0
7 | JOGULAMBA | 88 | 88 | 0 | 0
8 | KAMAREDDY | 135 | 135 | 0 | 0
9 | KARIMNAGAR | 77 | 77 | 0 | 0
10 | KHAMMAM | 194 | 194 | 0 | 0
11 | KOMRAM BHEEM | 107 | 107 | 0 | 0
12 | MAHABUBABAD | 123 | 123 | 0 | 0
13 | MAHABUBNAGAR | 100 | 100 | 0 | 0
14 | MANCHERIAL | 97 | 97 | 0 | 0
15 | MEDAK | 130 | 130 | 0 | 0
16 | MEDCHAL | 33 | 33 | 0 | 0
17 | MULUGU | 44 | 44 | 0 | 0
18 | NAGARKURNOOL | 131 | 131 | 0 | 0
19 | NALGONDA | 135 | 135 | 0 | 0
20 | NARAYANPET | 86 | 86 | 0 | 0
21 | NIRMAL | 93 | 93 | 0 | 0
22 | NIZAMABAD | 141 | 141 | 0 | 0
23 | PEDDAPALLI | 85 | 85 | 0 | 0
24 | RAJANNA | 38 | 38 | 0 | 0
25 | RANGA REDDY | 197 | 197 | 0 | 0
26 | SANGAREDDY | 195 | 195 | 0 | 0
27 | SIDDIPET | 114 | 114 | 0 | 0
28 | SURYAPET | 82 | 82 | 0 | 0
29 | VIKARABAD | 113 | 113 | 0 | 0
30 | WANAPARTHY | 58 | 58 | 0 | 0
31 | WARANGAL (R) | 81 | 81 | 0 | 0
32 | WARANGAL (U) | 62 | 62 | 0 | 0
33 | YADADRI | 63 | 63 | 0 | 0
| TOTAL | 3336 | 3319 | -17 | 0
2.2A Institutions- (Upper Primary) (Source data : Table AT-3C of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | ADILABAD | 111 | 111 | 0 | 0%
2 | BHADRADRI | 118 | 118 | 0 | 0%
3 | HYDERABAD | 297 | 257 | -40 | -13.47%
4 | JAGITIAL | 200 | 200 | 0 | 0%
5 | JANAGOAN | 122 | 122 | 0 | 0%
6 | JAYASHANKAR | 75 | 75 | 0 | 0%
7 | JOGULAMBA | 87 | 87 | 0 | 0%
8 | KAMAREDDY | 192 | 192 | 0 | 0%
9 | KARIMNAGAR | 166 | 166 | 0 | 0%
10 | KHAMMAM | 221 | 221 | 0 | 0%
11 | KOMRAM BHEEM | 62 | 62 | 0 | 0%
12 | MAHABUBABAD | 111 | 111 | 0 | 0%
13 | MAHABUBNAGAR | 144 | 144 | 0 | 0%
14 | MANCHERIAL | 121 | 121 | 0 | 0%
15 | MEDAK | 152 | 152 | 0 | 0%
16 | MEDCHAL | 110 | 110 | 0 | 0%
17 | MULUGU | 43 | 43 | 0 | 0%
18 | NAGARKURNOOL | 135 | 135 | 0 | 0%
19 | NALGONDA | 260 | 260 | 0 | 0%
20 | NARAYANPET | 82 | 82 | 0 | 0%
21 | NIRMAL | 119 | 119 | 0 | 0%
22 | NIZAMABAD | 276 | 276 | 0 | 0%
23 | PEDDAPALLI | 114 | 114 | 0 | 0%
24 | RAJANNA | 121 | 121 | 0 | 0%
25 | RANGA REDDY | 255 | 255 | 0 | 0%
26 | SANGAREDDY | 219 | 219 | 0 | 0%
27 | SIDDIPET | 242 | 242 | 0 | 0%
28 | SURYAPET | 197 | 197 | 0 | 0%
29 | VIKARABAD | 188 | 188 | 0 | 0%
30 | WANAPARTHY | 105 | 105 | 0 | 0%
31 | WARANGAL (R) | 140 | 140 | 0 | 0%
32 | WARANGAL (U) | 138 | 138 | 0 | 0%
33 | YADADRI | 161 | 161 | 0 | 0%
| TOTAL | 5084 | 5044 | -40 | -0.7868%
2.3 Coverage Chidlren vs. Enrolment ( Primary) (Source data : Table AT-4 & 5 of AWP&B 2020-21)
Sl. No. | Districts | Enrolment as on 30.9.2019 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | ADILABAD | 39437 | 35166 | -4271 | -10.83%
2 | BHADRADRI | 41148 | 36642 | -4506 | -10.95%
3 | HYDERABAD | 86919 | 75437 | -11482 | -13.21%
4 | JAGITIAL | 27174 | 23686 | -3488 | -12.84%
5 | JANAGOAN | 16195 | 14245 | -1950 | -12.04%
6 | JAYASHANKAR | 11731 | 10354 | -1377 | -11.74%
7 | JOGULAMBA | 35055 | 31006 | -4049 | -11.55%
8 | KAMAREDDY | 43898 | 39317 | -4581 | -10.44%
9 | KARIMNAGAR | 19095 | 16796 | -2299 | -12.04%
10 | KHAMMAM | 44986 | 38543 | -6443 | -14.32%
11 | KOMRAM BHEEM | 28826 | 25115 | -3711 | -12.87%
12 | MAHABUBABAD | 26690 | 23612 | -3078 | -11.53%
13 | MAHABUBNAGAR | 39745 | 35588 | -4157 | -10.46%
14 | MANCHERIAL | 21356 | 19250 | -2106 | -9.861%
15 | MEDAK | 39140 | 33833 | -5307 | -13.56%
16 | MEDCHAL | 40294 | 34870 | -5424 | -13.46%
17 | MULUGU | 11202 | 10054 | -1148 | -10.25%
18 | NAGARKURNOOL | 32549 | 29335 | -3214 | -9.874%
19 | NALGONDA | 52013 | 46354 | -5659 | -10.88%
20 | NARAYANPET | 32619 | 27504 | -5115 | -15.68%
21 | NIRMAL | 27319 | 24041 | -3278 | -12%
22 | NIZAMABAD | 53474 | 47405 | -6069 | -11.35%
23 | PEDDAPALLI | 14850 | 13283 | -1567 | -10.55%
24 | RAJANNA | 17577 | 15830 | -1747 | -9.939%
25 | RANGA REDDY | 75011 | 63197 | -11814 | -15.75%
26 | SANGAREDDY | 58769 | 50988 | -7781 | -13.24%
27 | SIDDIPET | 37785 | 33583 | -4202 | -11.12%
28 | SURYAPET | 31176 | 26113 | -5063 | -16.24%
29 | VIKARABAD | 46456 | 41889 | -4567 | -9.831%
30 | WANAPARTHY | 23629 | 20470 | -3159 | -13.37%
31 | WARANGAL (R) | 17998 | 16100 | -1898 | -10.55%
32 | WARANGAL (U) | 22485 | 20410 | -2075 | -9.228%
33 | YADADRI | 19569 | 17674 | -1895 | -9.684%
| TOTAL | 1136170 | 997690 | -138480 | -12.19%
2.4 Coverage Chidlren vs. Enrolment ( Up Pry) (Source data : Table AT- 4A & 5-A of AWP&B 2020-21)
Sl. No. | Districts | Enrolment as on 30.9.2019 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | ADILABAD | 16268 | 14905 | -1363 | -8.378%
2 | BHADRADRI | 17433 | 14530 | -2903 | -16.65%
3 | HYDERABAD | 44303 | 37691 | -6612 | -14.92%
4 | JAGITIAL | 18828 | 16294 | -2534 | -13.46%
5 | JANAGOAN | 12343 | 10803 | -1540 | -12.48%
6 | JAYASHANKAR | 6205 | 5468 | -737 | -11.88%
7 | JOGULAMBA | 17876 | 15663 | -2213 | -12.38%
8 | KAMAREDDY | 24488 | 20907 | -3581 | -14.62%
9 | KARIMNAGAR | 14439 | 12387 | -2052 | -14.21%
10 | KHAMMAM | 25259 | 21397 | -3862 | -15.29%
11 | KOMRAM BHEEM | 10606 | 9496 | -1110 | -10.47%
12 | MAHABUBABAD | 13649 | 12153 | -1496 | -10.96%
13 | MAHABUBNAGAR | 23876 | 20028 | -3848 | -16.12%
14 | MANCHERIAL | 15417 | 13089 | -2328 | -15.1%
15 | MEDAK | 24398 | 21175 | -3223 | -13.21%
16 | MEDCHAL | 25809 | 22619 | -3190 | -12.36%
17 | MULUGU | 4366 | 3823 | -543 | -12.44%
18 | NAGARKURNOOL | 19248 | 16758 | -2490 | -12.94%
19 | NALGONDA | 31645 | 28265 | -3380 | -10.68%
20 | NARAYANPET | 18395 | 16106 | -2289 | -12.44%
21 | NIRMAL | 14190 | 12208 | -1982 | -13.97%
22 | NIZAMABAD | 32003 | 27913 | -4090 | -12.78%
23 | PEDDAPALLI | 11140 | 9761 | -1379 | -12.38%
24 | RAJANNA | 10473 | 8972 | -1501 | -14.33%
25 | RANGA REDDY | 46868 | 39683 | -7185 | -15.33%
26 | SANGAREDDY | 35028 | 30972 | -4056 | -11.58%
27 | SIDDIPET | 26301 | 23659 | -2642 | -10.05%
28 | SURYAPET | 18177 | 15176 | -3001 | -16.51%
29 | VIKARABAD | 28193 | 23925 | -4268 | -15.14%
30 | WANAPARTHY | 13472 | 11917 | -1555 | -11.54%
31 | WARANGAL (R) | 10194 | 9132 | -1062 | -10.42%
32 | WARANGAL (U) | 13794 | 11986 | -1808 | -13.11%
33 | YADADRI | 15102 | 13223 | -1879 | -12.44%
| TOTAL | 659786 | 572084 | -87702 | -13.29%
2.5 No. of children ( Primary) (Source data : Table AT-5 of AWP&B 2020-21)
Sl. No. | Districts | No. of children as per PAB Approval for 2019-20 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | ADILABAD | 36615 | 35166 | -1449 | -3.957%
2 | BHADRADRI | 39180 | 36642 | -2538 | -6.478%
3 | HYDERABAD | 78114 | 75437 | -2677 | -3.427%
4 | JAGITIAL | 26197 | 23686 | -2511 | -9.585%
5 | JANAGOAN | 16042 | 14245 | -1797 | -11.2%
6 | JAYASHANKAR | 11660 | 10354 | -1306 | -11.2%
7 | JOGULAMBA | 33446 | 31006 | -2440 | -7.295%
8 | KAMAREDDY | 41255 | 39317 | -1938 | -4.698%
9 | KARIMNAGAR | 18125 | 16796 | -1329 | -7.332%
10 | KHAMMAM | 42174 | 38543 | -3631 | -8.61%
11 | KOMRAM BHEEM | 28340 | 25115 | -3225 | -11.38%
12 | MAHABUBABAD | 26578 | 23612 | -2966 | -11.16%
13 | MAHABUBNAGAR | 36875 | 35588 | -1287 | -3.49%
14 | MANCHERIAL | 20934 | 19250 | -1684 | -8.044%
15 | MEDAK | 36963 | 33833 | -3130 | -8.468%
16 | MEDCHAL | 38020 | 34870 | -3150 | -8.285%
17 | MULUGU | 10374 | 10054 | -320 | -3.085%
18 | NAGARKURNOOL | 32851 | 29335 | -3516 | -10.7%
19 | NALGONDA | 49323 | 46354 | -2969 | -6.02%
20 | NARAYANPET | 31697 | 27504 | -4193 | -13.23%
21 | NIRMAL | 26599 | 24041 | -2558 | -9.617%
22 | NIZAMABAD | 49873 | 47405 | -2468 | -4.949%
23 | PEDDAPALLI | 14076 | 13283 | -793 | -5.634%
24 | RAJANNA | 15979 | 15830 | -149 | -0.9325%
25 | RANGA REDDY | 69199 | 63197 | -6002 | -8.674%
26 | SANGAREDDY | 55294 | 50988 | -4306 | -7.787%
27 | SIDDIPET | 35277 | 33583 | -1694 | -4.802%
28 | SURYAPET | 30102 | 26113 | -3989 | -13.25%
29 | VIKARABAD | 45599 | 41889 | -3710 | -8.136%
30 | WANAPARTHY | 22246 | 20470 | -1776 | -7.983%
31 | WARANGAL (R) | 17465 | 16100 | -1365 | -7.816%
32 | WARANGAL (U) | 21180 | 20410 | -770 | -3.636%
33 | YADADRI | 18004 | 17674 | -330 | -1.833%
| TOTAL | 1075656 | 997690 | -77966 | -7.248%
2.6 No. of children ( Upper Primary) (Source data : Table AT-5-A of AWP&B 2020-21)
Sl. No. | Districts | No. of children as per PAB Approval for 2019-20 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | ADILABAD | 15634 | 14905 | -729 | -4.663%
2 | BHADRADRI | 18059 | 14530 | -3529 | -19.54%
3 | HYDERABAD | 41556 | 37691 | -3865 | -9.301%
4 | JAGITIAL | 18534 | 16294 | -2240 | -12.09%
5 | JANAGOAN | 12228 | 10803 | -1425 | -11.65%
6 | JAYASHANKAR | 6856 | 5468 | -1388 | -20.25%
7 | JOGULAMBA | 17265 | 15663 | -1602 | -9.279%
8 | KAMAREDDY | 24685 | 20907 | -3778 | -15.3%
9 | KARIMNAGAR | 14924 | 12387 | -2537 | -17%
10 | KHAMMAM | 25154 | 21397 | -3757 | -14.94%
11 | KOMRAM BHEEM | 11016 | 9496 | -1520 | -13.8%
12 | MAHABUBABAD | 14105 | 12153 | -1952 | -13.84%
13 | MAHABUBNAGAR | 25808 | 20028 | -5780 | -22.4%
14 | MANCHERIAL | 16119 | 13089 | -3030 | -18.8%
15 | MEDAK | 24655 | 21175 | -3480 | -14.11%
16 | MEDCHAL | 25277 | 22619 | -2658 | -10.52%
17 | MULUGU | 4890 | 3823 | -1067 | -21.82%
18 | NAGARKURNOOL | 20188 | 16758 | -3430 | -16.99%
19 | NALGONDA | 30306 | 28265 | -2041 | -6.735%
20 | NARAYANPET | 17022 | 16106 | -916 | -5.381%
21 | NIRMAL | 14251 | 12208 | -2043 | -14.34%
22 | NIZAMABAD | 30947 | 27913 | -3034 | -9.804%
23 | PEDDAPALLI | 11465 | 9761 | -1704 | -14.86%
24 | RAJANNA | 9911 | 8972 | -939 | -9.474%
25 | RANGA REDDY | 45257 | 39683 | -5574 | -12.32%
26 | SANGAREDDY | 33679 | 30972 | -2707 | -8.038%
27 | SIDDIPET | 25311 | 23659 | -1652 | -6.527%
28 | SURYAPET | 18104 | 15176 | -2928 | -16.17%
29 | VIKARABAD | 27393 | 23925 | -3468 | -12.66%
30 | WANAPARTHY | 14114 | 11917 | -2197 | -15.57%
31 | WARANGAL (R) | 10218 | 9132 | -1086 | -10.63%
32 | WARANGAL (U) | 13421 | 11986 | -1435 | -10.69%
33 | YADADRI | 15648 | 13223 | -2425 | -15.5%
| TOTAL | 654000 | 572084 | -81916 | -12.53%
2.7 Number of meal to be served and actual number of meal served during 2019-20 (Source data: Table AT-5 & 5A of AWP&B 2020-21)
Sr. No. | District | No of meals to be served during 2019-20 | No of meal served during 2019-20 | % Meals Served
1 | 2 | 3 | 4 | 5
1 | ADILABAD | 8255342 | 7911218 | 95.83%
2 | BHADRADRI | 9129148 | 8163500 | 89.42%
3 | HYDERABAD | 18907860 | 17874224 | 94.53%
4 | JAGITIAL | 7067498 | 6316840 | 89.38%
5 | JANAGOAN | 4466660 | 3957584 | 88.6%
6 | JAYASHANKAR | 2925528 | 2499876 | 85.45%
7 | JOGULAMBA | 8012338 | 7373702 | 92.03%
8 | KAMAREDDY | 10463246 | 9554340 | 91.31%
9 | KARIMNAGAR | 5221742 | 4610914 | 88.3%
10 | KHAMMAM | 10681694 | 9510966 | 89.04%
11 | KOMRAM BHEEM | 6218248 | 5468538 | 87.94%
12 | MAHABUBABAD | 6467504 | 5683612 | 87.88%
13 | MAHABUBNAGAR | 9979884 | 8793534 | 88.11%
14 | MANCHERIAL | 5854374 | 5109562 | 87.28%
15 | MEDAK | 9735644 | 8691264 | 89.27%
16 | MEDCHAL | 10000926 | 9083262 | 90.82%
17 | MULUGU | 2419844 | 2200912 | 90.95%
18 | NAGARKURNOOL | 8385512 | 7285048 | 86.88%
19 | NALGONDA | 12581382 | 11789802 | 93.71%
20 | NARAYANPET | 7697602 | 6890380 | 89.51%
21 | NIRMAL | 6454300 | 5727342 | 88.74%
22 | NIZAMABAD | 12844246 | 11964658 | 93.15%
23 | PEDDAPALLI | 4035478 | 3640952 | 90.22%
24 | RAJANNA | 4090620 | 3918716 | 95.8%
25 | RANGA REDDY | 18084048 | 16255040 | 89.89%
26 | SANGAREDDY | 14057734 | 12949680 | 92.12%
27 | SIDDIPET | 9572904 | 9044236 | 94.48%
28 | SURYAPET | 7616548 | 6523662 | 85.65%
29 | VIKARABAD | 11532736 | 10398612 | 90.17%
30 | WANAPARTHY | 5744880 | 5117146 | 89.07%
31 | WARANGAL (R) | 4373914 | 3986656 | 91.15%
32 | WARANGAL (U) | 5466958 | 5118568 | 93.63%
33 | YADADRI | 5317016 | 4881726 | 91.81%
| TOTAL | 273663358 | 248296072 | 90.73%
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 1.4.2019 | 1842.82 | 1842.82 | 0 | 0%
2 | Allocation for 2019-20 | 46350.25 | 46350.25 | 0 | 0%
3.2) District-wise opening balance as on 1.4.2019 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
S.No. | Name of District | Allocation | Opening Stock as on 01.04.2019 | % of OS on allocation
1 | 2 | 3 | 4 | 5
1 | ADILABAD | 1428.83 | 55.97 | 3.917%
2 | BHADRADRI | 1464.29 | 56.17 | 3.836%
3 | HYDERABAD | 3285.93 | 127.96 | 3.894%
4 | JAGITIAL | 1204 | 47.12 | 3.914%
5 | JANAGOAN | 762.87 | 33.91 | 4.445%
6 | JAYASHANKAR | 462.39 | 16.51 | 3.571%
7 | JOGULAMBA | 1357.19 | 59.13 | 4.357%
8 | KAMAREDDY | 1768.4 | 63.25 | 3.577%
9 | KARIMNAGAR | 885.94 | 38.12 | 4.303%
10 | KHAMMAM | 1768.83 | 74.7 | 4.223%
11 | KOMRAM BHEEM | 976.07 | 42.66 | 4.371%
12 | MAHABUBABAD | 1048.16 | 41.13 | 3.924%
13 | MAHABUBNAGAR | 1638.08 | 63.32 | 3.866%
14 | MANCHERIAL | 972.58 | 44.6 | 4.586%
15 | MEDAK | 1638.7 | 68.12 | 4.157%
16 | MEDCHAL | 1719.64 | 62.16 | 3.615%
17 | MULUGU | 393.07 | 15.88 | 4.04%
18 | NAGARKURNOOL | 1359.39 | 52.19 | 3.839%
19 | NALGONDA | 2216.31 | 84.67 | 3.82%
20 | NARAYANPET | 1289.36 | 54.51 | 4.228%
21 | NIRMAL | 1054.77 | 39.36 | 3.732%
22 | NIZAMABAD | 2239.83 | 90.12 | 4.024%
23 | PEDDAPALLI | 699.28 | 34.44 | 4.925%
24 | RAJANNA | 730.59 | 29.71 | 4.067%
25 | RANGA REDDY | 3065.96 | 123.01 | 4.012%
26 | SANGAREDDY | 2433.29 | 89.01 | 3.658%
27 | SIDDIPET | 1728.59 | 75.16 | 4.348%
28 | SURYAPET | 1219.69 | 53.01 | 4.346%
29 | VIKARABAD | 1940.35 | 73.11 | 3.768%
30 | WANAPARTHY | 956.91 | 38.12 | 3.984%
31 | WARANGAL (R) | 743.32 | 25.16 | 3.385%
32 | WARANGAL (U) | 958.12 | 35.1 | 3.663%
33 | YADADRI | 939.52 | 35.43 | 3.771%
| TOTAL | 46350.25 | 1842.82 | 3.976%
3.3) District-wise unspent balance as on 31.03.2020 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
S.No. | Name of District | Allocation | Unspent Balance as on 31.03.2020 | % of UB on allocation
1 | 2 | 3 | 4 | 5
1 | ADILABAD | 1428.83 | 162.04 | 11.34%
2 | BHADRADRI | 1464.29 | 161.45 | 11.03%
3 | HYDERABAD | 3285.93 | 375.12 | 11.42%
4 | JAGITIAL | 1204 | 140.02 | 11.63%
5 | JANAGOAN | 762.87 | 93.23 | 12.22%
6 | JAYASHANKAR | 462.39 | 51.45 | 11.13%
7 | JOGULAMBA | 1357.19 | 161.31 | 11.89%
8 | KAMAREDDY | 1768.4 | 195.49 | 11.05%
9 | KARIMNAGAR | 885.94 | 106.85 | 12.06%
10 | KHAMMAM | 1768.83 | 207.38 | 11.72%
11 | KOMRAM BHEEM | 976.07 | 114.47 | 11.73%
12 | MAHABUBABAD | 1048.16 | 118.95 | 11.35%
13 | MAHABUBNAGAR | 1638.08 | 187.49 | 11.45%
14 | MANCHERIAL | 972.58 | 119.58 | 12.3%
15 | MEDAK | 1638.7 | 193.62 | 11.82%
16 | MEDCHAL | 1719.64 | 194.23 | 11.29%
17 | MULUGU | 393.07 | 44.51 | 11.32%
18 | NAGARKURNOOL | 1359.39 | 155.45 | 11.44%
19 | NALGONDA | 2216.31 | 254.06 | 11.46%
20 | NARAYANPET | 1289.36 | 152.74 | 11.85%
21 | NIRMAL | 1054.77 | 118.79 | 11.26%
22 | NIZAMABAD | 2239.83 | 258.44 | 11.54%
23 | PEDDAPALLI | 699.28 | 88.68 | 12.68%
24 | RAJANNA | 730.59 | 85.22 | 11.66%
25 | RANGA REDDY | 3065.96 | 357.87 | 11.67%
26 | SANGAREDDY | 2433.29 | 274.91 | 11.3%
27 | SIDDIPET | 1728.59 | 208.79 | 12.08%
28 | SURYAPET | 1219.69 | 145.87 | 11.96%
29 | VIKARABAD | 1940.35 | 220.63 | 11.37%
30 | WANAPARTHY | 956.91 | 110.98 | 11.6%
31 | WARANGAL (R) | 743.32 | 81.64 | 10.98%
32 | WARANGAL (U) | 958.12 | 108.1 | 11.28%
33 | YADADRI | 939.52 | 108.42 | 11.54%
| TOTAL | 46350.25 | 5357.78 | 11.56%
3.4) Foodgrains Allocation & Lifting
(in MTs)
Allocation | Opening balance as on 01.4.19 | Lifting upto 31.03.2020 | Total Availibility | % Availibility
46350.25 | 1842.82 | 32877.62 | 34720.44 | 74.91%
Source: Table AT-6 & 6A of AWP&B 2020-21
3.5) District-wise Foodgrains availability as on 31.03.2020 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
Sl. No. | District | Allocation | OB as on 01.04.2019 | Lifted from FCI | Total Availibility | % Availibility
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | ADILABAD | 1428.83 | 55.97 | 1014.94 | 1070.91 | 74.95%
2 | BHADRADRI | 1464.29 | 56.17 | 1040.33 | 1096.5 | 74.88%
3 | HYDERABAD | 3285.93 | 127.96 | 2332.34 | 2460.3 | 74.87%
4 | JAGITIAL | 1204 | 47.12 | 853.31 | 900.43 | 74.79%
5 | JANAGOAN | 762.87 | 33.91 | 540.42 | 574.33 | 75.29%
6 | JAYASHANKAR | 462.39 | 16.51 | 328.12 | 344.63 | 74.53%
7 | JOGULAMBA | 1357.19 | 59.13 | 963.28 | 1022.41 | 75.33%
8 | KAMAREDDY | 1768.4 | 63.25 | 1254.79 | 1318.04 | 74.53%
9 | KARIMNAGAR | 885.94 | 38.12 | 627.68 | 665.8 | 75.15%
10 | KHAMMAM | 1768.83 | 74.7 | 1254.84 | 1329.54 | 75.16%
11 | KOMRAM BHEEM | 976.07 | 42.66 | 693.69 | 736.35 | 75.44%
12 | MAHABUBABAD | 1048.16 | 41.13 | 743.83 | 784.96 | 74.89%
13 | MAHABUBNAGAR | 1638.08 | 63.32 | 1162.05 | 1225.37 | 74.81%
14 | MANCHERIAL | 972.58 | 44.6 | 689.34 | 733.94 | 75.46%
15 | MEDAK | 1638.7 | 68.12 | 1161.91 | 1230.03 | 75.06%
16 | MEDCHAL | 1719.64 | 62.16 | 1219.09 | 1281.25 | 74.51%
17 | MULUGU | 393.07 | 15.88 | 279.34 | 295.22 | 75.11%
18 | NAGARKURNOOL | 1359.39 | 52.19 | 964.27 | 1016.46 | 74.77%
19 | NALGONDA | 2216.31 | 84.67 | 1571.66 | 1656.33 | 74.73%
20 | NARAYANPET | 1289.36 | 54.51 | 914.5 | 969.01 | 75.15%
21 | NIRMAL | 1054.77 | 39.36 | 748.61 | 787.97 | 74.71%
22 | NIZAMABAD | 2239.83 | 90.12 | 1588.52 | 1678.64 | 74.94%
23 | PEDDAPALLI | 699.28 | 34.44 | 495.45 | 529.89 | 75.78%
24 | RAJANNA | 730.59 | 29.71 | 518.26 | 547.97 | 75%
25 | RANGA REDDY | 3065.96 | 123.01 | 2173.86 | 2296.87 | 74.92%
26 | SANGAREDDY | 2433.29 | 89.01 | 1725.55 | 1814.56 | 74.57%
27 | SIDDIPET | 1728.59 | 75.16 | 1224.96 | 1300.12 | 75.21%
28 | SURYAPET | 1219.69 | 53.01 | 865.12 | 918.13 | 75.28%
29 | VIKARABAD | 1940.35 | 73.11 | 1376.39 | 1449.5 | 74.7%
30 | WANAPARTHY | 956.91 | 38.12 | 678.72 | 716.84 | 74.91%
31 | WARANGAL (R) | 743.32 | 25.16 | 527.29 | 552.45 | 74.32%
32 | WARANGAL (U) | 958.12 | 35.1 | 679.55 | 714.65 | 74.59%
33 | YADADRI | 939.52 | 35.43 | 665.61 | 701.04 | 74.62%
| TOTAL | 46350.25 | 1842.82 | 32877.62 | 34720.44 | 74.91%
3.6) Foodgrains Allocation, Lifting (availibility) & Utilisation
Allocation | T. Availibility | % T. Availibility | Utilisation | % Utilisation
46350.25 | 34720.44 | 74.91% | 29362.66 | 63.35%
3.7) District-wise Utilisation of foodgrains (Source data: Table AT-6 & 6A of AWP&B 2020-21)
Sl. No. | District | Allocation | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5
1 | ADILABAD | 1428.83 | 908.87 | 63.61%
2 | BHADRADRI | 1464.29 | 935.05 | 63.86%
3 | HYDERABAD | 3285.93 | 2085.18 | 63.46%
4 | JAGITIAL | 1204 | 760.41 | 63.16%
5 | JANAGOAN | 762.87 | 481.1 | 63.06%
6 | JAYASHANKAR | 462.39 | 293.18 | 63.41%
7 | JOGULAMBA | 1357.19 | 861.1 | 63.45%
8 | KAMAREDDY | 1768.4 | 1122.55 | 63.48%
9 | KARIMNAGAR | 885.94 | 558.95 | 63.09%
10 | KHAMMAM | 1768.83 | 1122.16 | 63.44%
11 | KOMRAM BHEEM | 976.07 | 621.88 | 63.71%
12 | MAHABUBABAD | 1048.16 | 666.01 | 63.54%
13 | MAHABUBNAGAR | 1638.08 | 1037.88 | 63.36%
14 | MANCHERIAL | 972.58 | 614.36 | 63.17%
15 | MEDAK | 1638.7 | 1036.41 | 63.25%
16 | MEDCHAL | 1719.64 | 1087.02 | 63.21%
17 | MULUGU | 393.07 | 250.71 | 63.78%
18 | NAGARKURNOOL | 1359.39 | 861.01 | 63.34%
19 | NALGONDA | 2216.31 | 1402.27 | 63.27%
20 | NARAYANPET | 1289.36 | 816.27 | 63.31%
21 | NIRMAL | 1054.77 | 669.18 | 63.44%
22 | NIZAMABAD | 2239.83 | 1420.2 | 63.41%
23 | PEDDAPALLI | 699.28 | 441.21 | 63.09%
24 | RAJANNA | 730.59 | 462.75 | 63.34%
25 | RANGA REDDY | 3065.96 | 1939 | 63.24%
26 | SANGAREDDY | 2433.29 | 1539.65 | 63.27%
27 | SIDDIPET | 1728.59 | 1091.33 | 63.13%
28 | SURYAPET | 1219.69 | 772.26 | 63.32%
29 | VIKARABAD | 1940.35 | 1228.87 | 63.33%
30 | WANAPARTHY | 956.91 | 605.86 | 63.31%
31 | WARANGAL (R) | 743.32 | 470.81 | 63.34%
32 | WARANGAL (U) | 958.12 | 606.55 | 63.31%
33 | YADADRI | 939.52 | 592.62 | 63.08%
| TOTAL | 46350.25 | 29362.66 | 63.35%
3.8) Cost of Foodgrains, Payment to FCI
Allocation | Bills submited by FCI | Payment made to FCI | % payment
1390.51 | 986.3286 | 959.0486 | 97.23%
3.9) Payment of cost of foodgrain to FCI
Sl. No. | District | Allocation | Bills raised by FCI | Payment to FCI | Pending Bills | % Bill paid
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | ADILABAD | 44.32 | 30.4482 | 30.4482 | 0 | 100%
2 | BHADRADRI | 45.62 | 31.2099 | 31.2099 | 0 | 100%
3 | HYDERABAD | 100.13 | 69.9702 | 42.6902 | 27.28 | 61.01%
4 | JAGITIAL | 35.39 | 25.5993 | 25.5993 | 0 | 100%
5 | JANAGOAN | 22.17 | 16.2126 | 16.2126 | 0 | 100%
6 | JAYASHANKAR | 14 | 9.8436 | 9.8436 | 0 | 100%
7 | JOGULAMBA | 41.31 | 28.8984 | 28.8984 | 0 | 100%
8 | KAMAREDDY | 53.46 | 37.6437 | 37.6437 | 0 | 100%
9 | KARIMNAGAR | 25.83 | 18.8304 | 18.8304 | 0 | 100%
10 | KHAMMAM | 53.22 | 37.6452 | 37.6452 | 0 | 100%
11 | KOMRAM BHEEM | 30.63 | 20.8107 | 20.8107 | 0 | 100%
12 | MAHABUBABAD | 31.79 | 22.3149 | 22.3149 | 0 | 100%
13 | MAHABUBNAGAR | 49.25 | 34.8615 | 34.8615 | 0 | 100%
14 | MANCHERIAL | 28.62 | 20.6802 | 20.6802 | 0 | 100%
15 | MEDAK | 48.69 | 34.8573 | 34.8573 | 0 | 100%
16 | MEDCHAL | 50.88 | 36.5727 | 36.5727 | 0 | 100%
17 | MULUGU | 12.32 | 8.3802 | 8.3802 | 0 | 100%
18 | NAGARKURNOOL | 40.81 | 28.9281 | 28.9281 | 0 | 100%
19 | NALGONDA | 66.04 | 47.1498 | 47.1498 | 0 | 100%
20 | NARAYANPET | 38.6 | 27.435 | 27.435 | 0 | 100%
21 | NIRMAL | 32.08 | 22.4583 | 22.4583 | 0 | 100%
22 | NIZAMABAD | 66.93 | 47.6556 | 47.6556 | 0 | 100%
23 | PEDDAPALLI | 20.4 | 14.8635 | 14.8635 | 0 | 100%
24 | RAJANNA | 21.95 | 15.5478 | 15.5478 | 0 | 100%
25 | RANGA REDDY | 91.06 | 65.2158 | 65.2158 | 0 | 100%
26 | SANGAREDDY | 72.54 | 51.7665 | 51.7665 | 0 | 100%
27 | SIDDIPET | 50.66 | 36.7488 | 36.7488 | 0 | 100%
28 | SURYAPET | 36.54 | 25.9536 | 25.9536 | 0 | 100%
29 | VIKARABAD | 58.25 | 41.2917 | 41.2917 | 0 | 100%
30 | WANAPARTHY | 28.67 | 20.3616 | 20.3616 | 0 | 100%
31 | WARANGAL (R) | 22.33 | 15.8187 | 15.8187 | 0 | 100%
32 | WARANGAL (U) | 28.67 | 20.3865 | 20.3865 | 0 | 100%
33 | YADADRI | 27.35 | 19.9683 | 19.9683 | 0 | 100%
| TOTAL | 1390.51 | 986.3286 | 959.0486 | 27.28 | 97.23%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 01.04.2019 (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2019 | % of OB on allocation
1 | 2 | 3 | 4 | 5
1 | ADILABAD | 840.23 | 23.07 | 2.746%
2 | BHADRADRI | 925.16 | 23.64 | 2.555%
3 | HYDERABAD | 1953.29 | 53.05 | 2.716%
4 | JAGITIAL | 745.17 | 19.43 | 2.607%
5 | JANAGOAN | 473.53 | 12.31 | 2.6%
6 | JAYASHANKAR | 304.36 | 7.46 | 2.451%
7 | JOGULAMBA | 825.99 | 21.91 | 2.653%
8 | KAMAREDDY | 1085.26 | 28.55 | 2.631%
9 | KARIMNAGAR | 556.73 | 14.3 | 2.569%
10 | KHAMMAM | 1107.85 | 28.55 | 2.577%
11 | KOMRAM BHEEM | 629.09 | 15.76 | 2.505%
12 | MAHABUBABAD | 663.93 | 16.92 | 2.548%
13 | MAHABUBNAGAR | 1043.41 | 26.45 | 2.535%
14 | MANCHERIAL | 621.1 | 15.69 | 2.526%
15 | MEDAK | 1022.1 | 26.45 | 2.588%
16 | MEDCHAL | 1049.71 | 27.76 | 2.645%
17 | MULUGU | 247.08 | 6.34 | 2.566%
18 | NAGARKURNOOL | 874.6 | 21.95 | 2.51%
19 | NALGONDA | 1313.05 | 35.78 | 2.725%
20 | NARAYANPET | 795.74 | 20.81 | 2.615%
21 | NIRMAL | 667.09 | 17.03 | 2.553%
22 | NIZAMABAD | 1333.63 | 36.16 | 2.711%
23 | PEDDAPALLI | 429.91 | 11.28 | 2.624%
24 | RAJANNA | 427.2 | 11.8 | 2.762%
25 | RANGA REDDY | 1895.85 | 49.49 | 2.61%
26 | SANGAREDDY | 1466.21 | 39.28 | 2.679%
27 | SIDDIPET | 1010.36 | 27.9 | 2.761%
28 | SURYAPET | 793.68 | 19.68 | 2.48%
29 | VIKARABAD | 1201.68 | 31.32 | 2.606%
30 | WANAPARTHY | 600.94 | 15.44 | 2.569%
31 | WARANGAL (R) | 454.89 | 12.01 | 2.64%
32 | WARANGAL (U) | 571.81 | 15.47 | 2.705%
33 | YADADRI | 569.16 | 15.17 | 2.665%
| TOTAL | 28499.79 | 748.21 | 2.625%
4.1.2) District-wise unspent balance as on 31.03.2020 Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Unspent Balance as on 31.03.2020 | % of UB on allocation
1 | 2 | 3 | 4 | 5
1 | ADILABAD | 840.23 | 212.79 | 25.33%
2 | BHADRADRI | 925.16 | 217.54 | 23.51%
3 | HYDERABAD | 1953.29 | 494.1 | 25.3%
4 | JAGITIAL | 745.17 | 184.47 | 24.76%
5 | JANAGOAN | 473.53 | 117.55 | 24.82%
6 | JAYASHANKAR | 304.36 | 69.75 | 22.92%
7 | JOGULAMBA | 825.99 | 204.21 | 24.72%
8 | KAMAREDDY | 1085.26 | 267.01 | 24.6%
9 | KARIMNAGAR | 556.73 | 136.28 | 24.48%
10 | KHAMMAM | 1107.85 | 267.75 | 24.17%
11 | KOMRAM BHEEM | 629.09 | 144.42 | 22.96%
12 | MAHABUBABAD | 663.93 | 157.97 | 23.79%
13 | MAHABUBNAGAR | 1043.41 | 248.06 | 23.77%
14 | MANCHERIAL | 621.1 | 148.9 | 23.97%
15 | MEDAK | 1022.1 | 249.67 | 24.43%
16 | MEDCHAL | 1049.71 | 262.59 | 25.02%
17 | MULUGU | 247.08 | 58.19 | 23.55%
18 | NAGARKURNOOL | 874.6 | 206.04 | 23.56%
19 | NALGONDA | 1313.05 | 337.19 | 25.68%
20 | NARAYANPET | 795.74 | 195.69 | 24.59%
21 | NIRMAL | 667.09 | 158.75 | 23.8%
22 | NIZAMABAD | 1333.63 | 340.27 | 25.51%
23 | PEDDAPALLI | 429.91 | 107.54 | 25.01%
24 | RAJANNA | 427.2 | 110.68 | 25.91%
25 | RANGA REDDY | 1895.85 | 467.25 | 24.65%
26 | SANGAREDDY | 1466.21 | 370.1 | 25.24%
27 | SIDDIPET | 1010.36 | 265.22 | 26.25%
28 | SURYAPET | 793.68 | 185.02 | 23.31%
29 | VIKARABAD | 1201.68 | 294.06 | 24.47%
30 | WANAPARTHY | 600.94 | 145.17 | 24.16%
31 | WARANGAL (R) | 454.89 | 112.61 | 24.76%
32 | WARANGAL (U) | 571.81 | 145.43 | 25.43%
33 | YADADRI | 569.16 | 144.68 | 25.42%
| TOTAL | 28499.79 | 7026.95 | 24.66%
4.2) Cooking cost allocation and disbursed to Districts
(Rs. In lakh)
Allocation | OB as on 01.4.19 | Disbursed to Dist | Total Availibility | % Availibility
28499.79 | 748.21 | 24383.87 | 25132.08 | 88.18%
4.3) District-wise Cooking Cost availability (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2019 | Cooking assistance received | Total Availibility of cooking cost | % Availibility of cooking cost
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | ADILABAD | 840.23 | 23.07 | 754.88 | 777.95 | 92.59%
2 | BHADRADRI | 925.16 | 23.64 | 774.06 | 797.7 | 86.22%
3 | HYDERABAD | 1953.29 | 53.05 | 1732.09 | 1785.14 | 91.39%
4 | JAGITIAL | 745.17 | 19.43 | 631.78 | 651.21 | 87.39%
5 | JANAGOAN | 473.53 | 12.31 | 399.75 | 412.06 | 87.02%
6 | JAYASHANKAR | 304.36 | 7.46 | 243.55 | 251.01 | 82.47%
7 | JOGULAMBA | 825.99 | 21.91 | 715.3 | 737.21 | 89.25%
8 | KAMAREDDY | 1085.26 | 28.55 | 931.23 | 959.78 | 88.44%
9 | KARIMNAGAR | 556.73 | 14.3 | 464.41 | 478.71 | 85.99%
10 | KHAMMAM | 1107.85 | 28.55 | 930.89 | 959.44 | 86.6%
11 | KOMRAM BHEEM | 629.09 | 15.76 | 516.47 | 532.23 | 84.6%
12 | MAHABUBABAD | 663.93 | 16.92 | 552.16 | 569.08 | 85.71%
13 | MAHABUBNAGAR | 1043.41 | 26.45 | 862 | 888.45 | 85.15%
14 | MANCHERIAL | 621.1 | 15.69 | 510.43 | 526.12 | 84.71%
15 | MEDAK | 1022.1 | 26.45 | 861.03 | 887.48 | 86.83%
16 | MEDCHAL | 1049.71 | 27.76 | 903.11 | 930.87 | 88.68%
17 | MULUGU | 247.08 | 6.34 | 207.94 | 214.28 | 86.72%
18 | NAGARKURNOOL | 874.6 | 21.95 | 715.2 | 737.15 | 84.28%
19 | NALGONDA | 1313.05 | 35.78 | 1164.97 | 1200.75 | 91.45%
20 | NARAYANPET | 795.74 | 20.81 | 678.12 | 698.93 | 87.83%
21 | NIRMAL | 667.09 | 17.03 | 555.86 | 572.89 | 85.88%
22 | NIZAMABAD | 1333.63 | 36.16 | 1177.74 | 1213.9 | 91.02%
23 | PEDDAPALLI | 429.91 | 11.28 | 366.59 | 377.87 | 87.9%
24 | RAJANNA | 427.2 | 11.8 | 384.42 | 396.22 | 92.75%
25 | RANGA REDDY | 1895.85 | 49.49 | 1610.91 | 1660.4 | 87.58%
26 | SANGAREDDY | 1466.21 | 39.28 | 1279.09 | 1318.37 | 89.92%
27 | SIDDIPET | 1010.36 | 27.9 | 906.74 | 934.64 | 92.51%
28 | SURYAPET | 793.68 | 19.68 | 641.55 | 661.23 | 83.31%
29 | VIKARABAD | 1201.68 | 31.32 | 1020.87 | 1052.19 | 87.56%
30 | WANAPARTHY | 600.94 | 15.44 | 503.31 | 518.75 | 86.32%
31 | WARANGAL (R) | 454.89 | 12.01 | 391.12 | 403.13 | 88.62%
32 | WARANGAL (U) | 571.81 | 15.47 | 503.88 | 519.35 | 90.83%
33 | YADADRI | 569.16 | 15.17 | 492.42 | 507.59 | 89.18%
| TOTAL | 28499.79 | 748.21 | 24383.87 | 25132.08 | 88.18%
4.4) Cooking Cost Utilisation |  |  |  | (Rs. In lakh)
Allocation | Total available | % available | Utilisation | % Utilisation
28499.79 | 25132.08 | 88.18% | 18105.13 | 63.53%
4.5) District-wise Utilisation of Cooking cost (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Utilisation of Cooking assistance | % Utilisation
1 | 2 | 3 | 4 | 5
1 | ADILABAD | 840.23 | 565.16 | 67.26%
2 | BHADRADRI | 925.16 | 580.16 | 62.71%
3 | HYDERABAD | 1953.29 | 1291.04 | 66.1%
4 | JAGITIAL | 745.17 | 466.74 | 62.64%
5 | JANAGOAN | 473.53 | 294.51 | 62.19%
6 | JAYASHANKAR | 304.36 | 181.26 | 59.55%
7 | JOGULAMBA | 825.99 | 533 | 64.53%
8 | KAMAREDDY | 1085.26 | 692.77 | 63.83%
9 | KARIMNAGAR | 556.73 | 342.43 | 61.51%
10 | KHAMMAM | 1107.85 | 691.69 | 62.44%
11 | KOMRAM BHEEM | 629.09 | 387.81 | 61.65%
12 | MAHABUBABAD | 663.93 | 411.11 | 61.92%
13 | MAHABUBNAGAR | 1043.41 | 640.39 | 61.37%
14 | MANCHERIAL | 621.1 | 377.22 | 60.73%
15 | MEDAK | 1022.1 | 637.81 | 62.4%
16 | MEDCHAL | 1049.71 | 668.28 | 63.66%
17 | MULUGU | 247.08 | 156.09 | 63.17%
18 | NAGARKURNOOL | 874.6 | 531.11 | 60.73%
19 | NALGONDA | 1313.05 | 863.56 | 65.77%
20 | NARAYANPET | 795.74 | 503.24 | 63.24%
21 | NIRMAL | 667.09 | 414.14 | 62.08%
22 | NIZAMABAD | 1333.63 | 873.63 | 65.51%
23 | PEDDAPALLI | 429.91 | 270.33 | 62.88%
24 | RAJANNA | 427.2 | 285.54 | 66.84%
25 | RANGA REDDY | 1895.85 | 1193.15 | 62.93%
26 | SANGAREDDY | 1466.21 | 948.27 | 64.67%
27 | SIDDIPET | 1010.36 | 669.42 | 66.26%
28 | SURYAPET | 793.68 | 476.21 | 60%
29 | VIKARABAD | 1201.68 | 758.13 | 63.09%
30 | WANAPARTHY | 600.94 | 373.58 | 62.17%
31 | WARANGAL (R) | 454.89 | 290.52 | 63.87%
32 | WARANGAL (U) | 571.81 | 373.92 | 65.39%
33 | YADADRI | 569.16 | 362.91 | 63.76%
| TOTAL | 28499.79 | 18105.13 | 63.53%
5. Reconciliation of Utilisation and Performance during 2019-20 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost (Source data: para 3.7 and 4.5 above)
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | ADILABAD | 63.61% | 67.26% | 3.653%
2 | BHADRADRI | 63.86% | 62.71% | -1.148%
3 | HYDERABAD | 63.46% | 66.1% | 2.638%
4 | JAGITIAL | 63.16% | 62.64% | -0.5216%
5 | JANAGOAN | 63.06% | 62.19% | -0.8699%
6 | JAYASHANKAR | 63.41% | 59.55% | -3.851%
7 | JOGULAMBA | 63.45% | 64.53% | 1.081%
8 | KAMAREDDY | 63.48% | 63.83% | 0.3562%
9 | KARIMNAGAR | 63.09% | 61.51% | -1.584%
10 | KHAMMAM | 63.44% | 62.44% | -1.005%
11 | KOMRAM BHEEM | 63.71% | 61.65% | -2.066%
12 | MAHABUBABAD | 63.54% | 61.92% | -1.62%
13 | MAHABUBNAGAR | 63.36% | 61.37% | -1.985%
14 | MANCHERIAL | 63.17% | 60.73% | -2.434%
15 | MEDAK | 63.25% | 62.4% | -0.8439%
16 | MEDCHAL | 63.21% | 63.66% | 0.4512%
17 | MULUGU | 63.78% | 63.17% | -0.6087%
18 | NAGARKURNOOL | 63.34% | 60.73% | -2.612%
19 | NALGONDA | 63.27% | 65.77% | 2.497%
20 | NARAYANPET | 63.31% | 63.24% | -0.06639%
21 | NIRMAL | 63.44% | 62.08% | -1.362%
22 | NIZAMABAD | 63.41% | 65.51% | 2.101%
23 | PEDDAPALLI | 63.09% | 62.88% | -0.2143%
24 | RAJANNA | 63.34% | 66.84% | 3.501%
25 | RANGA REDDY | 63.24% | 62.93% | -0.308%
26 | SANGAREDDY | 63.27% | 64.67% | 1.4%
27 | SIDDIPET | 63.13% | 66.26% | 3.121%
28 | SURYAPET | 63.32% | 60% | -3.316%
29 | VIKARABAD | 63.33% | 63.09% | -0.2432%
30 | WANAPARTHY | 63.31% | 62.17% | -1.148%
31 | WARANGAL (R) | 63.34% | 63.87% | 0.5272%
32 | WARANGAL (U) | 63.31% | 65.39% | 2.086%
33 | YADADRI | 63.08% | 63.76% | 0.6855%
| TOTAL | 63.35% | 63.53% | 0.1777%
5.2 Reconciliation of Food grains utilisation during 2019-20 (Source data: para 2.7 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 2019-20 | Expected consumption of food grains | Actual consumption of food grains | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | ADILABAD | 7911218 | 908.8713 | 908.87 | 100%
2 | BHADRADRI | 8163500 | 935.0532 | 935.05 | 100%
3 | HYDERABAD | 17874224 | 2085.1813 | 2085.18 | 100%
4 | JAGITIAL | 6316840 | 760.4066 | 760.41 | 100%
5 | JANAGOAN | 3957584 | 481.1021 | 481.1 | 100%
6 | JAYASHANKAR | 2499876 | 293.1848 | 293.18 | 100%
7 | JOGULAMBA | 7373702 | 861.1079 | 861.1 | 100%
8 | KAMAREDDY | 9554340 | 1122.5467 | 1122.55 | 100%
9 | KARIMNAGAR | 4610914 | 558.9487 | 558.95 | 100%
10 | KHAMMAM | 9510966 | 1122.1552 | 1122.16 | 100%
11 | KOMRAM BHEEM | 5468538 | 621.8722 | 621.88 | 100%
12 | MAHABUBABAD | 5683612 | 666.007 | 666.01 | 100%
13 | MAHABUBNAGAR | 8793534 | 1037.8849 | 1037.88 | 100%
14 | MANCHERIAL | 5109562 | 614.3593 | 614.36 | 100%
15 | MEDAK | 8691264 | 1036.4089 | 1036.41 | 100%
16 | MEDCHAL | 9083262 | 1087.0163 | 1087.02 | 100%
17 | MULUGU | 2200912 | 250.7102 | 250.71 | 100%
18 | NAGARKURNOOL | 7285048 | 861.0107 | 861.01 | 100%
19 | NALGONDA | 11789802 | 1402.2737 | 1402.27 | 100%
20 | NARAYANPET | 6890380 | 816.2754 | 816.27 | 100%
21 | NIRMAL | 5727342 | 669.1774 | 669.18 | 100%
22 | NIZAMABAD | 11964658 | 1420.1992 | 1420.2 | 100%
23 | PEDDAPALLI | 3640952 | 441.2071 | 441.21 | 100%
24 | RAJANNA | 3918716 | 462.7504 | 462.75 | 100%
25 | RANGA REDDY | 16255040 | 1938.9997 | 1939 | 100%
26 | SANGAREDDY | 12949680 | 1539.6468 | 1539.65 | 100%
27 | SIDDIPET | 9044236 | 1091.3297 | 1091.33 | 100%
28 | SURYAPET | 6523662 | 772.2566 | 772.26 | 100%
29 | VIKARABAD | 10398612 | 1228.8687 | 1228.87 | 100%
30 | WANAPARTHY | 5117146 | 605.8589 | 605.86 | 100%
31 | WARANGAL (R) | 3986656 | 470.8084 | 470.81 | 100%
32 | WARANGAL (U) | 5118568 | 606.5462 | 606.55 | 100%
33 | YADADRI | 4881726 | 592.6343 | 592.62 | 100%
| TOTAL | 248296072 | 29362.6598 | 29362.66 | 100%
5.3 Reconciliation of Cooking Cost utilisation during 2019-20 (Source data: para 2.5 and 4.7 above)
(Rs. in Lakh)
Sr. No. | District | No. of Meals served during 2019-20 | Expected expenditure of cooking cost | Actual expenditure of cooking cost | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | ADILABAD | 7911218 | 565.16 | 565.16 | 100%
2 | BHADRADRI | 8163500 | 580.16 | 580.16 | 100%
3 | HYDERABAD | 17874224 | 1291.04 | 1291.04 | 100%
4 | JAGITIAL | 6316840 | 466.74 | 466.74 | 100%
5 | JANAGOAN | 3957584 | 294.51 | 294.51 | 100%
6 | JAYASHANKAR | 2499876 | 181.26 | 181.26 | 100%
7 | JOGULAMBA | 7373702 | 533 | 533 | 100%
8 | KAMAREDDY | 9554340 | 692.77 | 692.77 | 100%
9 | KARIMNAGAR | 4610914 | 342.43 | 342.43 | 100%
10 | KHAMMAM | 9510966 | 691.69 | 691.69 | 100%
11 | KOMRAM BHEEM | 5468538 | 387.81 | 387.81 | 100%
12 | MAHABUBABAD | 5683612 | 411.11 | 411.11 | 100%
13 | MAHABUBNAGAR | 8793534 | 640.39 | 640.39 | 100%
14 | MANCHERIAL | 5109562 | 377.22 | 377.22 | 100%
15 | MEDAK | 8691264 | 637.81 | 637.81 | 100%
16 | MEDCHAL | 9083262 | 668.28 | 668.28 | 100%
17 | MULUGU | 2200912 | 156.09 | 156.09 | 100%
18 | NAGARKURNOOL | 7285048 | 531.11 | 531.11 | 100%
19 | NALGONDA | 11789802 | 863.56 | 863.56 | 100%
20 | NARAYANPET | 6890380 | 503.24 | 503.24 | 100%
21 | NIRMAL | 5727342 | 414.14 | 414.14 | 100%
22 | NIZAMABAD | 11964658 | 873.63 | 873.63 | 100%
23 | PEDDAPALLI | 3640952 | 270.33 | 270.33 | 100%
24 | RAJANNA | 3918716 | 285.54 | 285.54 | 100%
25 | RANGA REDDY | 16255040 | 1193.15 | 1193.15 | 100%
26 | SANGAREDDY | 12949680 | 948.27 | 948.27 | 100%
27 | SIDDIPET | 9044236 | 669.42 | 669.42 | 100%
28 | SURYAPET | 6523662 | 476.21 | 476.21 | 100%
29 | VIKARABAD | 10398612 | 758.13 | 758.13 | 100%
30 | WANAPARTHY | 5117146 | 373.58 | 373.58 | 100%
31 | WARANGAL (R) | 3986656 | 290.52 | 290.52 | 100%
32 | WARANGAL (U) | 5118568 | 373.92 | 373.92 | 100%
33 | YADADRI | 4881726 | 362.91 | 362.91 | 100%
| TOTAL | 248296072 | 18105.13 | 18105.13 | 100%
6. ANALYSIS of HONORIUM, To COOK-CUM-HELPERS
6.1) District-wise number of cook-cum-Helpers approved by PAB and engaged by State
(Refer table AT_8 and AT-8A, AWP&B, 2020-21)
S.No. | Name of District | PAB Approval | Engaged by State | Not engaged
1 | 2 | 3 | 4 | 5 = (4 - 3)
1 | ADILABAD | 1843 | 1840 | -3
2 | BHADRADRI | 2225 | 2219 | -6
3 | HYDERABAD | 1159 | 1159 | 0
4 | JAGITIAL | 1566 | 1564 | -2
5 | JANAGOAN | 1092 | 1092 | 0
6 | JAYASHANKAR | 784 | 784 | 0
7 | JOGULAMBA | 1204 | 1204 | 0
8 | KAMAREDDY | 2002 | 2002 | 0
9 | KARIMNAGAR | 1134 | 1134 | 0
10 | KHAMMAM | 2434 | 2429 | -5
11 | KOMRAM BHEEM | 1581 | 1581 | 0
12 | MAHABUBABAD | 1700 | 1700 | 0
13 | MAHABUBNAGAR | 1965 | 1965 | 0
14 | MANCHERIAL | 1290 | 1290 | 0
15 | MEDAK | 2325 | 2323 | -2
16 | MEDCHAL | 1159 | 1156 | -3
17 | MULUGU | 636 | 636 | 0
18 | NAGARKURNOOL | 1863 | 1863 | 0
19 | NALGONDA | 2903 | 2903 | 0
20 | NARAYANPET | 1524 | 1524 | 0
21 | NIRMAL | 1286 | 1285 | -1
22 | NIZAMABAD | 2283 | 2281 | -2
23 | PEDDAPALLI | 1123 | 1123 | 0
24 | RAJANNA | 863 | 863 | 0
25 | RANGA REDDY | 2693 | 2693 | 0
26 | SANGAREDDY | 2660 | 2658 | -2
27 | SIDDIPET | 2051 | 2051 | 0
28 | SURYAPET | 1892 | 1891 | -1
29 | VIKARABAD | 1949 | 1949 | 0
30 | WANAPARTHY | 1226 | 1226 | 0
31 | WARANGAL (R) | 1332 | 1330 | -2
32 | WARANGAL (U) | 1089 | 1087 | -2
33 | YADADRI | 1396 | 1396 | 0
| TOTAL | 54232 | 54201 | -31
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
(Refer table AT_8 and AT-8A, AWP&B, 2020-21)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2019 | Amount released | Total availability | % Availibilty
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | ADILABAD | 184.3 | 0 | 184.3 | 184.3 | 100%
2 | BHADRADRI | 222.5 | 0 | 222.5 | 222.5 | 100%
3 | HYDERABAD | 115.9 | 0 | 115.9 | 115.9 | 100%
4 | JAGITIAL | 156.6 | 0 | 156.6 | 156.6 | 100%
5 | JANAGOAN | 109.2 | 0 | 109.2 | 109.2 | 100%
6 | JAYASHANKAR | 78.4 | 0 | 78.4 | 78.4 | 100%
7 | JOGULAMBA | 120.4 | 0 | 120.4 | 120.4 | 100%
8 | KAMAREDDY | 200.2 | 0 | 200.2 | 200.2 | 100%
9 | KARIMNAGAR | 113.4 | 0 | 113.4 | 113.4 | 100%
10 | KHAMMAM | 243.4 | 0 | 243.4 | 243.4 | 100%
11 | KOMRAM BHEEM | 158.1 | 0 | 158.1 | 158.1 | 100%
12 | MAHABUBABAD | 170 | 0 | 170 | 170 | 100%
13 | MAHABUBNAGAR | 196.5 | 0 | 196.5 | 196.5 | 100%
14 | MANCHERIAL | 129 | 0 | 129 | 129 | 100%
15 | MEDAK | 232.5 | 0 | 232.5 | 232.5 | 100%
16 | MEDCHAL | 115.9 | 0 | 115.9 | 115.9 | 100%
17 | MULUGU | 63.6 | 0 | 63.6 | 63.6 | 100%
18 | NAGARKURNOOL | 186.3 | 0 | 186.3 | 186.3 | 100%
19 | NALGONDA | 290.3 | 0 | 290.3 | 290.3 | 100%
20 | NARAYANPET | 152.4 | 0 | 152.4 | 152.4 | 100%
21 | NIRMAL | 128.6 | 0 | 128.6 | 128.6 | 100%
22 | NIZAMABAD | 228.3 | 0 | 228.3 | 228.3 | 100%
23 | PEDDAPALLI | 112.3 | 0 | 112.3 | 112.3 | 100%
24 | RAJANNA | 86.3 | 0 | 86.3 | 86.3 | 100%
25 | RANGA REDDY | 269.3 | 0 | 269.3 | 269.3 | 100%
26 | SANGAREDDY | 266 | 0 | 266 | 266 | 100%
27 | SIDDIPET | 205.1 | 0 | 205.1 | 205.1 | 100%
28 | SURYAPET | 189.2 | 0 | 189.2 | 189.2 | 100%
29 | VIKARABAD | 194.9 | 0 | 194.9 | 194.9 | 100%
30 | WANAPARTHY | 122.6 | 0 | 122.6 | 122.6 | 100%
31 | WARANGAL (R) | 133.2 | 0 | 133.2 | 133.2 | 100%
32 | WARANGAL (U) | 108.9 | 0 | 108.9 | 108.9 | 100%
33 | YADADRI | 139.6 | 0 | 139.6 | 139.6 | 100%
| TOTAL | 5423.2 | 0 | 5423.2 | 5423.2 | 100%
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2020-21)
S.No. | Name of District | Allocation | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation
1 | 2 | 3 | 4 | 5 | 6
1 | ADILABAD | 184.3 | 184.3 | 128.8 | 69.89%
2 | BHADRADRI | 222.5 | 222.5 | 155.33 | 69.81%
3 | HYDERABAD | 115.9 | 115.9 | 81.13 | 70%
4 | JAGITIAL | 156.6 | 156.6 | 109.48 | 69.91%
5 | JANAGOAN | 109.2 | 109.2 | 76.44 | 70%
6 | JAYASHANKAR | 78.4 | 78.4 | 54.88 | 70%
7 | JOGULAMBA | 120.4 | 120.4 | 84.28 | 70%
8 | KAMAREDDY | 200.2 | 200.2 | 140.14 | 70%
9 | KARIMNAGAR | 113.4 | 113.4 | 79.38 | 70%
10 | KHAMMAM | 243.4 | 243.4 | 170.03 | 69.86%
11 | KOMRAM BHEEM | 158.1 | 158.1 | 110.67 | 70%
12 | MAHABUBABAD | 170 | 170 | 119 | 70%
13 | MAHABUBNAGAR | 196.5 | 196.5 | 137.55 | 70%
14 | MANCHERIAL | 129 | 129 | 90.3 | 70%
15 | MEDAK | 232.5 | 232.5 | 162.61 | 69.94%
16 | MEDCHAL | 115.9 | 115.9 | 80.92 | 69.82%
17 | MULUGU | 63.6 | 63.6 | 44.52 | 70%
18 | NAGARKURNOOL | 186.3 | 186.3 | 130.41 | 70%
19 | NALGONDA | 290.3 | 290.3 | 203.21 | 70%
20 | NARAYANPET | 152.4 | 152.4 | 106.68 | 70%
21 | NIRMAL | 128.6 | 128.6 | 89.95 | 69.95%
22 | NIZAMABAD | 228.3 | 228.3 | 159.67 | 69.94%
23 | PEDDAPALLI | 112.3 | 112.3 | 78.61 | 70%
24 | RAJANNA | 86.3 | 86.3 | 60.41 | 70%
25 | RANGA REDDY | 269.3 | 269.3 | 188.51 | 70%
26 | SANGAREDDY | 266 | 266 | 186.06 | 69.95%
27 | SIDDIPET | 205.1 | 205.1 | 143.57 | 70%
28 | SURYAPET | 189.2 | 189.2 | 132.37 | 69.96%
29 | VIKARABAD | 194.9 | 194.9 | 136.43 | 70%
30 | WANAPARTHY | 122.6 | 122.6 | 85.82 | 70%
31 | WARANGAL (R) | 133.2 | 133.2 | 93.1 | 69.89%
32 | WARANGAL (U) | 108.9 | 108.9 | 76.09 | 69.87%
33 | YADADRI | 139.6 | 139.6 | 97.71 | 69.99%
| TOTAL | 5423.2 | 5423.2 | 3794.06 | 69.96%
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2020-21)
S.No. | Name of District | Allocation | Total Availability | Unspent balance as on 31.03.2020 | % of UB as on Allocation
1 | 2 | 3 | 4 | 5 | 6
1 | ADILABAD | 184.3 | 184.3 | 55.5 | 30.11%
2 | BHADRADRI | 222.5 | 222.5 | 67.17 | 30.19%
3 | HYDERABAD | 115.9 | 115.9 | 34.77 | 30%
4 | JAGITIAL | 156.6 | 156.6 | 47.12 | 30.09%
5 | JANAGOAN | 109.2 | 109.2 | 32.76 | 30%
6 | JAYASHANKAR | 78.4 | 78.4 | 23.52 | 30%
7 | JOGULAMBA | 120.4 | 120.4 | 36.12 | 30%
8 | KAMAREDDY | 200.2 | 200.2 | 60.06 | 30%
9 | KARIMNAGAR | 113.4 | 113.4 | 34.02 | 30%
10 | KHAMMAM | 243.4 | 243.4 | 73.37 | 30.14%
11 | KOMRAM BHEEM | 158.1 | 158.1 | 47.43 | 30%
12 | MAHABUBABAD | 170 | 170 | 51 | 30%
13 | MAHABUBNAGAR | 196.5 | 196.5 | 58.95 | 30%
14 | MANCHERIAL | 129 | 129 | 38.7 | 30%
15 | MEDAK | 232.5 | 232.5 | 69.89 | 30.06%
16 | MEDCHAL | 115.9 | 115.9 | 34.98 | 30.18%
17 | MULUGU | 63.6 | 63.6 | 19.08 | 30%
18 | NAGARKURNOOL | 186.3 | 186.3 | 55.89 | 30%
19 | NALGONDA | 290.3 | 290.3 | 87.09 | 30%
20 | NARAYANPET | 152.4 | 152.4 | 45.72 | 30%
21 | NIRMAL | 128.6 | 128.6 | 38.65 | 30.05%
22 | NIZAMABAD | 228.3 | 228.3 | 68.63 | 30.06%
23 | PEDDAPALLI | 112.3 | 112.3 | 33.69 | 30%
24 | RAJANNA | 86.3 | 86.3 | 25.89 | 30%
25 | RANGA REDDY | 269.3 | 269.3 | 80.79 | 30%
26 | SANGAREDDY | 266 | 266 | 79.94 | 30.05%
27 | SIDDIPET | 205.1 | 205.1 | 61.53 | 30%
28 | SURYAPET | 189.2 | 189.2 | 56.83 | 30.04%
29 | VIKARABAD | 194.9 | 194.9 | 58.47 | 30%
30 | WANAPARTHY | 122.6 | 122.6 | 36.78 | 30%
31 | WARANGAL (R) | 133.2 | 133.2 | 40.1 | 30.11%
32 | WARANGAL (U) | 108.9 | 108.9 | 32.81 | 30.13%
33 | YADADRI | 139.6 | 139.6 | 41.89 | 30.01%
| TOTAL | 5423.2 | 5423.2 | 1629.14 | 30.04%
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
7.1) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2019-20 | 473.72 | 473.72 | 0 | 0%
2 | Opening Balance as on 01.04.2019 | 107.07 | 107.07 | 0 | 0%
3 | Released during 2019-20. | 366.65 | 366.65 | 0 | 0%
4 | Total Availibility | 473.72 | 473.72 | 0 | 0%
7.2) Utilisation of MME during 2019-20 (Source data: Table AT-10 of AWP&B 2020-21)
|  |  |  | (Rs. In lakh) | (As on 31.03.19)
Sl. No. | Activity | Allocated | Total Availibility | Expenditure | Exp as % of allocation
1 | 2 | 3 | 4 | 5 | 6
1 | School Level Expenses | 236.86 | 236.86 | 123 | 51.93%
2 | Management, Supervision, Training & Internal Monitoring, External Monitoring & Evaluation | 236.86 | 236.86 | 109.36 | 46.17%
Total |  | 473.72 | 473.72 | 232.36 | 49.05%
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
8.1) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Activity | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2019-20 | 495.36 | 495.36 | 0 | 0%
2 | Opening Balance as on 01.04.2019 | 13.6 | 13.6 | 0 | 0%
3 | Released during 2019-20. | 481.76 | 481.76 | 0 | 0%
4 | Total Availibility | 495.36 | 495.36 | 0 | 0%
8.2) Utilisation of TA during 2019-20 (Source data: Table AT-9 of AWP&B 2020-21)
(Rs. In lakh)
Allocated for 2019-20 | Total availibility of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7 | 8= (2-5)
495.36 | 495.36 | 32877.62 | 365.9279 | 355.81 | 10.1179 | 71.83% | 139.55
9. INFRASTRUCTURE DEVELOPMENT DURING 2019-20 (Primary + Upper primary)
Kitchen-cum-Stores
9.1) Releasing details
9.1.1) Releasing details
Releases for Kitchen sheds by GoI as on 31.3.2020
Schools | Installment | Dated | Units | Amount (Rs in lakh)
Primary + Upper-Primary | 2006-07 - 2012-13 |  | 30408 | 23469.15
| Sub total |  | 30408 | 23469.15
9.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-13 | 30408 | 23469.15 | 30408 | 23469.15 | 0% | 0%
9.3) Achievement ( under MDM Funds) (Source data: Table AT-10 of AWP&B 2020-21)
Sanctioned by GoI during 2006-07 to 2019-20 |  | Cosntructed upto 31.12.20219 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
30408 | 23469.15 | 17483 | 13377.4155 | 57.49% | 57%
10. Kitchen Devices
10.1) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-10 | 32993 | 1649.66 | 32993 | 1649.66 | 100% | 100%
2012-15 (Replacement) | 30532 | 1526.6 | 0 | 0 | 0% | 0%
2019-20 (Rep @ new norms) | 16324 | 1425.81 | 16324 | 1425.81 | 100% | 100%
10.2) Achievement ( under MDM Funds) (Source data: Table AT-11 of AWP&B 2019-20)
| Sanctioned during 2006-07 to 2018-19 |  | Achievement (Procured+IP) |  | Achievement as % of allocation
| Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7
2006-10 | 32993 | 1649.66 | 32993 | 1649.66 | 100% | 100%
2012-13 -2018-19(Replacement) | 30532 | 1526.6 | 0 | 0 | 0 | 0
2019-20 (Rep @ new norms) | 16324 | 1425.81 | 0 | 0 | 0% | 0%
Benchmark (85%)
100%
68%